## June-2022
S.No. | Detail | Priority | Estimated Hours | Status | Remarks
1 | Incorporation of Extra details in standard report template of Chennai. | 1 | 8 | Done
2 | Provision to upload graphs in pdf form order booking wise on 'Dispatching' role and will be visible to customer on Customer portal. | 2 | 45
Flow: 1.Master Form Creation(New Migration) for admin and dispatcher in dispatching role which allow user to upload the file. 2.Changes on Data Synchronization logic with testing. 3.Changes on customer portal for saving the grapth in db. 4.Displaying and allowing customer to download the file in browser. 5.Testing of all above points.
3 | Incorporate 'Sampler Name' in Order Booking Form. Create new role of 'Sampler' to define in Employee master. | 4 | 16 | Done
Flow: 1.Changes on adding and editing of Employee master for adding Sampler checkbox just like sales executive. 2.Changes on adding and editing of order master for displaying Sampler Drop down in design and logic level. 4.Implementation of above coloums in listed Mis-Reports - Sales Report Detail, Daily booking Detail 5.Testing of all above points.
4 | Provision to give 'Test Report Ammenment' rights to user in Employee master. | 6 | 18
Flow: 1.Creation and provision of custom role in employee master 2.Changes on adding and editing of employee master 3.Changes on Report for assigning amendment right to user 4.Testing of all above points.
5 | Provision to define 'Reference Test Standard' in Order Booking Form. | 5 | 14
Flow: 1.Table creation for Report Analyis Only.No master form creation. 2.Changes on adding and editing of order master for displaying Report Analysis Drop down in design and logic level 3.Implementation of above coloums in listed Mis-Reports - Sales Report Detail, Daily booking Detail 4.Testing of all above points.
6 | QR Code generation in all report templates | 3 | 7 | Partial Done | 6 Hr per pdf format blade
| Flow: 1.QR Code Genration Plugin Installation and testing 2.Changes on Order booking adding logic. 3.Displaying fo QR Code in all PDF format of Test Report for all branches and departments. 4.Testing fo all above points. |  |  |  | 18 hr qr code functionality
Completed in Food Department for testing(Only In PDF for trail testing)
7 | Incorporate Discipline & Group in Building template | 7 | 8 | Done