## Timeline
S.No. | Task Name | Timeline(in hours) | Estimated Hours | Remarks |  | RD = Required Discussion
1 | Enquiry Module:
| Designing of Enquiry Form and Enquiry Creation(Multiple Items and No data from master in enquiry form,all will be manual input),Customer from Master | 8 | 20
| EDIT/DELETE/PRINT of Enquiry |  | 25
| Follow Up Module |  | 20
| Enquiry Reports(4 reports) |  | 50
2 (a) | Addition of variables in Product Test | 12 | 16 | Product Test and Coloning of Product Test
Detector Name
Running Time
No. of Injection
Chemical Name
Chemical Quantity
Standard Name if required
Column Name
Impurity Name
Testing method in multiple steps - Multiline text box
Glass Ware
(b) | Master form for Chemical Name,Standard Names etc. |  | 32 | 8 = Per Master Creation
3 | Pesticide Residue invoicing provision
| Master form for entering slab and slab wise rate. | 6 | 10
| Consideration of master form at the time of invoice generation | 8 | 18
Quotation Creation
| When Complete Product Test master is available | 40 | 100
From Test Parameter master when complete Product test master is not available
5 | Discount Provision for Quotation
| Master form for discount authority | 10 | 10
6 | Quotation to Order booking
| Changes in Sample Receiving Form | 15 | 60 | Development = 30
| Changes in Order Booking Form |  |  | Testing & Fixing= 30
7 | Order Booking to PI Generation
| Parameter wise rate will be added in order Confirmation Mail |  | 16
| Same format of order confirmation mail will be used as PI and will be shared with customer on every change in order booking | 15 | 16
| Adding cost of Sample Collection |  | 6
8 | MIS | As per the format | 72 | BUT IT WAS NOT IN SCOPE OF QTN
9 | Price List Management :
| Invoicing Structure in Product Test |  | 70
| Total | 114 | 541 |  | WITHOUT MIS 469