## May-2018
ITC ERP TASK DETAIL(May-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-01-05 | Software Update Feedback Points and Integration of DT Limit in Order Module: | 1 | 2018-05-02 | 2018-05-02 | 2018-05-02 | Praveen Singh | 9 | 7 | Done
2 | 2018-04-05 | Software Update | 2 | 2018-05-04 | 2018-05-04 | 2018-05-04 | Praveen Singh | 1 | 1 | Done
3 | 2018-04-05 | User Feedback Points(Discussed Points of Meeting) | 3 | 2018-05-04 | 2018-05-04 | 2018-05-04 | Praveen Singh | 9 | 9 | Done
4 | 2018-05-08 | User Feedback Points: 1.Implementation and Uploading of Signature for users. 2.Searching of Order in multisearch window of Invoice Landing page. 3.Corrected the order whose invoice has been already generated. 4.Corrected the order which is dispatched already but still show in dispatching. 5.Amendment of Invoices. 6.Changing of Booked order billing type from daily to monthly as it is booked in daily Billing Type. 7.Report Format modification in design. | 6 | 2018-05-08 | 2018-05-08 | 2018-05-08 | Praveen Singh | 9 | 9 | Done
5 | 2018-05-11 | 1.Displaying Of PO-Date Calender while adding a order having Billing Type PO-Wise. 2.Displaying of Product Name according to Sample Name and Product Name entered by the User. 3.Changes the discount value of Booked Orders. 4.Modified the Layout of Invoice generation Blade. | 9 | 2018-05-11 | 2018-05-11 | 2018-05-11 | Praveen Singh | 7 | 7 | Done
6 | 2018-05-15 | Displaying of Right Logo Dynamically on all Test Report Blade: | 11 | 2018-05-16 | 2018-05-16 | 2018-05-16 | Praveen Singh | 9 | 9 | Done
7 | 2018-05-17 | User Feedback Points: 1.Pharma Department Stamp not displaying on PDF Generation of Report 2.Pharma Department User Sign not displaying on PDF Generation of Report 3.Data Validation of Listed MIS-Reports: a)Analyst Wise Performance Summary b)Sample Log Status | 12 | 2018-05-17 | 2018-05-17 | 2018-05-17 | Praveen Singh | 9 | 9 | Done
8 | 2018-05-18 | A.Software Updates on Staging Server. 1.Updated Code on ITC Dev Staging Server from SVN. 2.Updated DB on ITC Dev Staging Server. B.User Feedback Points: 1.Removal of Duplicate Customer in Invoicing. 2.Changing of Billing Type in booked orders. 3.Discount Updation in booked Orders. | 13 | 2018-05-18 | 2018-05-18 | 2018-05-18 | Praveen Singh | 9 | 9 | Done
9 | 2018-05-21 | User Feedback Points: 1.Mailing of State and City DB. 2.Mail Sending issue in Invoice Section. 3.Customer Portal Link. 4.Dynamic Header Foooter Implementation on Invoice Section. 5.Food Test Report:Implementation of Dynamic Content. 6.Testile Test Report:Implementation of Dynamic Content with Replacement of Sample Reg. No. with Report No. from Reviewing to Dispatching Order Process. | 14 | 2018-05-21 | 2018-05-21 | 2018-05-21 | Praveen Singh | 9 | 9 | Done
10 | 2018-05-22 | Dynamic Header Implementation: Invoicing(All Division) | 16 | 2018-05-24 | 2018-05-24 | 2018-05-24 | Praveen Singh | 9 | 9 | Done
11 | 2018-05-23 | User Feedback Points: 1.Search Box for method & instruments on Scheduling Job Sheet Print is not updated yet. 2.Adding of Discount Type and discount value in listed booked orders: a)P01-1804280040 b)P01-1804270159 c)P01-1804270157 d)P01-1804260069 e)P01-1804260040 f)P01-1804260039 g)P01-1804210047 h)P01-1804190091 i)P01-1803100046 j)P01-1804170042 3.Correction in listed generated Invoice Numbers:T-1805220023. 4.In our TAT report,presently cancelled samples are displayed pending for scheduling which is incorrect.Please replace 'P' with 'H' for hold samples at the time of scheduling.Similarly cancelled samples are also displayed as 'P' in scheduling or testing: Case I :- In Case of Hold Samples,the status of sample will be "Hold" & In Scheduling column we can use the alphabet 'H' in place of 'P' Case II :- In case of Cancelled samples,the status will be Cancelled and all the columns of that sample will be blank. | 17 | 2018-05-23 | 2018-05-23 | 2018-05-23 | Praveen Singh | 9 | 9 | Done
12 | 2018-05-24 | Client Feedback Points: 1.Give 30 % discount in below order booking codes: a.F01-1805160890,b.F01-1805050282,c.F01-1805050281,d.F01-1804301752 2.Convert invoicing type to customer wise product for below order nos.: a.F01-1805160883,b.F01-1805160882,c.F01-1805160881,d.F01-1805160880,e.F01-1805100517,f.F01-1805100516,g.F01-1805100515,h.F01-1805100514,i.F01-1804301774,j.F01-1804301773 3.JOB SHEET OF PHARMA NOT PRINTING:Order no are as follows:- P01-1805250052,P01-1805250055,P01-1805250056,P01-1805210113,P01-1805210114,P01-1805210116,P01-1805210117,P01-1805240107 | 18 | 2018-05-24 | 2018-05-24 | 2018-05-24 | Praveen Singh | 5 | 5 | Done
13 | 2018-05-28 | Client Feedback Points: 1.The interlaboratory or compensatory samples are reflected Pending for invoicing in TAT report. Replace interlaboratory samples with alphabet "I"(Interlaboratory) in place of "P" (Pending). 2.In order Booking Confirmation Mail Subject Line should be Customer Name,Sample Name,Batch No. & Order Booking No. 3.In Test Report Mail subject should be Customer Name,Sample Name,Batch No. & Order Booking No. Client Feedback Points: 4.One sample of Tirupati Life Sciences which is pending for invoicing in TAT report but in software Sales-Reports it is displayed in DIspatching Stage. Order No. is : F01-1804201296. a)Tirupati Life Sciences-F01-1804201296 b)Pritam International Glycerine having order no.-F01-1803301531.It is pending for invoicing in ERP & but dispatched in software. 5.We booked 16 samples of procter & gamble on 18 May and having expected due date of 25 May 2018 but when we generate TAT on 26052018 the expected due date of all samples changed to 23.5.2018. I want to know that does any one change the expected due date of samples or there in some problem in generation.Please send me the log of these samples or check on your end. | 19 | 2018-05-28 | 2018-05-28 | 2018-05-28 | Praveen Singh | 9 | 9 | Done
14 | 2018-05-29 | Scope-2 meeting and discussion with Client regarding listed Modules: 1.Auto Scheduling 2.Invoice Cancellation and Re-generation. 3.Auto Credit and Debit Note Updation on Invoice Cancellation and Re-generation. 4.MIS-Reports 5.Pop-up Implementation of user based on role assigned to it. 6.Message Popup Window on cancelaation of any order for all department. 7.Displaying of Schedulled Date and Completed Date in Assign Job Window of Scheduling. 8.Editing of Expected Due Daate for certain Customer based on record available in Custimer Defined Structure. | 20 | 2018-05-29 | 2018-05-29 | 2018-05-29 | Praveen Singh | 9 | 9 | Done
15 | 2018-05-30 | Client Feedback Points: 1.In Textile invoice : T-1805220023 Change Invoicing To customer code : 1528 in order no. T01-1805180028 2.In Food Invoice having invoice no. : F-1804260349-Change Invoicing to Cust Code 303( Marico Limited ) in only these two order no;s F01-1804231408 & F01-1804241463 3.One sample of Tirupati Life Sciences which is pending for invoicing in TAT report but in software Sales-Reports it is displayed in DIspatching Stage: a)Tirupati Life Sciences-F01-1804201296 b)Pritam International Glycerine having order no.-F01-1803301531.It is pending for invoicing in ERP & but dispatched in software. 4.On Genaration of Invoice Form,Provision of selection of all Department to administrator,so that administrator can generate invoice of multiple department simultaneously. 5.Displaying of rate inputed by the Invoicer or not at the time of Invoice Generation in Popup window on clicking any Orde/Report No.If not then 0.00 in Red color else inputed rate in green color. | 21 | 2018-05-30 | 2018-05-30 | 2018-05-30 | Praveen Singh | 9 | 9 | Done

## June-2018
ITC ERP TASK DETAIL(June-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Remarks
1 | 2018-06-01 | Small Amendments: -In Sales-Generate Invoices window add one more cols of Invoicing to (name of Customer invoice will be generated). -Provision of change of Customer name by the Administrator if the receiver will do the receiving on wrong name. | 1 | 2018-06-01 | 2018-06-01 | 2018-06-01 | Praveen Singh | 9 | 9 | Done | Task is in Scope-II
2 | 2018-06-08 | 1.Task Name:Regarding Back up:- a)Please update Invoice no. of F-1806050001 (Chennai) to F-1806080143 and invoice date will be 08.06.2018. 2.Printout of these invoices are not visible .Please check.Invoices are F-1805010433 & F-1805170702 | 2 | 2018-06-08 | 2018-06-08 | 2018-06-08 | Praveen Singh | 2 | 2 | Done
3 | 2018-06-11 | Changes discussed in dynamic header Implementation and provided in Mail: A.Pharma :- 1)Form 39 & License no. will be incorporated on top of Interstellar Testing Centre Pvt. Ltd. (already have in previous test report format) 2)NABL Certificate No. & its validity under the logo of ITC labs on left corner of report.(This certificate no. & validity will be changed with time). On printing of test report the certificate no. & validity displayed will be related to that corresponding time. B.Ayurvedic :- Format of Ayurveda will be same as that of Pharma.(No NABL Certificate No. & its validity is required.) | 3 | 2018-06-11 | 2018-06-12 | 2018-06-12 | Praveen Singh | 13 | 13 | Done | its was part of dynamic header implementation
4 | 2018-06-11 | Urgent Requirement of 2 MIS Reports: a)Sample log status b)Instrument & User wise performance Note:Changes Provided in a word document. | 4 | 2018-06-12 | 2018-06-16 | 2018-06-16 | Praveen Singh | 30 | 32 | Done | Mis Reports was Scope-I task
5 | 2018-06-14 | Client Feedback Points: 1.Ammendment in invoice a)In invoiceno .- F-1806090012 change amount into 3590 in place of 2630. The tax slab will be IGST :- 646 Total amount will be 4236 b)In invoiceno .- F-1806090012 change amount into 1600 in place of 1200. The tax slab will be SGST = 144 & CGST :- 144 Total amount will be 1888. | 5 | 2018-06-14 | 2018-06-14 | 2018-06-14 | Praveen Singh | 2 | 2 | Done
6 | 2018-06-14 | Software Updation on ITC Dev Server | 6 | 2018-06-14 | 2018-06-14 | 2018-06-14 | Praveen Singh | 2 | 2 | Done | it will not be included in new task list as per discussion with Antaryami Sir
7 | 2018-06-18 | A.Client Feedback points: 1)Correction: Invoice no. is F-1806140021 of Chennai branch Customer Name is Cargo Inspectors & Superitendence Co. Pvt. Ltd. This invoice has two samples :- Change the amount of Sample two of Black Tea having order no. F02-1806080042 . The present amount is 3590. Change this amount to 7630, Total amount will be Rs. 10260 IGST will be :- Rs. 1847 Total amount will be Rs. 12107 Do correction on priority B.TimeSheet:Filling of Timesheet and Email : Reviewing of Emails. C.R&D on Cross Domain Data Transfer regarding Web Module of ITC Customer Portal. 2)Pharma detail is not matching: There is some error in the TAT report. Yesterday reports were mailed we got the report from system generated email ID, but in TAT it is showing as pending. Pls find the screen shot for your information with example. I am unable to extract the actual data to share with everyone. Pls do the needful urgently. | 7 | 2018-06-18 | 2018-06-18 | 2018-06-18 | Praveen Singh | 2 | 2 | Done
8 | 2018-06-20 | Client Feed Points: 1)Change invoicing to Teijin Gurgaon(Cust code is 595): Textile invoice no are T-1806110040 & T-1805260027 2)Change is in the name of customer in following orders: a)P01-1806110129 b)P01-1806110130 Currently it is booked in Procter & Gamble Hygiene and Health Care Limited -Baddi (Cust Code -393) but it should be in Procter & Gamble Hygiene and Health Care Limited - Thailand cust code - CUST1905 | 8 | 2018-06-20 | 2018-06-20 | 2018-06-18 | Praveen Singh | 2 | 2 | Done
9 | 2018-06-22 | Client Feedback Points: 1)Invoice no. of building to be corrected:I am sending you invoice as an attachment. 2)Please find the attachment of Chennai Users.Please verify the user-signature Label/Name with the ERP Employes List. 3)Please share the data of customer master in excel format. | 9 | 2018-06-22 | 2018-06-22 | 2018-06-22 | Praveen Singh | 1 | 1 | Done
10 | 2018-06-26 | Software Updation on ITC Live/StagingServer | 10 | 2018-06-26 | 2018-06-26 | 2018-06-26 | Praveen Singh | 3 | 2 | Done | it will not be included in new task list as per discussion with Antaryami Sir
11 | 2018-06-26 | Client feedback Points: 1.Changes on Food Test Report regarding Part-B Report Section auto break. 2.Changes on Building Test Report regarding Part-B Report Section auto break. 3.Addressed the issues regarding editing of Order in Order booker Role Login. 4.Addressed the issues regarding Updation of Invoicing Type Consideration Parameters Coloum in Test Parameter Controller. 5.Updated the missing Micro-biologist Name in Order Master of all department except Pharma. | 11 | 2018-06-26 | 2018-06-26 | 2018-06-26 | Praveen Singh | 5 | 5 | Done | This problem is not resolved yet and Praveen had updates.
12 | 2018-06-27 | Client feedback Points: 1.Changes on Environment Test Report regarding Part-B Report Section auto break. 2.Changes on Helmet Test Report regarding Part-B Report Section auto break. 3.Changes on Textile Test Report regarding Part-B Report Section auto break. 4.Changes on Pharma Test Report regarding Part-B Report Section auto break. 5.Addressed the Email Sending issues in all Departments. 6.Addressed the scheduling issues regarding processing slow in assigning Job for Scheduler Role. 7.Amendment of Orders regarding biiling Type,Invoicing Type,discount Type and discount value. 8.Amendment of Invoices regarding sgst_rate,sgst_amount,cgst_rate,cgst_amount,igst_rate,igst_amount and total_amount. 9.Changes the Email Templates for Environment Department regarding Mobile Number Updation. | 12 | 2018-06-27 | 2018-06-27 | 2018-06-27 | Praveen Singh | 7 | 7 | Done | This problem is not resolved yet and Praveen had updates.
13 | 2018-06-30 | Client feedback Points: Change billing types of these customers into PO wise and invoicing type into Customer wise Product(of all samples in any stage). The name of customers are as follows:- (a) HETERO LABS LTD. - Cust Code 507 (b) Hetero Labs Ltd. Unit-I -Cust Code 539 (c) Hetero Labs Ltd. Unit-II -Cust Code 540 (d) HETERO FORMULATION DIVISION - Cust Code 843 (e) HETERO LABS LIMITED (R & D) -Cust Code 844 | 14 | 2018-06-30 | 2018-06-30 | 2018-06-30 | Praveen Singh | 1 | 1 | Done

## July-2018
ITC ERP TASK DETAIL(July-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-07-06 | Client Feedback Points: 1.Add conveyance of Rs. 500 in order booking no. E02-1806090022 Then in invoice: Invoice no. is E-1806280011. Total remains same Rs. 3950 Conveyance -Rs. 500 SGST :- 400 CGST:- 400 Grand Total : Rs. 5250 | 1 | 2018-07-06 | 2018-07-06 | 2018-07-06 | Praveen Singh | 1 | 1 | Done
2 | 2018-07-10 | Client Feedback Points: 1)Exchanging of Invoice Number and Invoice Date in listed two Invoices: a)E-1806250009-Chennai -Gabriel India Pvt Ltd. b)E-1806230008-Chennai-M/S. PIRAMAL ENTERPRISES LIMITED 2)Amendment of Amount in listed two Invoices: a)E-1806250009-Chennai-M/S. PIRAMAL ENTERPRISES LIMITED b)E-1806230008-Chennai -Gabriel India Pvt Ltd. 3)Changing of Invoice Date in listed Invoices: a)Invoicing date of E-1806230008 is E-1806210008(dated :- 21/06/2018) b)Invoicing date of E-1806250009 is E-1806230009(dated :- 23/06/2018) c)Add conveyance in invoice no. E-1806230009 in order no. E02-1806160064 d)THEN CORRECTED VALUE OF INVOICE IS :- TOTAL-8500,SGST:- 765.00,CGST-765.00 and GRAND TOTAL :- 10030 | 2 | 2018-07-10 | 2018-07-10 | 2018-07-10 | Praveen Singh | 2 | 2 | Done
3 | 2018-07-18 | (A) Customer Wise Product - In Case of Customer Wise Product sample name is directly related to test master name. (i) In sample name textbox - Only distinct samples of corresponding customers will be displayed in sample name textbox.-New Modification regarding displaying of Product Master along with Sample Name. (ii) No tree view option will be displayed if rates will be product wise-New Modification (iii) In invoicing - system is not picking rates for customer wise product.-System Error Error is :- If same alias name we had created for multiple test masters, for corresponding customer we used one alias and enter rates in invoicing structure,system allow user to do booking but not displayed any amount in invoicing until we will not enter rates in all test masters of that product alias. (B) Customer Wise Parameter :- In case of customer wise parameter (i) In sample name textbox :- only distinct sample names of corresponding customer will be displayed-New Modification regarding displaying of Product Master along with Sample Name. (ii) On selecting the parameter from tree view ,there should be one col. in last of grid which displayed the rates of that parameter so that it will be clear to user which parameter is pending for rates. Because in present scenario syestem is displaying the error "Invoicing type is not defiend " but it is not clear to user which parameter is pending for rates.-New Modification (iii) On typing the sample name for Customer Wise Parameter , system will automatically checks all the parameters previously booked for that sample had rates defined in Invoicing master or not . If any parameter don't have rate in master then system will display a message box for that parameter and will not allow user to proceed booking.-New Modification(Discussed with you). | 3 | 2018-07-18 | 2018-07-19 | 2018-07-19 | Praveen Singh | 16 | 16 | Done |  | In this task one system problem is not resolved yet.Praveen had updates
4 | 2018-07-26 | B)Client Feedback Points: (a) Order Editing:- System is showing invoicing error while editing a order in "Customer Wise Parameter" . COMMENT:Please find the attachment. (b) Customer Wise Product :- System is not picking rates at the time of invoicing as discussed earlier. COMMENT:Discussed / Will be addressed (c) Older Bookings :- In older bookings of food at the time of order editing system is not picking customer name. COMMENT: Addressed (d) Fix value in Description of master :- Please share master list of those masters in which we have default value in description filed COMMENT:Please find the attachment. | 4 | 2018-07-26 | 2018-07-26 | 2018-07-26 | Praveen Singh | 2 | 2 | Done |  | This was system error
5 | 2018-07-30 | A)USER ERROR: 1)Change into Customer Wise Product:- Pure & Cure P01-1806250128, P01-1806220116, P01-1806220115, P01-1806190164, P01-1806180264, P01-1806110173, P01-1806110171, P01-1806110169, P01-1806110167, P01-1806050188 2)Change Billing Type -Monthly P01-1805010055, P01-1805010067, P01-1804300103 3)Remove Duplicate Party Name Merge Names :- Cust Code :- 855 LENUS LIFE CARE PVT. LTD. Cust Code:- 177 Lenus Lifecare Pvt. Ltd. Keep Cust Code 177 and merge data of 855 into it. Change Billing Type -Monthly B)Please update this file today so that we can include these samples in monthly invoicing. C)Fix value in Description of master :- Please share master list of those masters in which we have default value in description filed. COMMENT:Please find the attachment. D)Please resolve this today in user query hour . This sample was booked compensatory by mistake now we have to generate invoice of this sample. Please open this ammendment option on Admininstrative end also. Order:F02-1807200087/Chennai/Regal Healthy Fine Foods,Hyderabad/20-07-2018/30-07-2018/Sweet Sample | 5 | 2018-07-30 | 2018-07-30 | 2018-07-30 | Praveen Singh | 2 | 2 | Done
6 | 2018-07-31 | B)Client feedback Points: Amendment of Orders regarding listed parts: i)biiling Type ii)Invoicing Type iii)discount Type iv)discount value. v)Customer Name | 6 | 2018-07-31 | 2018-07-31 | 2018-07-31 | Praveen Singh | 2 | 2 | Done
7 | 2018-07-31 | Software Update on Staging Server | 7 | 2018-07-31 | 2018-07-31 | 2018-07-31 | Praveen Singh | 2 | 2 | Done |  | it will not be included in new task list as per discussion with Antaryami Sir