## Dec-2018
ITC ERP TASK DETAIL(Dec-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-12-03 | 1)User-Role-Wise : Implementation of Multi Session Script-Stopping User to Open New Tab of Software: a)Creating a provision in the administrator end to assign the multi-session condition according to their roles assigned. b)Stopping User to open New Tab in any Browser(At a time one browser) according to user role assigned in step-1.-Working On c)Testing in multiple browser like Mozilla,Chrome etc. | 1 | 2018-12-03 | 2018-12-03 | 2018-12-03 | Praveen Singh(Approved) | 6 | 7 | Done
2 | 2018-12-07 | Client Feedback Points: 1)Removal of amendment rights of Test Report from "Approval to QA" end and keeping it to "Administrator" end only. 2)Shifting of these reports to reviewing stage: i)E02-1811300218, ii)E02-1811300219, iii)E02-1811300212, iv)F02-1812040057 3)Restricting User:All parameters are removed from the sample. | 2 | 2018-12-07 | 2018-12-07 | 2018-12-07 | Praveen Singh(Query) | 3 | 5 | Done
3 | 2018-12-11 | Regarding Credit Note / Debit Note / Account Sales Report Task: STEP-1 : CREDIT NOTE: 1)Changes on adding of credit note(Against invoice no./Against fresh ref. no.) : On inputting the Amount, system will automatically calculate the CGST-SGST/IGST/Net Amount Value according to the tax slab of Selected Customer. 2)Changes on viewing of particular Credit Note for remarks column in software Against invoice no. 3)Changes on PDF Generation of particular Credit Note for remarks column Against invoice no. 4)Viewing of particular Credit Note with remarks column in software Against fresh ref. no.(New Design Implementation) 5)PDF Generation of particular Credit Note with remarks column Against fresh ref. no. (New Design Implementation) STEP-2 : DEBIT NOTE: 1)Changes on adding of Debit Note(Against invoice no./Against fresh ref. no.) : On inputting the Amount, system will automatically calculate the CGST-SGST/IGST/Net Amount Value according to the tax slab of Selected Customer. 2)Changes on viewing of particular Debit Note for remarks column in software Against invoice no. 3)Changes on PDF Generation of particular Debit Note for remarks column Against invoice no. 4)Viewing of particular Debit Note with remarks column in software Against fresh ref. no. (New Design Implementation) 5)PDF Generation of particular Debit Note with remarks column Against fresh ref. no. (New Design Implementation) STEP-3 : MIS-REPORT: Account sales detail Report : 1)Including of Credit note date and remarks column in viewing of report in software. 2)Including of Credit note date and remarks column in excel download of report. 3)Including of Debit note date and remarks column in viewing of report in software. 4)Including of Debit note date and remarks column in excel download of report. | 3 | 2018-12-11 | 2018-12-13 | 2018-12-13 | Praveen Singh(Approved) | 16 | 20 | Done
4 | 2018-12-13 | Client Feedback Points: Shifting of below Orders to Section-Incharge to Reviewing: E02-1812030001,E02-1812030002,E02-1812030003,E02-1812030004,E02-1812040007,E02-1812040008,E02-181205002,E02-1812030005 | 4 | 2018-12-13 | 2018-12-13 | 2018-12-13 | Praveen Singh(Query) | 2 | 2 | Done
5 | 2018-12-21 | This is regarding the updation of NABL notification points in ERP uploaded on 19.12.2018, due to non-clarification of one point of NABL uploaded on 19.12.2018 it is requested to deactivate that function from live server on urgent basis from all departments. The detail of point is as below:- --Remove higlighting of non-NABL parameters using special symbol "*" and outsource parameters using "**" in all conditions. | 5 | 2018-12-21 | 2018-12-21 | 2018-12-21 | Praveen Singh(Approved) | 3 | 3 | Done
[7 empty] | TOTAL |  | 37