## July-2019
ITC ERP TASK DETAIL(July-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-07-01 | TAT Mail Scheduling | 1 | 2019-07-01 | 2019-07-01 | 2019-07-01 | Praveen Singh | 1.5 | 1.5 | Done
2 | 2019-07-01 | Regarding 9th digit of NABL ULR no. -- Very Very Urgent | 2 | 2019-07-01 | 2019-07-01 | 2019-07-01 | Praveen Singh | 0.5 | 0.5 | Done
3 | 2019-07-01 | Regarding multiple access to client in web portal | 3 | 2019-07-01 | 2019-07-05 | 2019-07-05 | Praveen Singh | 20 | 20 | Done
4 | 2019-07-05 | Regarding report no. in invoice | 4 | 2019-07-05 | 2019-07-05 | 2019-07-05 | Praveen Singh | 3 | 3 | Done
5 | 2019-07-06 | ITC Web Module : Client Feedback Points : Changes : I. Integration of listed columns on the Customer Section: Displaying of Brand Type Selectbox using Order booking Data of ERP Software using API. Brand Type Selection in Adding of Customer Brand Type Selection in Editing of Customer Displaying of Customer Order according to the selected Brand Type Upon Customer Login II. Integration of listed columns on the Customer Order Listing Page: Brand Type Stability Condition | 5 | 2019-07-06 | 2019-07-09 | 2019-07-09 | Praveen Singh (QH) | 4 | 5 | Done |  | Removed the required fields from adding and editing of Customers
6 | 2019-07-08 | MIS-Report : Sales Report Detail and Daily Sales Detail : | 6 | 2019-07-08 | 2019-07-09 | 2019-07-09 | Praveen Singh (3 Hrs A + 2 QH) | 5 | 5 | Done
7 | 2019-07-10 | Regarding new task of Department due date | 7 | 2019-07-10 | 2019-07-17 | 2019-07-17 | Praveen Singh | 30 | 30 | Done
8 | 2019-07-17 | Query hour - 17.07.2019 : i)Please update running series in LIMS.(Chennai Report No) ii)In form 39 in place Authorised Signatory please write Dharmendra Kumar [Person Incharge / DGM Pharma] as written previously. | 8 | 2019-07-17 | 2019-07-17 | 2019-07-17 | Praveen Singh | 1 | 1 | Done
9 | 2019-07-17 | List of small Tasks : (a) Expected Due Date Calculation :- At the time of order booking expected due date is calculated with reference of date and time but now we will consider time in the calculation.Example :- (a) If sample is booked on 16.07.2019 at 9:00 am and testing time required is 3 days then as per current logic expected due date will be 19.07.2019 but as per new logic expected due date will be 18.07.2019. (b) Column. of Remarks in Web portal :- Incorporate column. of remarks from Order Booking to Web portal Order Dashboard (c) Expected Due Date in order Confirmation Mail :- In order confirmation mail the Expected Due Date will +1 than of Expected Due Date in LIMS. | 9 | 2019-07-17 | 2019-07-20 | 2019-07-20 | Praveen Singh | 12 | 12 | Done
10 | 2019-07-18 | Involvement in ITC New Server for resolving speed issue with Networking Team and Tester | 10 | 2019-07-18 | 2019-07-23 | 2019-07-23 | Praveen Singh | 15 | 15 | Done
11 | 2019-07-23 | Client Feedback Points : TAT Mail Scheduling Worked On the following Changes: i)CronJob will not run on Sunday. ii)CronJob will not run on company holiday. iii)CronJob will not run on third Saturday. | 11 | 2019-07-23 | 2019-07-23 | 2019-07-23 | Praveen Singh(QH) | 5 | 5 | Done
12 | 2019-07-23 | Chaand Sir | 12 |  |  |  | Chaand Sir | 6 | 6 | Done
[7 empty] | Total | 103 | 104
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs