## May-2019
ITC ERP TASK DETAIL(May-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-05-01 | Regarding Accounts Related Task GST | 1 | 2019-05-01 | 2019-05-06 | 2019-05-06 | Praveen Singh | 35 | 36 | Done | Extra task added by Client after scope approval and time estimation
2 | 2019-05-08 | Regarding Urgent-Task-Regarding Incorporation of Form 50(Test Report Format) in Cosmetics department | 2 | 2019-05-08 | 2019-05-08 | 2019-05-09 | Praveen Singh | 5 | 5 | Done
3 | 2019-05-06 | Web-Module : ERP & Customer Module : TRF Creation : | 3 | 2019-05-06 | 2019-05-06 | 2019-05-28 | Praveen Singh | 90 | 90 | Done
4 | 05-27-2019 | Planning Module(Documentation + Development) | 4 | 2019-05-27 | 2019-05-28 | 2019-05-28 | Praveen Singh | 10 | 3 | Hold
5 | 2019-05-28 | Regarding new tasks | 5 | 2019-05-28 | 2019-05-31 | 2019-05-31 | Praveen Singh | 22 | 22 | Done
[7 empty] | Total | 162 | 156