## Nov-2019
ITC ERP TASK DETAIL(Nov-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-11-01 | Query hour- 19.10.2019 : Merging of Customer Name and Invoicing Customer Name. | 1 | 2019-11-01 | 2019-11-01 | 2019-11-01 | Praveen-Singh | 2 | 2 | Done
2 | 2019-11-08 | Software Updation | 2 | 2019-11-08 | 2019-11-08 | 2019-11-08 | Praveen Singh(QH) | 2 | 2 | Done
4 | 2019-10-18 | Regarding Chennai Report Format | 4 | 2019-11-09 | 2019-11-22 | 2019-11-22 | Praveen-Singh | 44 | 44 | Done
4 | 11-25-2019 | Software Updation | 4 | 11-25-2019 | 11-25-2019 | 11-25-2019 | Praveen Singh(QH) | 2 | 2 | Done
5 | 11-30-2019 | Chand Sir | 5 | 11-30-2019 |  |  | Chand Sir | 6 | 6 | Done
[7 empty] | Total | 56 | 56
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs