## Oct-2019
ITC ERP TASK DETAIL(Oct-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-10-01 | Regarding Very-Very Urgent task of Chennai Branch | 1 | 2019-10-01 | 2019-10-04 | 2019-10-04 | Praveen-Singh | 5 | 5 | Done
2 | 2019-09-26 | Regarding issue in calculation of department due date | 2 | 2019-10-05 | 2019-10-19 | 2019-10-19 | 2019-10-19 | 16 | 16 | Done
3 | 2019-09-27 | Sales Executive List to be uploaded in LIMS | 3 | 2019-10-11 | 2019-10-11 | 2019-10-11 | Praveen-Singh(QH) | 1 | 1 | Done
4 | 2019-10-01 | ITC New Server : Debugging & Optimization of the SQL Query | 4 | 2019-10-19 | 2019-10-19 | 2019-10-19 | Praveen Singh | 17 | 16.5 | Done
5 | 2019-10-01 | Optimization of Report Landing Page according to Role Users. | 5 | 2019-10-31 | 2019-10-31 | 2019-10-31 | Praveen Singh | 5 | 5 | Done
6 | 2019-10-01 | Performance Optimization | 6 |  |  |  | Chand Sir | 45 | 45 | Done
[7 empty] | Total | 89 | 88.5
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs