## JAN-2018
ITC ERP TASK DETAIL(JAN-2018)
S.No. | Date | Detail | Priority | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 15-12-2017 | Changes in Migaration:Addition of two new coloum Cost Price and Selling Price. | 5 | 2018-01-01 | 2018-01-04 | Ruby | 5 | 6.3 | Done | Done | Completed
2 | 15-12-2017 | In test master one more value of no limit will be added with numeric and alpha numeric | 23 | 2018-02-08 | 2018-02-08 | Ruby | 5 | 5 | Done
2 | 2018-01-01 | Software Updation | 24 | 2018-02-01 | 2018-02-01 | Praveen Singh | 1 | 1 | Done
3 | 2018-01-01 | MIS Report: Data validation of Booking Detail Report |  | 2018-01-01 | 2018-01-01 | Praveen Singh | 4 | 4 | Done
2 | 2018-04-01 | Software Updation | 24 | 2018-01-04 | 2018-01-04 | Praveen Singh | 2 | 2 | Done
3 | 2018-04-01 | 1)In every window, we should have option(buttons) to fetch the detail(sample pendency) expected due date wise till date 2)The listing will be parameter wise as well as sample wise. 3)In analyst window we should have print button so that analyst will take the print out of its pendency its own. 4)In scheduling sheet of analyst we should have coloum of priority. | 1 | 2018-01-11 | 2018-01-11 | Ruby | 16 | 16 | Done |  | Print button on analyst window is not updated. Rest points are completed.
6 | 2018-04-01 | In the window of reviewer, testing completed date & time should be displayed to track the reviewing pendency.Also pendency count according to roles in the header tab. | 2 | 2018-01-09 | 2018-01-09 | Praveen Singh | 8 | 8 | Done | Done | Completed
7 | 2018-04-01 | At the reviewing level reviewer needs a remark box to add the reason of delaying in reviewing. |  |  |  |  | 5
8 | 2018-04-01 | At the analyst level ,if a paramter reverts back to the analyst by the reviewer ,analyst needs the remark box to add reason of change. |  |  |  |  | 5
9 | 2018-04-01 | Multiple mail id's for a particular customer to be used as 'cc' in auto emailing of reports & invoices. | 4 | 2018-01-10 | 2018-01-10 | Praveen+Ruby(2.30 + 12) | 16 | 14.3 | Done | Under Testing
10 | 2018-04-01 | Clubbing of test report in one mail :- All the reports pending for email will be clubbed and send to the customer by the system itself in a single mail as an attachment at predefined time or on click of a particular button. |  |  |  |  | 16
11 | 2017-04-01 | All the MIS reports will be generated department wise(Food,Pharma,Environment) & Division wise(Panchkula,Chennai).And Option for All in Department and Location | 13 | 2018-01-24 | 2018-01-24 | Praveen Singh | 16 | 16 | Done
12 | 2017-04-01 | Export to Excel on listed master form to export master data at Administrator level: 1.Customer Master with all Columns, 2.Parameter Master along with Category and Equipment and 3.Product Test Master:One-by-one and All | 18 | 2018-01-30 |  | Ruby | 16
14 | 2017-04-01 | The status of draft report will be stored in system and will be displayed in TAT report. Draft report will not have any header,footer and signature.Only Label Draft Report will be specified on the top of report. | 3 | 2018-01-12 | 2018-01-12 | Praveen Singh | 6 | 6 | Done with one day delay due to Other Task Pendency | Completed
2 | 2018-06-01 | Software Updation | 24 | 2018-01-06 | 2018-01-06 | Praveen Singh | 1.5 | 1.5 | Done
2 | 2018-09-01 | Software Updation | 24 | 2018-01-09 | 2018-01-09 | Praveen Singh | 2 | 2 | Done
15 | 2018-12-01 | In Booking options for interlaboratory,Compensatory samples and Retestingand invoices for these samples will not be generated and don't considered in invoicing pendency. | 14 | 2018-01-20 | 2018-01-20 | Ruby | 10 | 10 | Done
16 | 2018-12-01 | Purchase order wise invoicing.Option to generate invoice for single PO and multiples PO in a single invoice.Changes on Order Form: Billing Type : Addition of New Billing Type : PO-Wise Addition of New fields : PO-Number(po_no),PO-Date(po_date) Changes on Generate Invoice Form: Po-wise->All PO-Wise Customer(All pending) -> Checkbox - all PO's(All PO pending for Invoices) On checking Po-Checkbox,all orders of selected PO's will be displagting for Invoice Generation.And orders of selected po's will be merged in one invoice. i.e. Invoice generation will be just like Daily Invoicing. Changes on Invoice PDF: Listing of all Samples according to PO just like Category-Subcategory. | 15 | 2018-01-25 | 2018-01-25 | Ruby | 20 | 20 | Done
17 | 2018-12-01 | In Booking, priority there should one option of On Hold having one text box to specify reson of hold.Hold samples will not be scheduled and information should be shared with client with reason of hold.User should have option to change the status from Hold to unhold and after that the expected due date of that sample will be calculated according to the unhold date. | 9 | 2018-01-15 | 2018-01-15 | Ruby | 12 | 12 | Done
2 | 2018-10-01 | Software Updation | 24 | 2018-01-10 | 2018-01-10 | Praveen Singh | 2 | 2 | Done
18 | 2018-12-01 | In scheduling the machine wise efficency and pendency will be displayed to the scheduler to decide the expected due date of sample. | 7 | 2018-01-11 | 2018-01-11 | Ruby | 6 | 6 | Done | Not Uploaded Yet
19 | 2018-12-01 | When the analyst enters the result in the system ,the reports will be reviewed by section incharge first,then the reports will be shifted to reviewer for reviewing. | 8 |  |  |  | Discussion required
20 | 2018-12-01 | Format of Job Order, Two job orders will be generated at the time of booking,one with client information and another without client information. with sample. Job order with client information will be retained by booking user and without client information will be sent to the lab | 6 | 2018-01-15 | 2018-01-15 | Praveen Singh | 20 | 20 | Done | Not Uploaded Yet
21 | 2018-12-01 | Export to PDF button on tester,invoicer & dispatcher window to export pendency to the PDF | 10 | 2018-01-16 | 2018-01-17 | Praveen Singh | 8 | 8 | Done
22 | 2018-12-01 | TAT Report show 'P' in place of ' ' | 12 | 2018-01-17 | 2018-01-17 | Praveen Singh | 4 | 4 | Done
2 | 15-01-2018 | Software Updation | 24 | 2018-01-15 | 2018-01-15 | Praveen Singh | 2 | 2 | Done
23 | 16-01-2018 | Validation of GST No. For individual user and govt. clients we don't have GST No. In that case nothing will be displayed in Invoice and should have option in customer master to add this. | 16 | 2018-01-17 | 2018-01-19 | Ruby | 6 | 6 | Done
24 | 16-01-2018 | Cancellation of previous invoices and provision to regenrate it in current date with current invoice no. | 17 |  |  | Praveen Singh | 16
26 | 16-01-02018 | MIS Report[Sales Report] :- Report to generate revenue category & subcategory wise.(Date wise& Month Wise & Year Wise). The fields in the report are as follows := Department Name,Branch,Date,Month,Year,Customer Name,Location Name,Sales Executive Name,Category Name,Sub Category Name,Product Name,Manufactured By,Supplied By,Revenue(Invoicing Amount excluding Tax).Search Criteria : From Date & To Date | 11 | 2018-01-20 | 2018-01-20 | Praveen Singh | 24 | 20 | Done
27 | 18-01-2018 | User Wise Performance Detail | [6 empty] | Moved to April Task
28 | 18-01-2018 | Eqipment Sorting and Instrument Wise Performance Detail | 19 | 2018-01-31 |  | Praveen Singh | 20 |  | Moved to April Task
29 | 25-01-2018 | Report Amendment at Reviewing Stage
30 | 25-01-2018 | Invoice Cancellationa and Regeneration
30 | 25-01-2018 | MDI Reports given by Mr.Mutul
31 | 31-01-2018 | Creation Of Pharma Master for Staging Server | 20 | 2018-01-01 | 2018-01-01 | Pratyush | 9 | 9 | Done
INDEX
Completed
Working
Discussion Required
Hold

## FEB-2018
ITC ERP TASK DETAIL(FEB-2018)
S.No. | Date | Detail | Priority | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 31-01-2018 | Uploading of Pharma Master on Staging Server(CSV to Sql Data Uploading): | 21 | 2018-02-02 | 2018-02-02 | Praveen Singh | 9 | 9 | Done
2 | 31-01-2018 | Testing of Helmet Department Go-Live Process Flow | 22 | 2018-02-01 | 2018-02-02 | Ruby | 9 | 9 | Done
3 | 31-01-2018 | Testing of Building Department Go-Live Process Flow | 23 | 2018-02-02 | 2018-02-02 | Ruby | 9 | 9 | Done
4 | 2018-01-02 | Testing of Textile Department Go-Live Process Flow | 27 | 2018-02-03 | 2018-02-03 | Ruby | 9 | 9 | Done
5 | 2018-01-02 | Testing of Environment Department Go-Live Process Flow | 28 | 2018-02-05 | 2018-02-05 | Ruby | 9 | 9 | Done
6 | 2018-01-02 | Creation Of Helmet Master from Staging Server | 25 | 2018-02-01 | 2018-02-01 | Pratyush | 8 | 8 | Done
7 | 2018-01-02 | Removing of Old Pharma Master | 26 | 2018-02-02 | 2018-02-02 | Praveen Singh | 7 | 7 | Done
8 | 2018-02-02 | Pharma Points of Testing
(a) | 1 | For pharma we do the sample receiving on reception only on current samples,no receiving will be done in case of back date samples. Booking User should have provision to do the booking without the sample receiving code. | 29 | 2018-02-09 | 2018-02-09 | Praveen Singh | 2 | 16 | Done
(b) |  | In Pharma,Manufacturing license no. is product specific for a particular customer. Booking user will define it at the time of booking according to product category. | 30 | 2018-02-03 | 2018-02-03 | Praveen Singh | 10 | 10 | Done
(c) | 2 | For Header note we have some standard notes which will be incorporated for the user ease and user should also have option to type any other header note.. | 31 | 2018-02-02 | 2018-02-02 | Praveen Singh | 3 | 3 | Done | In place of showing all header notes from Booking,Update only below standard list at the time of Booking
Each Film Coated Tablet Contains
Each Uncoated Tablet Contains
Composition
Each Hard Gelatin Capsule Contains
Each Enteric Coated Tablet Contains
Each ml Contains
Each Mouth Dissolving Tablet Contains
Each Vial Contains
Each Bolus Contains
(d) | 3 | In Job order, if a testing parameter don't have method then in place of displaying N/A,it will be blank. | 32 | 2018-02-02 | 2018-02-02 | Praveen Singh | 3 | 3 | Done
(e) | 4 | Like Description in food , In Pharma there are two parameters Reference to Protocol & Description have no instrument. | 33 | 2018-02-02 | 2018-02-02 | Praveen Singh | 1 | 1 | Done
9 | 2018-02-02 | Cloning of Order Booking | 34
10 | 2018-03-02 | Go-Live Process of Pharma Department(Overall Process Testing): a)In Analytical sheet, we should have two coloumns for claim and for pharma header note will be included in Assay Category b)In Scheduling Jobs ,text box to define reason of pendency is not disp laying. c)System is displaying server error at the time of reviewing of report.-Pharma d)Final print out of report is not correct. e)Label "Date of start of analysis" will be removed from Final report. | 35 | 2018-02-06 | 2018-02-06 | Ruby | 12 | 12 | Done | Claim limit value will also be displayed along with claim.
11 | 2018-03-02 | Back Date Booking Provision in Pharma Department | 39 | 2018-02-12 | 2018-02-12 | Praveen Singh | 16 | 16 | Done
12 | 31-01-2018 | Uploading of Helmet Master on Live Server(CSV to Sql Data Uploading): | 40 | 2018-02-08 | 2018-02-08 | Praveen Singh | 3 | 3 | Done
13 | 2018-03-02 | 1)If Invoicing-To will be in different name then tax slab will be according to invoicing to name in place of booking client name. 2)Displaying of Deparment Due date to Analyst in place of Expected Due Date | 38 | 2018-02-06 | 2018-02-06 | Praveen Singh | 8 | 8 | Done
14 | 2018-05-02 | Testing of Ayurvedic Department Go-Live Process Flow | 41 | 2018-02-13 | 2018-02-13 | Ruby | 9 | 9 | Done
15 | 2018-07-02 | Signatures of reviewer and finalier are not updated in the pharma software. | 44 | 2018-02-13 | 2018-02-13 | Praveen Singh | 5 | 5 | Done
16 | 2018-07-02 | In analystical sheet, only single printout will be taken for one instrument, if user want to take the printout of sheet again then, the approval from QA will be mandatory. The user is able to take the prinout of blank sheet from the scheduler no. of times according to the requirement and system will maintain the count of blank sheet taken by the analyst for a particular sample. I case of printing of analytical sheet for a particular instrument only those parameters will be displayed at the time of printing which was booked by the user.
17 | 2018-07-02 | There sholud be a provision to send the report with equipment & Without equipment at the the time of finalization by Finalizer and Dispatcher for printing | 45 | 2018-02-19 | 2018-02-19 | Pratyush | 13 | 13 | Done
18 | 2018-07-02 | Helmet:- In Scheduling, assign job prints order no's will be related to the department of scheduler. | 46 | 2018-02-13 | 2018-02-13 | Ruby | 3 | 3 | Done
19 | 2018-07-02 | Text body of order confirmation mail will be changed for helmet and other departments. | 47 | 2018-02-13 | 2018-02-13 | Praveen Singh | 8 | 8 | Done
20 | 2018-07-02 | Creation of Ayurvedic Department Master On ITC Ayurvedic Staging Server: | 48 | 2018-02-08 | 2018-02-08 | Pratyush | 18 | 18 | Done
21 | 2018-12-02 | Creation and Uploading of Pharma Master from Staging Server to Live Server(CSV To SQL) | 26 | 2018-02-17 | 2018-02-17 | Praveen Singh | 27 | 27 | Done
22 | 2018-12-02 | Software Updation | 24 | 2018-02-12 | 2018-02-12 | Praveen Singh | 2 | 2 | Done
23 | 2018-12-02 | Testing Ayurvedic Department ITC Dev Ayurvedic Staging Server | 24 | 2018-02-12 | 2018-02-12 | Pratyush | 8 | 8 | Done
24 | 13-02-2018 | Put Check Boxes in front of samples in invoicing for the user to select or deselect the no. of samples for invoicing. | 27 | 2018-02-13 | 2018-02-13 | Ruby | 5 | 5 | Done
25 | 13-02-2018 | Display the list of parameters and their amount in the pop up at the time of Generate Invoices on any location to make it easier for user to cross check the rates. | 28 | 2018-02-16 | 2018-02-16 | Ruby | 8 | 8 | Done
26 | 2018-05-02 | Testing of Ayurvedic Department Go-Live Process Flow | 41 | 2018-02-13 | 2018-02-13 | Pratu | 9 | 9 | Done
27 | 16-02-2018 | The Report format of ayurvedic will be same as pharma and header format is different.Scan copy is provided to Parveen. | 29 | 2018-02-19 | 2018-02-19 | Ruby | 12 | 8 | Done
28 | 16-02-2018 | The signature on the report will be of the last reviewer who confirms irrespective of save(action) count. | 49 | 2018-02-19 | 2018-02-19 | Pratyush | 5 | 5 | Done
29 | 16-02-2018 | Test Master and Assay Master Category Changes all over the Pharma Section.Real Time Stability Note will be displayed above test parameters and header note will be displayed between test master and assay master. | 52 | 2018-02-21 | 2018-02-21 | Ruby | 6 | 6 | Done
31 | 16-02-2018 | In Pharma back date booking,at the time of finalization there should be an option to select date of finalization .By default the date of reviewing will be displayed to the the finalizer and date of finalization will be displayed to the Approval to QA. | 56 | 2018-02-23 | 2018-02-23 | Ruby | 9 | 12 | Done
33 | 16-02-2018 | Partial Report Provision-
34 | 16-02-2018 | Pin Code in Customer Master & Country wise state and city. | 52 | 2018-02-22 | 2018-02-22 | Pratyush | 18 | 18 | Done
35 | 17-02-2018 | Invoicing will be done on the basis of parameter name and instrument irresctive of method | 51 | 2018-02-20 | 2018-02-20 | Praveen Singh | 12 | 12 | Done
36 | 19-02-2018 | Signatures of User(Alok & Dharmendra) on Finalizer and Approval Order Stage | 53 | 2018-02-21 | 2018-02-21 | Praveen Singh | 5 | 5 | Done
37 | 20-02-2018 | Booking - Invoicing Rate Issue. Reviewing - Report Date and Report Code Generation Issue. Finalizing - Signature Updation of Reviewer Issue. Approval - Signature Updation of Reviewer and Finalizer Issue. | 54 | 2018-02-22 | 2018-02-22 | Praveen Singh | 9 | 9 | Done
38 | 20-02-2018 | Displaying of Department Due Date in Scheduling and Changing of Expected Due date will change the Report DUe date and Department DUe Date | 55 | 2018-02-23 | 2018-02-23 | Praveen SIngh | 5 | 5 | Done
39 | 20-02-2018 | Creation of New Role for Master Creation for the Users | 56 | 2018-02-23 | 2018-02-23 | Pratyush | 6 | 6 | Done
40 | 2018-12-02 | Software Updation | 24 | 2018-02-20 | 2018-02-20 | Praveen Singh | 2 | 2 | Done
41 | 22-02-2018 | Uploading of Ayurvedic Master on Live Server | 57 | 2018-02-23 | 2018-02-23 | Pratyush | 8 | 8 | Done
42 | 23-02-2018 | Reporting Listing Changes: 1)Displaying of dispatched button of dispatched Orders. Invoicing Listing Changes: 2)Displaying of pagination on all invoicing listing. 3)Displaying of Pagination in viewing of all generated orders. | 58 | 2018-02-24 | 2018-02-24 | Praveen Singh | 7 | 7 | Done
43 | 22-02-2018 | Uploading of Textile Master on Staging Server | 59 | 2018-02-24 | 2018-02-24 | Pratyush | 8 | 8 | Done
44 | 26-02-2018 | Search Buttons on all Invoicing Structure | 60 | 2018-02-27 | 2018-02-27 | Pratyush | 9 | 9 | Done
45 | 26-02-2018 | Department Filter on Order Number Selectbox in Job Sheet Print in Scheduling | 62 | 2018-02-28 | 2018-02-28 | Pratyush | 7 | 7 | Done
46 | 26-02-2018 | Invoice generation will be department wise | 61 | 2018-02-26 | 2018-02-26 | Praveen Singh | 7 | 7 | Done
47 | 26-02-2018 | Invoicing Structure for adding rates will be department wise | 63 | 2018-02-28 | 2018-03-01 | Ruby | 18 | 18 | Done
48 | 26-02-2018 | In the report format of food, Part -A Sample information the fields with N/A will not be displayed in report. | 65 | 2018-02-28 | 2018-02-28 | Pratyush | 9 | 9 | Done
49 | 27-02-2018 | Name and Signature Implementation on Helment Order Process Stages.Removing of Equipment Column. | 64 | 2018-02-27 | 2018-02-27 | Praveen Singh | 7 | 7 | Done
INDEX
Completed
Working
Discussion Required
Hold

## March-2018
ITC ERP TASK DETAIL(March-2018)
S.No. | Date | Detail | Priority | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-01-03 | Ayurvedic Order Process Changes on listed Stages On Web and PDF View: 1.Reviewer:User Name and Signature Updation and Removal of NABL located just below the Logo. 2.Finalizer:User Name and Signature Updation and Removal of NABL located just below the Logo. 3.Approval:User Name and Signature Updation and Removal of NABL located just below the Logo. | 1 | 2018-03-05 | 2018-03-05 | Pratyush | 9 | 9 | Done
2 | 2018-01-03 | Building Order Process Changes on listed Stages On Web and PDF View: 1.Reviewer:User Name and Signature Updation and Removal of NABL located just below the Logo. 2.Finalizer:User Name and Signature Updation and Removal of NABL located just below the Logo. 3.Approval:User Name and Signature Updation and Removal of NABL located just below the Logo. | 2 | 2018-03-05 | 2018-03-05 | Pratyush | 8 | 8 | Done
3 | 2018-01-03 | User Assigned Department Wise in Scheduling | 3 | 2018-03-01 | 2018-03-01 | Praveen Singh | 9 | 9 | Done
4 | 2018-01-03 | Switching of User Role | 4 | 2018-03-05 | 2018-03-05 | Praveen Singh | 8 | 8 | Done
5 | 2018-01-03 | Creation and Uploading of Pharma Master on Live Server: | 5 | 2018-03-08 | 2018-03-08 | Praveen Singh | 28 | 27 | Done
6 | 2018-05-03 | In all departments, reviewing date will be the current date and report finalization date and report approval to QA date will also be the current date irrespective of report review date. | 6 | 2018-03-07 | 2018-03-07 | Ruby | 12 | 10 | Done
7 | 2018-05-03 | Testing of Switching of User Role(Task shifted due to Pharma-Master-Uploading) | 7 | 2018-03-06 | 2018-03-06 | Pratyush | 9 | 9 | Done
8 | 2018-05-03 | Report Ammendment- Option to type report ammenment no on the reviewer window and suffix 'A' should be added on the end of report and Date of reviewing and Date of Completion will be the current date. (a) In the reviewing level, Reviewer have option to add "A" at the end of report no. (b) In the case of ammended report, Date of completion will be the date of reviewing. | 8 | 2018-03-08 | 2018-03-12 | Ruby | 18 | 18 | Done
9 | 2018-05-03 | We should Save copy of previous report and ammended report in the system.
10 | 2018-07-03 | Dispatcher Permission to Print an report. | 9 | 2018-03-07 | 2018-03-07 | Pratyush | 8 | 8 | Done
11 | 2018-07-03 | Software Updation | 24 | 2018-03-07 | 2018-03-07 | Praveen Singh | 2 | 2 | Done
12 | 2018-08-03 | Party Ref Date/Letter Date on Ayurvedic Reports | 10 | 2018-03-08 | 2018-03-08 | Pratyush | 8 | 8 | Done
13 | 2018-09-03 | User Manual Creation-Order and Master Creation | 11 | 2018-03-12 | 2018-03-12 | Pratyush | 18 | 18 | Done
14 | 2018-09-03 | Users Feedback Points regarding: 1.Invoicing-Food: i.Re-creation of Invoice ii.Amendment of Invoice 2.Report Format-Ayurvedic 3.Test Parameter Updation-Pharma: i.Method should be Null ii.Claim Dependent should be Zero | 12 | 2018-03-09 | 2018-03-09 | Praveen-Singh | 8 | 8 | Done
15 | 2018-12-03 | Calculation of Calim Value for Alpha-numeric Value. | 13 | 2018-03-12 | 2018-03-12 | Praveen Singh | 8 | 7 | Done
16 | 2018-12-03 | Displaying of dispatched detail in Invocier and Dispatcher | 14 | 2018-03-13 | 2018-03-13 | Pratyush | 8 | 8 | Done
17 | 2018-12-03 | Displaying of Product Master Name in a Product Master Alias in State-Wise-Product and Customer-Wise-Product Invocing | 15 | 2018-03-13 | 2018-03-14 | Ruby | 8 | 10 | Done
18 | 2018-12-03 | ENV Report PDF Change:Requirement Label Changes in case of IS:10500 Test Standard in Environment Test Report.If Test Standard is IS:10500,then add 'Acceptable Limit-Permissible Limit in absence of alternative Source' with Label Requirement. | 16 | 2018-03-13 | 2018-03-13 | Praveen Singh | 8 | 8 | Done
19 | 14-03-2018 | Displaying of Party Ref. No on Order Process Stage of Ayurvedic Department | 17 | 2018-03-14 | 2018-03-14 | Ruby | 8 | 8 | Done
20 | 14-03-2018 | Customer-wise-Parameter Rates Updation | 18 | 2018-03-14 | 2018-03-14 | Pratyush | 8 | 8 | Done
21 | 14-03-2018 | Uploading of Invoicing Rate of State-wise Invoicing Structure in Pharma Deparment | 19 | 2018-03-14 | 2018-03-14 | Praveen Singh | 8 | 8 | Done
22 | 15-03-2018 | Microbiological Signature on Ayurvedic Report | 20 | 2018-03-15 | 2018-03-15 | Pratyush | 8 | 8 | Done
23 | 15-03-2018 | New Report Format Implementation on Environment Report Template regarding General Parameter seperation | 21 | 2018-03-19 | 2018-03-19 | Ruby | 16 | 16 | Done
24 | 15-03-2018 | Dispalying of Customer-name with Cityname in Submitted By Field in Pharma Test Report | 23 | 2018-03-15 | 2018-03-15 | Praveen Singh | 3 | 3 | Done
25 | 15-03-2018 | Uploading of Invoicing Rate-Customer-Wise-Product Invoicing Structure in Pharma Deparment and Addressing of User Feedbacks. | 22 | 2018-03-16 | 2018-03-16 | Praveen Singh | 13 | 13 | Done
26 | 15-03-2018 | In Pharma backdate Booking, Review date will be the default date for further Order Process Stage .i.e in datepicker of Finalizer and Approval. Remove all dates from Finalizer and Approval Signature | 24 | 2018-03-16 | 2018-03-16 | Pratyush | 8 | 8 | Done
27 | 15-03-2018 | Rounding of Standard value from and Standard value to according to Standard Value Type ie Numeric,Alphanumeric,NA in all Departments | 26 | 2018-03-17 | 2018-03-17 | Pratyush | 8 | 8 | Done
28 | 15-03-2018 | Uploading of Invoicing Rate-Customer-Wise-Parameter Invoicing Structure in Pharma Deparment and Addressing of User Feedbacks. | 27 | 2018-03-17 | 2018-03-17 | Praveen Singh | 9 | 9 | Done
29 | 16-03-2018 | Creation of Food Staging Server for Chennai Team | [6 empty] | Moved to April 2018
30 | 19-03-2018 | MIS Report: Daily Invoicing Report as Excel Format | 28 | 2018-03-20 | 2018-03-20 | Pratyush | 16 | 16 | Done
31 | 19-03-2018 | Cloning of Order Booking as New Order using Save as Option | 29 | 2018-03-20 | 2018-03-20 | Praveen Singh | 12 | 12 | Done
32 | 20-03-2018 | Integration of Invoice Number in Credit and Debit Note of Payment Module. | 30 | 2018-03-21 | 2018-03-21 | Ruby | 8 | 8 | Done
33 | 20-03-2018 | Displaying of Batch No with search in Order Listing and option to refresh the Invoicing Structure at the time of Booking | 31 | 2018-03-21 | 2018-03-21 | Praveen Singh | 5 | 5 | Done
34 | 21-03-2018 | Creation of Detector Master according to Equipment. | 32 | 2018-03-21 | 2018-03-21 | Ruby | 5 | 5 | Done
35 | 21-03-2018 | Test Master Creation(Step-2)-Option to Select Detector in selectbox | 33 | 2018-03-23 | 2018-03-23 | Ruby | 8 | 8 | Done
36 | 21-03-2018 | New Invoicing Structure : Customer Wise Assay Parameter-Option for adding of rates using new Customer Wise Assay Parameter form | 34 | 2018-03-24 | 2018-03-24 | Praveen Singh | 24 | 20 | Done
37 | 21-03-2018 | Creation of Test Master for Partial Report and Part-Wise Report | 37 | 2018-03-23 | 2018-03-23 | Pratyush | 16 | 15 | Done
38 | 2018-04-01 | Software Updation | 38 | 2018-03-22 | 2018-03-22 | Praveen Singh | 2 | 2 | Done
39 | 21-03-2018 | Customer Wise Assay Parameter integration with Order Booking Form-Option to enter running time as combo box and no of Injection as Input.Also allow user to book an order only if rate is available. | 35 |  |  |  | 16 |  | Moved to April Task List
40 | 21-03-2018 | Customer Wise Assay Parameter integration with generation of Invoice | 36 | [5 empty] | Moved to April Task List
41 | 22-03-2018 | Users Feedback Points(Approval and Invoicing): 1.Invoicing- Amendment of Invoice. 2.Approval - Report Format Change in Environment / Water Department(General Information and Observation) | 39 | 2018-03-22 | 2018-03-22 | Praveen Singh | 2 | 2 | Done
42 | 23-03-2018 | Allowing Order Booking with checking the Invoicing in case of Pharma Department in Customer-wise-Parameter Invoicing and Addressing of User Feedback Points | 40 | 2018-03-23 | 2018-03-23 | Praveen Singh | 3 | 3 | Done
43 | 23-03-2018 | Report Changes in Ayurvedic Department listed in a Hard Copy | 41 | 2018-03-23 | 2018-03-28 | Pratyush | 9 | 11 | Done
44 | 23-03-2018 | Department wise Mail Body Intergration changes | 42 | 2018-03-26 | 2018-03-26 | Pratyush | 8 | 8 | Done
45 | 24-03-2018 | Invoicer should able to take a print out of report | 43 | 2018-03-27 | 2018-03-30 | Pratyush | 8 | 8 | Done
46 | 24-03-2018 | All department Except Food : There sholud be a provision to send the report with equipment & Without equipment at the the time of finalization by Finalizer and Dispatcher for printing | 44 | 2018-03-27 | 2018-03-28 | Ruby | 16 | 16 | Done
47 | 28-03-2018 | Meeting and discussion with Client. | 46 | 28-03-2018 | 28-03-2018 | Praveen Singh | 4 | 4 | Done
48 | 28-03-2018 | Pharma User Feedback Points: 1.Fixed Rates displaying Issue. 2.Displaying of sample according to the saved Invoicing Rate in case of Pharma department in Customer Wise Product Invoicing. 3.Limit having ? Mark. 4.Invoicing Error on editing of Orders 5.Header and footer Notes dissappears on displaying Invoicing Erroe at the time of Booking. 6.After Dispatched, the order again standing for Invoicing with amendment. | 45 | 2018-03-29 |  | Praveen Singh | 16 | 14 | Done
49 | 29-03-2018 | Report PDF Format : Error to be Checked - In Order Booking Form if supplied by & manufactured by is blank then on final report Part A system automatically keep submitteb by col. blank. | 47 | 2018-03-29 | 2018-03-30 | Ruby | 3 | 3 | Done
50 | 29-03-2018 | Duplicacy Check- Order Booking Form :- if a sample of particular batch for a corresponding client already exists then then system will display a warning message to the user having the previous order booking date and order no and asked for permission of user to proceed for booking ,. If user press "Yes" then booking will be continued and if user select "No" then booking will not be proceed.
51 | 30-03-2018 | Error to be checked :- The sorting of parameter(top & down) is not functioning properly. | 49 | 2018-03-30 | 2018-03-30 | Ruby | 4 | 4 | Done
52 | 30-03-2018 | In Scheduling,Job sheet print if user want to leave one col. of of standard value from & to blank then system is not allowing to do that.And Provision to Update Standard Value Type also | 50 | 2018-03-31 | 2018-03-31 | Ruby | 8 | 8 | Done
53 | 30-03-2018 | Testing of Order Booking in case of Customer Wise Product/Fixed Rate Invoicing Structure. | 51 | 2018-03-30 | 2018-03-30 | Pratyush | 8 | 8 | Done
54 | 30-03-2018 | Pharma User Feedback Points: 1.Booking Date and Booking Code Changes. 2.Reporting Date and Reporting Code Changes. 3.Invoicing Type and invoicing rate modification. | 52 | 2018-03-30 | 2018-03-30 | Praveen Singh | 5 | 5 | Done
55 | 28-03-2018 | Meeting and discussion with Client regarding Scope-2 Document | 53 | 2018-03-30 | 2018-03-30 | Praveen Singh | 2 | 2 | Done
56 | 31-03-2018 | Software Updation | 54 | 2018-03-31 |  | Praveen Singh | 2 | 2 | Done
57 | 31-03-2018 | Ayurvedic Report Format Implementation(New Changes) 1.Sample Information Detail 2.View Level changes on all Stages. 3.PDF Report Format Changes. 4.Removal of Date of Completion 5.Page Setup. | 55 | 2018-03-31 | 2018-03-31 | Pratyush | 8 | 8 | Done
58 | 31-03-2018 | Clearance of Invoicing Issues of all Department | 54 | 2018-03-31 |  | Praveen Singh | 6 | 6 | Done
INDEX
Completed
Working
Discussion Required
Hold
Moved

## April-2018
ITC ERP TASK DETAIL(April-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-02-04 | Creation of New Migration : Table1:test_parameter_invoicing_parents:tpip_id,test_parameter_id,test_parameter_status. Changes in Test_parameter_migration: Table2:Addition of New Column ' test_parameter_invoicing_parent_id'' in test_parameters table Changes on Test Parameter Master: a.Displaying of Test_Parameter_Invoicing_Parent Selectbox in adding form. b.Displaying of Test_Parameter_Invoicing_Parent Selectbox in editing form. c.Adding of Test_Parameter_Invoicing_Parent_id fields. d.Editing of Test_Parameter_Invoicing_Parent_id fields. Changes on Invoicing Structure : Customer Wise Assay Parameter-Option for adding of rates using new Customer Wise Assay Parameter form: a.Displaying of Test Parameter Category b.Displaying of Test Parameter Name according to above Migration. | 14 |  | 2018-04-07 |  | Praveen-Singh | 16 | 14 | Done
2 | 2018-02-04 | Customer Wise Assay Parameter integration with Order Booking Form-Option to enter running time as combo box and no of Injection as Input.Also allow user to book an order only if rate is available. | 17 | 2018-04-09 | 2018-04-18 | 2018-04-18 | Praveen-Singh | 63 | 47 | Done(Uploaded on Dev Server)
2 | 2018-02-04 | Customer Wise Assay Parameter integration with generation of Invoice | 26 | 2018-04-18 | 2018-04-19 | 2018-04-19 | Praveen-Singh | 8 |  | Done(Uploaded on Dev Server)
3 | 2018-02-04 | Creation of Food Staging Server for Chennai Team | 1 |  | 2018-04-02 | 2018-04-02 | Praveen Singh | 2 | 2 | Done
4 | 2018-02-04 | Duplicacy Check- Order Booking Form :- if a sample of particular batch for a corresponding client already exists then then system will display a warning message to the user having the previous order booking date and order no and asked for permission of user to proceed for booking ,. If user press "Yes" then booking will be continued and if user select "No" then booking will not be proceed. | 2 |  | 2018-04-02 | 2018-04-02 | Ruby | 8 | 8 | Done
5 | 2018-02-04 | Changing of layout of Viewing of Ayurvedic Order Process Stage and editing with same Format at Reviewer-end | 3 |  | 2018-04-02 | 2018-04-02 | Pratyush | 8 | 8 | Done
6 | 2018-02-04 | User Wise Performance Detail and Analyst Summary Report | 29 | 2018-04-26 | 2018-04-28 | 2018-04-28 | Praveen Singh | 32 | 32 | Done
7 | 2018-02-04 | Equipment Sorting and Instrument Wise Performance Detail : Date Branch Department Instrument Name Allocated Count Pending/Opening Balance Count Completed count Over Due Count Not Due Count Total count in footer | 28 | 2018-04-23 | 2018-04-28 | 2018-04-28 | Praveen Singh | 24 | 24 | Done
8 | 2018-02-04 | Administrator End:- Administrator should have provision to close the receiving of sample if its left unlcosed by the user by mistake. | 4 |  | 2018-04-02 | 2018-04-02 | Praveen Singh | 4 | 4 | Done
9 | 2018-02-04 | To be provided:- Remark form to the administrator to add ,remove or edit a new remark department wise. | 10 |  | 2018-04-06 | 2018-04-07 | Pratyush | 16 | 16 | Done
10 | 2018-02-04 | Create master form for the label of these charges,user will select the charges type and add the amount | 16 |  | 2018-04-07 | 2018-04-09 | Pratyush | 16 | 16 | Done
10 | 2018-02-04 | Booking Form :Rename extra amount as Conveyance and add one more column to add PPCB Charges | 17
11 | 2018-02-04 | Customer Master:- We should incorporate department & branch in customer master to define (billing type,invoicing type,discount type) | 7 |  | 2018-04-06 | 2018-04-07 | Ruby | 20 | 18 | Done
12 | 2018-02-04 | Sample Receiving Code:- Incorporate Location code in sample receiving code same as booking code(i.e 01 for panchkula & 02 for chennai). | 8 |  | 2018-04-04 | 2018-04-04 | Praveen Singh | 2 | 2 | Done
13 | 2018-02-04 | Report Format Implementation(New Changes): 1.Remove report no from the reports, system will generate the report no in back end but it will not be reflected on the reports. 2.Booking code is displayed on the invoices. 3.Inrease the font size of reports of all departments. | 5 |  | 2018-04-04 | 2018-04-04 | Pratyush | 16 | 16 | Done
14 | 28-03-2018 | Meeting and discussion with Empower Software Team | 6 |  | 2018-03-30 | 2018-03-30 | Praveen Singh | 2 | 2 | Done
15 | 2017-02-04 | Signature of invoicer will be displayed on invoices. | 9 |  | 2018-04-04 | 2018-04-04 | Praveen Singh | 2 | 2 | Done
16 | 2018-02-04 | Pharma:- Limit of Disintegration time will be displayed automatically on the selection of header note. | 24 | 2018-04-17 | 2018-04-17 | 2018-04-17 | Pratyush | 8 | 8 | Done
17 | 2018-02-04 | Round Off of results:- If claim value will be of decimal point then limit will not be roundoff and decimal place value of limit will be one as of claim value. | 20 |  | 2018-04-10 | 2018-04-12 | Pratyush | 16 | 24 | Done
18 | 2018-02-04 | In invoicing only customer name of cooresponding departments will be displayed to the invoicer. | 10 |  | 2018-04-04 | 2018-04-04 | Praveen Singh | 4 | 4 | Done
19 | 2018-04-04 | MIS Report :- Add column of current date in MIS report of Pharma. | 13 |  | 2018-04-05 | 2018-04-05 | Praveen Singh | 4 | 4 | Done
20 | 2018-04-04 | The changes done in Customer wise Product is also applicable on State Wise Product. | 11 |  | 2018-04-05 | 2018-04-05 | Praveen Singh | 4 | 4 | Done
21 | 2018-04-04 | Pharma User Feedback Points: | 12 |  | 2018-04-04 | 2018-04-04 | Praveen Singh | 1 | 1 | Done
21 | 2018-04-04 | Pharma User Feedback Points: | 12 |  | 2018-04-06 | 2018-04-06 | Praveen Singh | 2 | 2 | Done
22 | 2018-05-04 | Pharma-: In automailing of Govt. reports we need stamp of Standard Quality & Not of Standard Quality and Roud stamp of ITC with signature of Finalizer. The Stamp type will be depend on the remark selected by the reviewer. Standard Quality :- (a) The sample referred above is of standard quality with respect to above tests only. (b)In the opinion of the undersigned,the sample referred above is of standard quality as defined in the Drugs and Cosmetics Act 1940 and the rules made there under for the reasons given below. Not of Standard quality :- (a) The sample referred above is not of standard quality with respect to above test only. (b)In the opinion of the undersigned,the sample referred above is not of standard quality as defined in the Drugs and Cosmetics Act 1940 and the rules made there under for the reasons given below. | 15 |  | 2018-04-07 | 2018-04-09 | Ruby | 8 | 8 | Done
23 | 2018-10-04 | Order module testing regarding Customer Defined Structure | 18 |  | 2018-04-10 | 2018-04-10 | Ruby | 4 | 3 | Done
24 | 2018-05-04 | Invoicing Master:- Incorporate branch in all invoicing types to add rates. | 19 |  | 2018-04-12 | 2018-04-16 | Ruby | 16 | 16 | Done
25 | 2018-05-04 | Auto printing of reports: Need a provision to print all the reports of a particular invoice automatically by the system in the no. of sets given by the user.
25 | 2018-05-04 | Connect weekly off with the calculation of expected due date.TAT :- In TAT Report Expected due report will be calculated according to the current date irrespective of current date. |  | 2018-04-16 | 2018-04-16 | 2018-04-17 | Ruby | 8 | 9 | Done
26 | 2018-09-04 | MIS Report:- Daily Sales Report & DOD ,DOR of Environment & Pending Invoicing Detail
27 | 2018-10-04 | Pharma User Feedback Points: | 12 |  | 2018-04-12 | 2018-04-12 | Praveen Singh | 1 | 1 | Done
28 | 2018-10-13 | 1.After booking the order if user want to add extra parameter than on claim value section previous added standard value from and to will not showing the calculated value , user need to again click on the tab for calculation claim . 2.In Invoices list section Batch no,discounttype,discount value option needed in the list. | 20 |  | 2018-04-13 | 2018-04-13 | Pratyush | 8 | 8 | Done
29 | 13-04-2018 | Pharma User Feedback Points and Software Live for Stamp with Signature and Standard/Non-standard Quality Stamp | 21 |  | 2018-04-13 | 2018-04-13 | Praveen Singh | 3 | 3 | Done
30 | 14-04-2018 | Pharma User Feedback Points(Invoicing) | 22 |  | 2018-04-14 | 2018-04-14 | Praveen Singh | 2 | 2 | Done
30 | 16-04-2018 | Pharma User Feedback Points(Invoicing) | 22 |  | 2018-04-16 | 2018-04-16 | Praveen Singh | 1 | 1 | Done
31 | 16-04-2018 | Displaying of Claim and Claim Calumated value in Standard Value from and Standard Value To upto clicking on Addmore link and Updating from Parameter Popup in case of adding of Order and Editing of Order in Order Form | 23
30 | 17-04-2018 | Pharma User Feedback Points(Invoicing) | 25 |  | 2018-04-17 | 2018-04-17 | Praveen Singh | 2 | 2 | Done
31 | 18-04-2018 | To Be Rectified:- Value of claim is not parameter category specifiec it will be related to the claim dependency of the parameters on the master
32 | 18-04-2018 | Pharma User Feedback Points(Invoicing) | 26 |  | 2018-04-18 | 2018-04-18 | Praveen Singh | 2 | 2 | Done
33 | 19-04-2018 | Pharma User Feedback Points | 27 |  | 2018-04-19 | 2018-04-19 | Praveen Singh | 2 | 2 | Done
34 | 20-04-2018 | Pharma User Feedback Points | 29 |  | 2018-04-20 | 2018-04-20 | Praveen Singh | 1 | 1 | Done
35 | 21-04-2018 | Pharma User Feedback Points | 30 |  | 2018-04-21 | 2018-04-21 | Praveen Singh | 2 | 2 | Done
35 | 21-04-2018 | Pharma User Feedback Points and Meeting with Client regarding MIS-Report Discussion | 31 |  | 2018-04-21 | 2018-04-21 | Praveen Singh | 1 | 1 | Done
36 | 23-04-2018 | Option for Editing of Sample Date in case of Pharma Department | 32 |  | 2018-04-23 | 2018-04-23 | Praveen Singh | 2 | 2 | Done
37 | 24-04-2018 | Pharma User Feedback Points | 33 |  | 2018-04-24 | 2018-04-24 | Praveen Singh | 2 | 2 | Done
38 | 25-04-2018 | Dynamic Header to be Incorporated.
39 | 25-04-2018 | Labels to be Changed :- Submitted into referred
40 | 25-04-2018 | in remarks :- two times with with - "with"
41 | 25-04-2018 | General Information & Observation Report Format : Add Test Report as per IS
42 | 25-04-2018 | To be checked : Sequence of parameters in Environment Masters are changing automatically.
43 | 25-04-2018 | TAT Report: Filter by Expected Due Date and Order Process Stage | 34 |  | 2018-04-25 | 2018-04-25 | Praveen Singh | 2 | 2 | Done
44 | 25-04-2018 | Pharma User Feedback Points | 35 |  | 2018-04-25 | 2018-04-25 | Praveen Singh | 1 | 1 | Done
45 | 25-04-2018 | MIS Reports : Sample Log Status Changes discuss with Client(AS) | 36 |  | 2018-04-25 | 2018-04-25 | Praveen Singh | 5 | 5 | Done
46 | 26-04-2018 | Pharma User Feedback Points | 37 |  | 2018-04-26 | 2018-04-26 | Praveen Singh | 2 | 2 | Done
47 | 30-04-2018 | Pharma User Feedback Points | 38 |  | 2018-04-30 | 2018-04-30 | Praveen Singh | 8 | 8 | Done

## May-2018
ITC ERP TASK DETAIL(May-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-01-05 | Software Update Feedback Points and Integration of DT Limit in Order Module: | 1 | 2018-05-02 | 2018-05-02 | 2018-05-02 | Praveen Singh | 9 | 7 | Done
2 | 2018-04-05 | Software Update | 2 | 2018-05-04 | 2018-05-04 | 2018-05-04 | Praveen Singh | 1 | 1 | Done
3 | 2018-04-05 | User Feedback Points(Discussed Points of Meeting) | 3 | 2018-05-04 | 2018-05-04 | 2018-05-04 | Praveen Singh | 9 | 9 | Done
4 | 2018-05-05 | User Feedback Points: 1.Building Report Design Auto Break Implementation. 2.Environment Report Design Auto Break Implementation. 3.Uploading of Signatue of missing Users. 4.Removal of Duplicate Customer in Invoicing 5.Changing of Billing Type in booked orders. 5.Discount Updation in booked Orders. 7.Implementation of Brand in MIS TAT Report. | 4 | 2018-05-04 | 2018-05-04 | 2018-05-04 | Praveen Singh | 9 | 9 | Done
5 | 2018-05-07 | 1.Addressed the Pharma Invoicing Points of following cases: CASE 1: If Parameter has defined for Invoicing Type.If Yes,then check is Parameter consider for Parent Invoicing Type,If Yes,then calculate the count of the Children and apply the Invoicing rate based on Invoicing Type,Customer Name,Product Category,Sub Product Category,Parameter Category,Test Parameter Name,Equipment and Equipment Count. CASE 2: If Parameter has defined for Invoicing Type.If Yes,then check is Parameter consider for Parent Invoicing Type,If No,apply the Invoicing rate based on Invoicing Type,Customer Name,Product Category,Test Parameter Name,Equipment. 2.Page Auto Break Implementation in PDF Design of Invoice for all Department. 3.Changes the Viewing of Rates in Popup involved in any booking at the time of Invoice Generation in following Invoicing Type: a.Customer Wise Product / Fixed Rate b.Customer Wise Parameter 4.Amendment in booked order regarding Discount and Discount Value Change. | 5 | 2018-05-07 | 2018-05-07 | 2018-05-07 | Praveen Singh | 9 | 9 | Done
6 | 2018-05-08 | User Feedback Points: 1.Implementation and Uploading of Signature for users. 2.Searching of Order in multisearch window of Invoice Landing page. 3.Corrected the order whose invoice has been already generated. 4.Corrected the order which is dispatched already but still show in dispatching. 5.Amendment of Invoices. 6.Changing of Booked order billing type from daily to monthly as it is booked in daily Billing Type. 7.Report Format modification in design. | 6 | 2018-05-08 | 2018-05-08 | 2018-05-08 | Praveen Singh | 9 | 9 | Done
6 | 2018-05-09 | Client Feedback Points(Changes Discussed): 1.Food Report Design Auto Break Implementation. 2.Ayurvedic Report Design Auto Break Implementation. 3.Displaying of Customer name having pending orders for invoicing at the time of Invoice Generation. 4.Incorperate the Signature of Amit Kumar of Building Department. 5.Changes on messaging of Invoicing Section regarding invoice Generation and Viewing of Invoices. 6.Display the report No on Dispatched Detail Popup in Sales/reports Listing. 7.Display the Invoice No on Dispatched Detail Popup in Sales/Invoice Listing. | 7 | 2018-05-09 | 2018-05-09 | 2018-05-09 | Praveen Singh | 9 | 9 | Done
7 | 2018-05-10 | Client Feedback Points(Changes Discussed): 1.Food Report Design Auto Break Implementation. 2.Ayurvedic Report Design Auto Break Implementation. 3.Displaying of Customer name having pending orders for invoicing at the time of Invoice Generation. 4.Incorperate the Signature of Amit Kumar of Building Department. 5.Changes on messaging of Invoicing Section regarding invoice Generation and Viewing of Invoices. 6.Display the report No on Dispatched Detail Popup in Sales/reports Listing. 7.Display the Invoice No on Dispatched Detail Popup in Sales/Invoice Listing. | 8 | 2018-05-10 | 2018-05-10 | 2018-05-10 | Praveen Singh | 9 | 9 | Done
8 | 2018-05-11 | 1.Displaying Of PO-Date Calender while adding a order having Billing Type PO-Wise. 2.Displaying of Product Name according to Sample Name and Product Name entered by the User. 3.Changes the discount value of Booked Orders. 4.Modified the Layout of Invoice generation Blade. | 9 | 2018-05-11 | 2018-05-11 | 2018-05-11 | Praveen Singh | 7 | 7 | Done
9 | 2018-05-14 | Dynamic Header Implementation in all departments:Test Report | 10 | 2018-05-11 | 2018-05-15 | 2018-05-15 | Praveen Singh | 24 | 23 | Done
10 | 2018-05-15 | Displaying of Right Logo Dynamically on all Test Report Blade: | 11 | 2018-05-16 | 2018-05-16 | 2018-05-16 | Praveen Singh | 9 | 9 | Done
11 | 2018-05-17 | User Feedback Points: 1.Pharma Department Stamp not displaying on PDF Generation of Report 2.Pharma Department User Sign not displaying on PDF Generation of Report 3.Data Validation of Listed MIS-Reports: a)Analyst Wise Performance Summary b)Sample Log Status | 12 | 2018-05-17 | 2018-05-17 | 2018-05-17 | Praveen Singh | 9 | 9 | Done
12 | 2018-05-18 | A.Software Updates on Staging Server. 1.Updated Code on ITC Dev Staging Server from SVN. 2.Updated DB on ITC Dev Staging Server. B.User Feedback Points: 1.Removal of Duplicate Customer in Invoicing. 2.Changing of Billing Type in booked orders. 3.Discount Updation in booked Orders. | 13 | 2018-05-18 | 2018-05-18 | 2018-05-18 | Praveen Singh | 9 | 9 | Done
13 | 2018-05-21 | User Feedback Points: 1.Mailing of State and City DB. 2.Mail Sending issue in Invoice Section. 3.Customer Portal Link. 4.Dynamic Header Foooter Implementation on Invoice Section. 5.Food Test Report:Implementation of Dynamic Content. 6.Testile Test Report:Implementation of Dynamic Content with Replacement of Sample Reg. No. with Report No. from Reviewing to Dispatching Order Process. | 14 | 2018-05-21 | 2018-05-21 | 2018-05-21 | Praveen Singh | 9 | 9 | Done
14 | 2018-05-22 | User Feedback Points: 1.In Report,under name of replace F& C with Textile. 2.In Order Booking Form search box for searching any parameter at the parameter selection window is still not updated. 3.Reports of Food(Chennai) for reviewing is visible to Reviewer of Panchkula. Please Check. 4.Signature of Microbiologist will be branch wise. At present signature of Parkash Kaur is used for Chennai also which is wrong.Rectify it. 5.Search Box for method & instruments on Scheduling Job Sheet Print is not updated yet. | 15 | 2018-05-22 | 2018-05-23 | 2018-05-23 | Praveen Singh | 12 | 12
15 | 2018-05-22 | Dynamic Header Implementation: Invoicing(All Division) | 16 | 2018-05-24 | 2018-05-24 | 2018-05-24 | Praveen Singh | 9 | 9 | Done
16 | 2018-05-23 | User Feedback Points: 1.Search Box for method & instruments on Scheduling Job Sheet Print is not updated yet. 2.Adding of Discount Type and discount value in listed booked orders: a)P01-1804280040 b)P01-1804270159 c)P01-1804270157 d)P01-1804260069 e)P01-1804260040 f)P01-1804260039 g)P01-1804210047 h)P01-1804190091 i)P01-1803100046 j)P01-1804170042 3.Correction in listed generated Invoice Numbers:T-1805220023. 4.In our TAT report,presently cancelled samples are displayed pending for scheduling which is incorrect.Please replace 'P' with 'H' for hold samples at the time of scheduling.Similarly cancelled samples are also displayed as 'P' in scheduling or testing: Case I :- In Case of Hold Samples,the status of sample will be "Hold" & In Scheduling column we can use the alphabet 'H' in place of 'P' Case II :- In case of Cancelled samples,the status will be Cancelled and all the columns of that sample will be blank. | 17 | 2018-05-23 | 2018-05-23 | 2018-05-23 | Praveen Singh | 9 | 9 | Done
17 | 2018-05-24 | Client Feedback Points: 1.Give 30 % discount in below order booking codes: a.F01-1805160890,b.F01-1805050282,c.F01-1805050281,d.F01-1804301752 2.Convert invoicing type to customer wise product for below order nos.: a.F01-1805160883,b.F01-1805160882,c.F01-1805160881,d.F01-1805160880,e.F01-1805100517,f.F01-1805100516,g.F01-1805100515,h.F01-1805100514,i.F01-1804301774,j.F01-1804301773 3.JOB SHEET OF PHARMA NOT PRINTING:Order no are as follows:- P01-1805250052,P01-1805250055,P01-1805250056,P01-1805210113,P01-1805210114,P01-1805210116,P01-1805210117,P01-1805240107 | 18 | 2018-05-24 | 2018-05-24 | 2018-05-24 | Praveen Singh | 5 | 5 | Done
18 | 2018-05-28 | Client Feedback Points: 1.The interlaboratory or compensatory samples are reflected Pending for invoicing in TAT report. Replace interlaboratory samples with alphabet "I"(Interlaboratory) in place of "P" (Pending). 2.In order Booking Confirmation Mail Subject Line should be Customer Name,Sample Name,Batch No. & Order Booking No. 3.In Test Report Mail subject should be Customer Name,Sample Name,Batch No. & Order Booking No. Client Feedback Points: 4.One sample of Tirupati Life Sciences which is pending for invoicing in TAT report but in software Sales-Reports it is displayed in DIspatching Stage. Order No. is : F01-1804201296. a)Tirupati Life Sciences-F01-1804201296 b)Pritam International Glycerine having order no.-F01-1803301531.It is pending for invoicing in ERP & but dispatched in software. 5.We booked 16 samples of procter & gamble on 18 May and having expected due date of 25 May 2018 but when we generate TAT on 26052018 the expected due date of all samples changed to 23.5.2018. I want to know that does any one change the expected due date of samples or there in some problem in generation.Please send me the log of these samples or check on your end. | 19 | 2018-05-28 | 2018-05-28 | 2018-05-28 | Praveen Singh | 9 | 9 | Done
19 | 2018-05-29 | Scope-2 meeting and discussion with Client regarding listed Modules: 1.Auto Scheduling 2.Invoice Cancellation and Re-generation. 3.Auto Credit and Debit Note Updation on Invoice Cancellation and Re-generation. 4.MIS-Reports 5.Pop-up Implementation of user based on role assigned to it. 6.Message Popup Window on cancelaation of any order for all department. 7.Displaying of Schedulled Date and Completed Date in Assign Job Window of Scheduling. 8.Editing of Expected Due Daate for certain Customer based on record available in Custimer Defined Structure. | 20 | 2018-05-29 | 2018-05-29 | 2018-05-29 | Praveen Singh | 9 | 9 | Done
20 | 2018-05-30 | Client Feedback Points: 1.In Textile invoice : T-1805220023 Change Invoicing To customer code : 1528 in order no. T01-1805180028 2.In Food Invoice having invoice no. : F-1804260349-Change Invoicing to Cust Code 303( Marico Limited ) in only these two order no;s F01-1804231408 & F01-1804241463 3.One sample of Tirupati Life Sciences which is pending for invoicing in TAT report but in software Sales-Reports it is displayed in DIspatching Stage: a)Tirupati Life Sciences-F01-1804201296 b)Pritam International Glycerine having order no.-F01-1803301531.It is pending for invoicing in ERP & but dispatched in software. 4.On Genaration of Invoice Form,Provision of selection of all Department to administrator,so that administrator can generate invoice of multiple department simultaneously. 5.Displaying of rate inputed by the Invoicer or not at the time of Invoice Generation in Popup window on clicking any Orde/Report No.If not then 0.00 in Red color else inputed rate in green color. | 21 | 2018-05-30 | 2018-05-30 | 2018-05-30 | Praveen Singh | 9 | 9 | Done

## June-2018
ITC ERP TASK DETAIL(June-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-06-01 | Small Amendments: -In Sales-Generate Invoices window add one more cols of Invoicing to (name of Customer invoice will be generated). -Provision of change of Customer name by the Administrator if the receiver will do the receiving on wrong name. | 1 | 2018-06-01 | 2018-06-01 | 2018-06-01 | Praveen Singh | 9 | 9 | Done
2 | 2018-06-08 | 1.Task Name:Regarding Back up:- a)Please update Invoice no. of F-1806050001 (Chennai) to F-1806080143 and invoice date will be 08.06.2018. 2.Printout of these invoices are not visible .Please check.Invoices are F-1805010433 & F-1805170702 | 2 | 2018-06-08 | 2018-06-08 | 2018-06-08 | Praveen Singh | 2 | 2 | Done
3 | 2018-06-11 | Changes discussed in dynamic header Implementation and provided in Mail: A.Pharma :- 1)Form 39 & License no. will be incorporated on top of Interstellar Testing Centre Pvt. Ltd. (already have in previous test report format) 2)NABL Certificate No. & its validity under the logo of ITC labs on left corner of report.(This certificate no. & validity will be changed with time). On printing of test report the certificate no. & validity displayed will be related to that corresponding time. B.Ayurvedic :- Format of Ayurveda will be same as that of Pharma.(No NABL Certificate No. & its validity is required.) | 3 | 2018-06-11 | 2018-06-12 | 2018-06-12 | Praveen Singh | 13 | 13 | Done
4 | 2018-06-11 | Urgent Requirement of 2 MIS Reports: a)Sample log status b)Instrument & User wise performance Note:Changes Provided in a word document. | 4 | 2018-06-12 | 2018-06-16 | 2018-06-16 | Praveen Singh | 30 | 32 | Done
5 | 2018-06-14 | Client Feedback Points: 1.Ammendment in invoice a)In invoiceno .- F-1806090012 change amount into 3590 in place of 2630. The tax slab will be IGST :- 646 Total amount will be 4236 b)In invoiceno .- F-1806090012 change amount into 1600 in place of 1200. The tax slab will be SGST = 144 & CGST :- 144 Total amount will be 1888. | 5 | 2018-06-14 | 2018-06-14 | 2018-06-14 | Praveen Singh | 2 | 2 | Done
6 | 2018-06-14 | Software Updation on ITC Dev Server | 6 | 2018-06-14 | 2018-06-14 | 2018-06-14 | Praveen Singh | 2 | 2 | Done
7 | 2018-06-18 | A.Client Feedback points: 1)Correction: Invoice no. is F-1806140021 of Chennai branch Customer Name is Cargo Inspectors & Superitendence Co. Pvt. Ltd. This invoice has two samples :- Change the amount of Sample two of Black Tea having order no. F02-1806080042 . The present amount is 3590. Change this amount to 7630, Total amount will be Rs. 10260 IGST will be :- Rs. 1847 Total amount will be Rs. 12107 Do correction on priority B.TimeSheet:Filling of Timesheet and Email : Reviewing of Emails. C.R&D on Cross Domain Data Transfer regarding Web Module of ITC Customer Portal. 2)Pharma detail is not matching: There is some error in the TAT report. Yesterday reports were mailed we got the report from system generated email ID, but in TAT it is showing as pending. Pls find the screen shot for your information with example. I am unable to extract the actual data to share with everyone. Pls do the needful urgently. | 7 | 2018-06-18 | 2018-06-18 | 2018-06-18 | Praveen Singh | 2 | 2 | Done
8 | 2018-06-20 | Client Feed Points: 1)Change invoicing to Teijin Gurgaon(Cust code is 595): Textile invoice no are T-1806110040 & T-1805260027 2)Change is in the name of customer in following orders: a)P01-1806110129 b)P01-1806110130 Currently it is booked in Procter & Gamble Hygiene and Health Care Limited -Baddi (Cust Code -393) but it should be in Procter & Gamble Hygiene and Health Care Limited - Thailand cust code - CUST1905 | 8 | 2018-06-20 | 2018-06-20 | 2018-06-18 | Praveen Singh | 2 | 2 | Done
9 | 2018-06-22 | Client Feedback Points: 1)Invoice no. of building to be corrected:I am sending you invoice as an attachment. 2)Please find the attachment of Chennai Users.Please verify the user-signature Label/Name with the ERP Employes List. 3)Please share the data of customer master in excel format. | 9 | 2018-06-22 | 2018-06-22 | 2018-06-22 | Praveen Singh | 1 | 1 | Done
10 | 2018-06-26 | Software Updation on ITC Live/StagingServer | 10 | 2018-06-26 | 2018-06-26 | 2018-06-26 | Praveen Singh | 3 | 2 | Done
11 | 2018-06-26 | Client feedback Points: 1.Changes on Food Test Report regarding Part-B Report Section auto break. 2.Changes on Building Test Report regarding Part-B Report Section auto break. 3.Addressed the issues regarding editing of Order in Order booker Role Login. 4.Addressed the issues regarding Updation of Invoicing Type Consideration Parameters Coloum in Test Parameter Controller. 5.Updated the missing Micro-biologist Name in Order Master of all department except Pharma. | 11 | 2018-06-26 | 2018-06-26 | 2018-06-26 | Praveen Singh | 5 | 5 | Done
12 | 2018-06-27 | Client feedback Points: 1.Changes on Environment Test Report regarding Part-B Report Section auto break. 2.Changes on Helmet Test Report regarding Part-B Report Section auto break. 3.Changes on Textile Test Report regarding Part-B Report Section auto break. 4.Changes on Pharma Test Report regarding Part-B Report Section auto break. 5.Addressed the Email Sending issues in all Departments. 6.Addressed the scheduling issues regarding processing slow in assigning Job for Scheduler Role. 7.Amendment of Orders regarding biiling Type,Invoicing Type,discount Type and discount value. 8.Amendment of Invoices regarding sgst_rate,sgst_amount,cgst_rate,cgst_amount,igst_rate,igst_amount and total_amount. 9.Changes the Email Templates for Environment Department regarding Mobile Number Updation. | 12 | 2018-06-27 | 2018-06-27 | 2018-06-27 | Praveen Singh | 7 | 7 | Done
13 | 2018-06-30 | Client feedback Points: Change billing types of these customers into PO wise and invoicing type into Customer wise Product(of all samples in any stage). The name of customers are as follows:- (a) HETERO LABS LTD. - Cust Code 507 (b) Hetero Labs Ltd. Unit-I -Cust Code 539 (c) Hetero Labs Ltd. Unit-II -Cust Code 540 (d) HETERO FORMULATION DIVISION - Cust Code 843 (e) HETERO LABS LIMITED (R & D) -Cust Code 844 | 14 | 2018-06-30 | 2018-06-30 | 2018-06-30 | Praveen Singh | 1 | 1 | Done

## July-2018
ITC ERP TASK DETAIL(July-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-07-06 | Client Feedback Points: 1.Add conveyance of Rs. 500 in order booking no. E02-1806090022 Then in invoice: Invoice no. is E-1806280011. Total remains same Rs. 3950 Conveyance -Rs. 500 SGST :- 400 CGST:- 400 Grand Total : Rs. 5250 | 1 | 2018-07-06 | 2018-07-06 | 2018-07-06 | Praveen Singh | 1 | 1 | Done
2 | 2018-07-10 | Client Feedback Points: 1)Exchanging of Invoice Number and Invoice Date in listed two Invoices: a)E-1806250009-Chennai -Gabriel India Pvt Ltd. b)E-1806230008-Chennai-M/S. PIRAMAL ENTERPRISES LIMITED 2)Amendment of Amount in listed two Invoices: a)E-1806250009-Chennai-M/S. PIRAMAL ENTERPRISES LIMITED b)E-1806230008-Chennai -Gabriel India Pvt Ltd. 3)Changing of Invoice Date in listed Invoices: a)Invoicing date of E-1806230008 is E-1806210008(dated :- 21/06/2018) b)Invoicing date of E-1806250009 is E-1806230009(dated :- 23/06/2018) c)Add conveyance in invoice no. E-1806230009 in order no. E02-1806160064 d)THEN CORRECTED VALUE OF INVOICE IS :- TOTAL-8500,SGST:- 765.00,CGST-765.00 and GRAND TOTAL :- 10030 | 2 | 2018-07-10 | 2018-07-10 | 2018-07-10 | Praveen Singh | 2 | 2 | Done
3 | 2018-07-18 | (A) Customer Wise Product - In Case of Customer Wise Product sample name is directly related to test master name. (i) In sample name textbox - Only distinct samples of corresponding customers will be displayed in sample name textbox.-New Modification regarding displaying of Product Master along with Sample Name. (ii) No tree view option will be displayed if rates will be product wise-New Modification (iii) In invoicing - system is not picking rates for customer wise product.-System Error Error is :- If same alias name we had created for multiple test masters, for corresponding customer we used one alias and enter rates in invoicing structure,system allow user to do booking but not displayed any amount in invoicing until we will not enter rates in all test masters of that product alias. (B) Customer Wise Parameter :- In case of customer wise parameter (i) In sample name textbox :- only distinct sample names of corresponding customer will be displayed-New Modification regarding displaying of Product Master along with Sample Name. (ii) On selecting the parameter from tree view ,there should be one col. in last of grid which displayed the rates of that parameter so that it will be clear to user which parameter is pending for rates. Because in present scenario syestem is displaying the error "Invoicing type is not defiend " but it is not clear to user which parameter is pending for rates.-New Modification (iii) On typing the sample name for Customer Wise Parameter , system will automatically checks all the parameters previously booked for that sample had rates defined in Invoicing master or not . If any parameter don't have rate in master then system will display a message box for that parameter and will not allow user to proceed booking.-New Modification(Discussed with you). | 3 | 2018-07-18 | 2018-07-19 | 2018-07-19 | Praveen Singh | 16 | 16 | Done
4 | 2018-07-26 | B)Client Feedback Points: (a) Order Editing:- System is showing invoicing error while editing a order in "Customer Wise Parameter" . COMMENT:Please find the attachment. (b) Customer Wise Product :- System is not picking rates at the time of invoicing as discussed earlier. COMMENT:Discussed / Will be addressed (c) Older Bookings :- In older bookings of food at the time of order editing system is not picking customer name. COMMENT: Addressed (d) Fix value in Description of master :- Please share master list of those masters in which we have default value in description filed COMMENT:Please find the attachment. | 4 | 2018-07-26 | 2018-07-26 | 2018-07-26 | Praveen Singh | 2 | 2 | Done
5 | 2018-07-30 | A)USER ERROR: 1)Change into Customer Wise Product:- Pure & Cure P01-1806250128, P01-1806220116, P01-1806220115, P01-1806190164, P01-1806180264, P01-1806110173, P01-1806110171, P01-1806110169, P01-1806110167, P01-1806050188 2)Change Billing Type -Monthly P01-1805010055, P01-1805010067, P01-1804300103 3)Remove Duplicate Party Name Merge Names :- Cust Code :- 855 LENUS LIFE CARE PVT. LTD. Cust Code:- 177 Lenus Lifecare Pvt. Ltd. Keep Cust Code 177 and merge data of 855 into it. Change Billing Type -Monthly B)Please update this file today so that we can include these samples in monthly invoicing. C)Fix value in Description of master :- Please share master list of those masters in which we have default value in description filed. COMMENT:Please find the attachment. D)Please resolve this today in user query hour . This sample was booked compensatory by mistake now we have to generate invoice of this sample. Please open this ammendment option on Admininstrative end also. Order:F02-1807200087/Chennai/Regal Healthy Fine Foods,Hyderabad/20-07-2018/30-07-2018/Sweet Sample | 5 | 2018-07-30 | 2018-07-30 | 2018-07-30 | Praveen Singh | 2 | 2 | Done
6 | 2018-07-31 | B)Client feedback Points: Amendment of Orders regarding listed parts: i)biiling Type ii)Invoicing Type iii)discount Type iv)discount value. v)Customer Name | 6 | 2018-07-31 | 2018-07-31 | 2018-07-31 | Praveen Singh | 2 | 2 | Done
7 | 2018-07-31 | Software Update on Staging Server | 7 | 2018-07-31 | 2018-07-31 | 2018-07-31 | Praveen Singh | 2 | 2 | Done

## Aug-2018
ITC ERP TASK DETAIL(Aug-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-08-04 | A)Client feedback Points: 1)In (1) Order Cancellation task:Updated the records of all cancelled orders in newly created table `order_cancellation_dtls`. 2)In (8) MIS Reports-(b) Amended Reports Task:Updated the records of all amended orders in newly created table `order_amended_dtl`. 3)Approved date is showing as 01.01.1970-I. 4)Approved date is showing as 01.01.1970-II. 5)Allowing user to accept dash if po-number is not available. | 1 | 2018-08-04 | 2018-08-04 | 2018-08-04 | Praveen Singh | 8 | 8 | Done
2 | 2018-08-06 | 1)Order Form : Editing of Customer Detail Section: a)Billing Type b)Invoicing Type c)Discount Type d)Discount Value 2)Please change approval name to Indra Rai.Order No.'s are: a)F01-1807110692 b)F01-1807110696 c)F01-1807140849 d)F01-1807130794 3)In below report microbiologist will be Parkash Kaur in place of Udayveer: a)F01-1806281522 | 2 | 2018-08-06 | 2018-08-06 | 2018-08-06 | Praveen Singh | 8 | 8 | Done
3 | 2018-08-09 | Software Update on ITC Live/Staging Server | 3 | 2018-08-09 | 2018-08-09 | 2018-08-09 | Praveen Singh | 2 | 2 | Done
4 | 2018-08-10 | Client feedback Points: 1.Invoice wise report printing-without Header and Footer. 2.Andra/Telangana Invoice Format-Label of ServiceTax will be service Amount. 3.Sales Report by accounts for reconciliation of invoices Mis-Report:Account Sales Detail-GST,Payable Amount Rounding. 4.Tree view of the fixed rate Customer. 5)Testing of Order Editing Modules: a)Order Booking Form : Changes in displaying of Invoicing,Billing,Discount Type Selectbox in case of following: Case I: If invoicing of any order is not completed,then all options of Invoicing,Billing,Discount Type will be displayed. Case II: If invoicing of any order is completed,then only selected options of Invoicing,Billing,Discount Type will be displayed. b)Order Booking Form :Changes on displaying of Parameter Rate in listed cases: Case I : If User changes the Customer Detail by selecting it from Customer Selectbox while editing. Case II : If User changes the Invoicing Detail by selecting it from Invoicing Type Selectbox while editing. 6)Tested the Order Confirmation Mail using Cron Job on ITC Live Server. | 4 | 2018-08-10 | 2018-08-10 | 2018-08-10 | Praveen Singh | 9 | 9 | Done
5 | 2018-08-13 | Client feedback Points:Points available in Documents: 1.Order Booking : Tree View for fixed Rate Customers. 2.Environment Report:Table border of Test Report. 3.Invoice : Insertion of Dispatched Detail data of all department in the Invoice Dispatch Detail Table. 4.Amendment Report : Insertion of Amended Report data in the order Detail Amended Table. 5.Order Cancellation: Insertion of Cancelled Report data in the order Cancellation Detail Table. 6.Chennai Test Report Format: a)Received On : Order Booking Date b)Commenced On : First Parameter scheduled date of an order. c)Best Before End : Remove this Line d)Customer Reference No : Ref. No./Ref. Date e)Unit Column: Remove this Column 7.Customer Master : Export to Excel data is not showing all columns of Customer Master Table. 8.MIS-Report / Delay Status Report:Don't Include Interlaboratory/Compensatory Order in count. | 5 | 2018-08-13 | 2018-08-13 | 2018-08-13 | Praveen Singh | 9 | 9 | Done
6 | 2018-08-14 | A)Client feedback Points: 1.New bill format of Andhra/Telangana: Changes Discussed with Client: On Invoice Generate Criteria Popup: a)Implement a checkbox with label 'State-Wise'. b)If User Select the Checkbox,then system will generate the State-Wise Invoice Templete, c)And If User uncheck the Checkbox,then system will generate Normal Invoice Templete. On Invoice Listing Page: a)Implement a Popup with Button 'Normal'/'State-Wise which will prompt upon clicking the button View Invoice. b)If User Select the 'Normal' button,then system will generate Normal Invoice Templete, c)And If User Select the 'State-Wise' button,then system will generate State-Wise Invoice Templete. 2.Implemented the Email Templete of Water Department regarding Listed Section: a)Order Booking Confirmation, b)Reports and b)Invoices 3.Uploaded the Email Templete of Water Department regarding Listed Section: a)Order Booking Confirmation, b)Reports and b)Invoices | 6 | 2018-08-14 | 2018-08-14 | 2018-08-14 | Praveen Singh | 6 | 6 | Done
7 | 2018-08-11 | POINT-3-Provision of Section Incharge for reviewing of report: (a)Common instrument for multiple section incharges:- Challenge:- In this case the parameter of common instrument will be displayed on the window of both section incharges and it will not be shifted into reviewing stage until it is not reviewed by both section incharges Solution :- if one incharge approve parameter of common instrument then it will be by default remove from other incharge end. (b)Pendency of reports will be role wise not user name wise :- Challenge :- If after adding the result of some parameters we changed the role of section incharge from one user to another user then system will not displayed all the pending reports of section incharge to the new use. Solution:- Righrts will be role wise not the user name wise. (c)Stage of sample :- Challenge:- Stage of sample shifted to section incharge after the complete testing of all parameters of sample Solution :- If testing of parameters of one section is completed then it will be shifted to section incharge irrespective of the status of parameters of other sections in the same sample | 7 | 2018-08-16 | 2018-08-21 | 2018-08-21 | Praveen Singh | 24 | 24 | Done
8 | 2018-08-20 | Implementation of Template Design and Testing of Order Process Stage for New Department Water: a)Testing Stage. b)Section-Incharge Stage. c)Reviewing Stage. d)Finalizing Stage. e)Approving Stage. f)Invoicing g)Dispatching h)Dispatched | 8 | 2018-08-21 | 2018-08-22 | 2018-08-22 | Praveen Singh | 12 | 12 | Done
9 | 2018-08-23 | Software Update on ITC Live Server for listed task: 1)POINT-3-Provision of Section Incharge for reviewing of report: 2)Implementation of Template Design for New Department 'Water'. | 9 | 2018-08-23 | 2018-08-23 | 2018-08-23 | Praveen Singh | 1 | 1 | Done
10 | 2018-08-27 | Editing of listed two parameter by the Reviewer in all departments: 1)Description Parameter: i)Food ii)Environment iii)Building iv)Water v)Textile vi)Helmet vii)Ayurvedic viii)Pharma 2)Reference to protocol parameter: i)Pharma | 10 | 2018-08-27 | 2018-08-27 | 2018-08-27 | Ruby | 8 | 8 | Done
11 | 2018-08-28 | A)Client Feedback Points: 1.Resolved (please add general information) 2.Submitted sample is optional and is not applicable for all.Please remove 3.Part D has been mentioned which is not required 4.Please remove, only remarks would be enough 5.Instead of Other details , please change it to :Sample Submission type 6.Options to be added are:- Submitted and -Sampled by Lab Rep. 7.Also environment reports are generated in 2 different formats, please take a note of it and do the needful. (for e.g. E02-1807300234 & E02-18073002120 are in two different formats) will be rectified by you. 8.Issued to client Name.Not required in all pages, only to be mentioned in first page. 9.Can we enable this button on user end(in point 2). Please open on user end. 10.Provide provision of cancellation & regeneration of invoices button on invoicer end. | 11 | 2018-08-28 | 2018-08-28 | 2018-08-28 | Praveen Singh | 3 | 3 | Done

## Feb-2022
ITC ERP TASK DETAIL(Feb-2022)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Developer | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2022-02-08 | QH : E01-2112281414 second page is coming blank for with equipment and with digital signature.Same problem is coming other 3 reports. Please correct this and i will check rest. A01-2201180081,82, A01-2201190089 | 1 | 2022-02-08 | 2022-02-08 | Praveen Singh | 1 | Done
2 | 2022-02-14 | Display only current month data in all tabs of below modules.(a)Product master creation --- Master-->Tests Parameters Product Tests (b)Master -->Invoicing Product master alias State wise products Customer wise product Customer wise parameter (c)Payments Debite Notes Credit Notes | 2 | 2022-02-14 | 2022-02-18 | Praveen Singh | 25 | Done
3 | 2022-02-18 | Write Label Test Report in Form 39 & Form 50 template Pharma | 3 | 2022-02-18 | 2022-02-19 | Praveen Singh | 5 | Done
4 | 2022-02-19 | Sales-Samples - Add LIMS Customer & Address along with Customer Name & City.Sequence will be LIMS Customer Code /Customer Name/City | 4 | 2022-02-19 | 2022-02-21 | Praveen Singh | 5 | Done
5 | 2022-02-19 | Sales-Order-Add LIMS Customer code & Address in Customer Detail along with Customer Name & City.Sequence will be LIMS Customer Code /Customer Name/City | 5 | 2022-02-21 | 2022-02-21 | Praveen Singh | 3 | Done
6 | 2022-02-19 | Sales-Order - Dashboard-- Filter for searching Place & Prototype No. & Expected Due Date,customer code. | 6 | 2022-02-21 | 2022-02-21 | Praveen Singh | 4 | Done
7 | 2022-02-19 | Sales-Reports- Dashboard- Add Customer code & City for search filter on Admin,CRM & Dispatcher Role | 7 | 2022-02-22 | 2022-02-24 | Praveen Singh | 5 | Done
8 | 2022-02-19 | Master-Customer - Dashboard - Add Customer city column and search filter. | 8 | 2022-02-24 | 2022-02-24 | Praveen Singh | 3 | Done
9 | 2022-02-24 | Mailgun Process Document Study and its Implementation | 9 | 2022-02-24 | 2022-02-24 | Praveen Singh | 3 | Done
10 | 2022-02-19 | Provision to upload PO no. in order bookings using csv | 10 | 2022-02-25 | 2022-02-28 | Praveen-Singh | 14 | Done
11 | 2022-02-19 | Cosmetics Report Format - Replicate Form 39 as it is and change label 'Form 39' to 'Cos24' | 11 | 2022-02-28 | 2022-03-03 | Praveen-Singh | 12 | Done
12 | 2022-02-01 | Chand Sir | 13 | 2022-02-01 | 2022-02-28 | Chand Sir | 4 | Done
[6 empty] | Total | 84