## Jan-2022
ITC ERP TASK DETAIL(Jan-2022)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Developer | Expected/Approved Hours | Dev Status
1 | 2021-01-01 | AWS-SES-Implementation of Amazon SES SDK Mailing Module | 1 | 2021-01-05 | 2022-01-08 | Praveen-Singh | 30 | Done
2 | 2022-01-10 | QH -Software Updation and Feedback Point Resolution | 2 | 2022-01-10 | 2022-01-10 | Praveen-Singh(QH) | 4 | Done
3 | 2022-01-11 | QH : Nabl New Logo Implementation in Test Report (All Branches and Departments) : Feddback Points- Testing and Implementation on Live Server: | 3 | 2021-10-07 | 2021-10-13 | Praveen-Singh(QH) | 4 | Done
4 | 2022-01-12 | QH : Change in provision of Authorized signatory in Food-Panchkula report template : Chnages : Displaying of Reviewer Signature if Section Incharge Signature is not present in the Master | 4 | 2022-01-12 | 2022-01-12 | Praveen-Singh(QH) | 4 | Done
5 | 2022-01-12 | QH : Software Update Feedback Points :i)Addressed the PDF Test Report format issue of water department-W01-2112310147,W01-2112180064. ii)Added the common logic to resolve all the PDF format issue of water department. iii)Food PDF Test Report- First Page Coming Blank. | 5 | 2022-01-12 | 2022-01-12 | Praveen-Singh(QH) | 3 | Done
6 | 2022-01-12 | QH : Software Update Feedback Points :i)Addressed the scheduling issue on live server.ii)Addressed/Tested the Sales Executive updation process issue using CSV upload. | 6 | 2022-01-14 | 2022-01-14 | Praveen-Singh(QH) | 1 | Done
7 | 2022-01-16 | QH : Software Update Feedback Points : Cosmetic PDF Test Report- First Page Coming Blank : Still facing first page blank issue in Cosmetics & Technical Pesticides | 7 | 2022-01-16 | 2022-01-16 | Praveen-Singh(QH) | 1 | Done
8 | 2022-01-17 | Provision to download uploaded TRF File in CRM Role | 8 | 2022-01-17 | 2022-01-17 | Praveen-Singh(QH) | 3 | Done
9 | 2022-01-18 | QH : Error in Report Format : Addressed the listed client feedback points: 1) As discussed Kindly sort the below reports format error : E01-2112160740,E01-2112160741,--E01-2112160742 & E01-2112160743 2)B01-2112310001 page no.is overlapping with document no. In building reports.3)First page blank issue is coming in B01-2201110001 ,0002,003. | 9 | 2022-01-18 | 2022-01-18 | Praveen-Singh(QH) | 2 | Done
10 | 2022-01-19 | QH : Form 39 & Form 39 A : Header Types Implementation on Pharma PDF Report and New PDF Report Implementation with Form 39 : Implementation on Live Server | 10 | 2022-01-19 | 2022-01-19 | Praveen-Singh(QH) | 1 | Done
11 | 2022-01-20 | QH : Error in Report Format : Addressed the listed client feedback points: Please check E01-2201130744, printout is not coming properly. Facing issue in maximum reports.In maximum reports first page is coming blank.O01-2111230101 without logoNo report with new logo is available in software .Please correct above one. Please check P01-2112280074,A01-2112230159 and 0160 rest same as above. | 11 | 2022-01-20 | 2022-01-20 | Praveen-Singh(QH) | 1 | Done
12 | 2022-02-01 | QH : Correction in Report Format:E01-2112311683,E01-2112311684,E01-2112311685 & E01-2112311686 | 12 | 2022-02-01 | 2022-02-01 | Praveen-Singh(QH) | 1 | Done
13 | 2022-01-01 | Chand Sir | 13 | 2022-01-01 | 2022-01-31 | Chand Sir | 5 | Done
[6 empty] | Total | 60
QH : Query Hours