## Aug-2020
ITC ERP TASK DETAIL(Aug-2020)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2020-07-28 | Regarding General Information in Environment Report | 1 | 2020-08-01 | 2020-08-06 | 2020-08-06 | Praveen Singh | 15 | Done
2 | 2020-08-05 | Back date provision of Building : Sample,Order and Report Number generation in Back Date Booking : Changes | 2 | 2020-08-13 | 2020-08-14 | 2020-08-14 | Praveen Singh(QH) | 1 | Done
3 | 2020-08-08 | Query Hours-(a) Please help to change product batch no. in stability protocol no. P01-2008060002 of product D95-3-2a with 3.0 % Night Owl DOIS 2018C (Fragrance GCAS: 91731015).Please change batch no. from B0205A45502 to B0205A45503 | 3 | 2020-08-12 | 2020-08-12 | 2020-08-12 | Praveen Singh(QH) | 1 | Done
4 | 2020-08-08 | Approval-(Point-b)- Query Hours-(b) In all formats of test report we are writing one remark line"'*' represents categories/test parameters not covered under NABL ¦ '**' represents outsource sample ¦ '#' represents Customer Defined Fields" but as per the implementation of NABL 133 in second report(2) we have to remove" '*' represents categories/test parameters not covered under NABL " because as per the NABL 133 in place of highlighting non-accredited parameters with "*" we are generating separate report.This change is applicable | 4 | 2020-08-17 | 2020-08-24 | 2020-08-24 | Praveen Singh | 21 | Done |  | 1 hr QH approved by client
5 | 2020-08-08 | Query Hours-(c) The terminology " Submitted by" mentioned in PART A of test report can be replaced with "Test Request Submitted By" in test report format.This change is applicable for Building,Textile,Cosmetics,Food,Technical Pesticides,Helmet) | 5 | 2020-08-13 | 2020-08-13 | 2020-08-13 | Praveen Singh(QH) | 3 | Done
6 | 2020-08-08 | Query Hours-(d) In Order confirmation mail template system is not highlighting non-accredited parameters with "*". Please check.(point given in NABL 133) | 6 | 2020-08-12 | 2020-08-12 | 2020-08-12 | Ruby(QH) | 2 | Done
7 | 8-31-2020 | Chaand Sir | 7 | 8-31-2020 |  |  | Chaand Sir | 3 | Done
[7 empty] | Total | 46