## Feb-2020
ITC ERP TASK DETAIL(Feb-2020)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2020-01-27 | Regarding Chennai report formats to be incorporated in LIMS : | 1 | 2020-02-01 | 2020-02-13 | 2020-02-13 | Praveen Singh | 41 | Done
2 | 2020-02-04 | Client Side Visit regarding below points: i)Task Discussion ii)New Scope Discussion iii)Documentation/Mockup creation of New Scope | 2 | 2020-02-04 | 2020-02-04 | 2020-02-04 | Praveen Singh | 5 | Done
3 | 2020-02-14 | Web Portal : Auto Synchronization of Report/Invoice/VOC using CRON JOB Scheduler | 3 | 2020-02-14 | 2020-02-15 | 2020-02-15 | Praveen Singh | 9 | Done
4 | 2020-02-17 | Regarding Task List | 4 | 2020-02-17 | 2020-02-20 | 2020-02-20 | Praveen Singh | 4 | Done
5 | 2020-02-24 | Changes : APEDA Chennai report formats to be incorporated in LIMS | 5 | 2020-02-24 | 2020-02-29 | 2020-02-29 | Praveen Singh | 14 | Done
6 | 2019-12-01 | Chaand Sir | 6 | 2020-02-01 |  |  | Chand Sir | 4 | Done
[7 empty] | Total | 77
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs