## July-2020
ITC ERP TASK DETAIL(July-2020)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2020-06-26 | Back date provision of Building : Sample,Order and Report Number generation in Back Date Booking | 1 | 2020-07-04 | 2020-07-04 | 2020-07-04 | Praveen Singh | 4 | Done
2 | 2020-07-04 | In continuation of NABL 133 task : Order confirmation mail template : | 2 | 2020-07-04 | 2020-07-07 | 2020-07-07 | Praveen Singh/Ruby | 14 | Done
3 | 2020-07-08 | ITC CUSTOMER PORTAL | 3 | 2020-07-08 | 2020-07-10 | 2020-07-10 | Praveen Singh | 7 | Done
[7 empty] | Total | 25