## JAN-2018
ITC ERP TASK DETAIL(JAN-2018)
S.No. | Date | Detail | Priority | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 15-12-2017 | Changes in Migaration:Addition of two new coloum Cost Price and Selling Price. | 5 | 2018-01-01 | 2018-01-04 | Ruby | 5 | 6.3 | Done | Done | Completed
2 | 15-12-2017 | In test master one more value of no limit will be added with numeric and alpha numeric | 23 | 2018-02-08 | 2018-02-08 | Ruby | 5 | 5 | Done
2 | 2018-01-01 | Software Updation | 24 | 2018-02-01 | 2018-02-01 | Praveen Singh | 1 | 1 | Done
3 | 2018-01-01 | MIS Report: Data validation of Booking Detail Report |  | 2018-01-01 | 2018-01-01 | Praveen Singh | 4 | 4 | Done
2 | 2018-04-01 | Software Updation | 24 | 2018-01-04 | 2018-01-04 | Praveen Singh | 2 | 2 | Done
3 | 2018-04-01 | 1)In every window, we should have option(buttons) to fetch the detail(sample pendency) expected due date wise till date 2)The listing will be parameter wise as well as sample wise. 3)In analyst window we should have print button so that analyst will take the print out of its pendency its own. 4)In scheduling sheet of analyst we should have coloum of priority. | 1 | 2018-01-11 | 2018-01-11 | Ruby | 16 | 16 | Done |  | Print button on analyst window is not updated. Rest points are completed.
6 | 2018-04-01 | In the window of reviewer, testing completed date & time should be displayed to track the reviewing pendency.Also pendency count according to roles in the header tab. | 2 | 2018-01-09 | 2018-01-09 | Praveen Singh | 8 | 8 | Done | Done | Completed
7 | 2018-04-01 | At the reviewing level reviewer needs a remark box to add the reason of delaying in reviewing. |  |  |  |  | 5
8 | 2018-04-01 | At the analyst level ,if a paramter reverts back to the analyst by the reviewer ,analyst needs the remark box to add reason of change. |  |  |  |  | 5
9 | 2018-04-01 | Multiple mail id's for a particular customer to be used as 'cc' in auto emailing of reports & invoices. | 4 | 2018-01-10 | 2018-01-10 | Praveen+Ruby(2.30 + 12) | 16 | 14.3 | Done | Under Testing
10 | 2018-04-01 | Clubbing of test report in one mail :- All the reports pending for email will be clubbed and send to the customer by the system itself in a single mail as an attachment at predefined time or on click of a particular button. |  |  |  |  | 16
11 | 2017-04-01 | All the MIS reports will be generated department wise(Food,Pharma,Environment) & Division wise(Panchkula,Chennai).And Option for All in Department and Location | 13 | 2018-01-24 | 2018-01-24 | Praveen Singh | 16 | 16 | Done
12 | 2017-04-01 | Export to Excel on listed master form to export master data at Administrator level: 1.Customer Master with all Columns, 2.Parameter Master along with Category and Equipment and 3.Product Test Master:One-by-one and All | 18 | 2018-01-30 |  | Ruby | 16
14 | 2017-04-01 | The status of draft report will be stored in system and will be displayed in TAT report. Draft report will not have any header,footer and signature.Only Label Draft Report will be specified on the top of report. | 3 | 2018-01-12 | 2018-01-12 | Praveen Singh | 6 | 6 | Done with one day delay due to Other Task Pendency | Completed
2 | 2018-06-01 | Software Updation | 24 | 2018-01-06 | 2018-01-06 | Praveen Singh | 1.5 | 1.5 | Done
2 | 2018-09-01 | Software Updation | 24 | 2018-01-09 | 2018-01-09 | Praveen Singh | 2 | 2 | Done
15 | 2018-12-01 | In Booking options for interlaboratory,Compensatory samples and Retestingand invoices for these samples will not be generated and don't considered in invoicing pendency. | 14 | 2018-01-20 | 2018-01-20 | Ruby | 10 | 10 | Done
16 | 2018-12-01 | Purchase order wise invoicing.Option to generate invoice for single PO and multiples PO in a single invoice.Changes on Order Form: Billing Type : Addition of New Billing Type : PO-Wise Addition of New fields : PO-Number(po_no),PO-Date(po_date) Changes on Generate Invoice Form: Po-wise->All PO-Wise Customer(All pending) -> Checkbox - all PO's(All PO pending for Invoices) On checking Po-Checkbox,all orders of selected PO's will be displagting for Invoice Generation.And orders of selected po's will be merged in one invoice. i.e. Invoice generation will be just like Daily Invoicing. Changes on Invoice PDF: Listing of all Samples according to PO just like Category-Subcategory. | 15 | 2018-01-25 | 2018-01-25 | Ruby | 20 | 20 | Done
17 | 2018-12-01 | In Booking, priority there should one option of On Hold having one text box to specify reson of hold.Hold samples will not be scheduled and information should be shared with client with reason of hold.User should have option to change the status from Hold to unhold and after that the expected due date of that sample will be calculated according to the unhold date. | 9 | 2018-01-15 | 2018-01-15 | Ruby | 12 | 12 | Done
2 | 2018-10-01 | Software Updation | 24 | 2018-01-10 | 2018-01-10 | Praveen Singh | 2 | 2 | Done
18 | 2018-12-01 | In scheduling the machine wise efficency and pendency will be displayed to the scheduler to decide the expected due date of sample. | 7 | 2018-01-11 | 2018-01-11 | Ruby | 6 | 6 | Done | Not Uploaded Yet
19 | 2018-12-01 | When the analyst enters the result in the system ,the reports will be reviewed by section incharge first,then the reports will be shifted to reviewer for reviewing. | 8 |  |  |  | Discussion required
20 | 2018-12-01 | Format of Job Order, Two job orders will be generated at the time of booking,one with client information and another without client information. with sample. Job order with client information will be retained by booking user and without client information will be sent to the lab | 6 | 2018-01-15 | 2018-01-15 | Praveen Singh | 20 | 20 | Done | Not Uploaded Yet
21 | 2018-12-01 | Export to PDF button on tester,invoicer & dispatcher window to export pendency to the PDF | 10 | 2018-01-16 | 2018-01-17 | Praveen Singh | 8 | 8 | Done
22 | 2018-12-01 | TAT Report show 'P' in place of ' ' | 12 | 2018-01-17 | 2018-01-17 | Praveen Singh | 4 | 4 | Done
2 | 15-01-2018 | Software Updation | 24 | 2018-01-15 | 2018-01-15 | Praveen Singh | 2 | 2 | Done
23 | 16-01-2018 | Validation of GST No. For individual user and govt. clients we don't have GST No. In that case nothing will be displayed in Invoice and should have option in customer master to add this. | 16 | 2018-01-17 | 2018-01-19 | Ruby | 6 | 6 | Done
24 | 16-01-2018 | Cancellation of previous invoices and provision to regenrate it in current date with current invoice no. | 17 |  |  | Praveen Singh | 16
26 | 16-01-02018 | MIS Report[Sales Report] :- Report to generate revenue category & subcategory wise.(Date wise& Month Wise & Year Wise). The fields in the report are as follows := Department Name,Branch,Date,Month,Year,Customer Name,Location Name,Sales Executive Name,Category Name,Sub Category Name,Product Name,Manufactured By,Supplied By,Revenue(Invoicing Amount excluding Tax).Search Criteria : From Date & To Date | 11 | 2018-01-20 | 2018-01-20 | Praveen Singh | 24 | 20 | Done
27 | 18-01-2018 | User Wise Performance Detail | [6 empty] | Moved to April Task
28 | 18-01-2018 | Eqipment Sorting and Instrument Wise Performance Detail | 19 | 2018-01-31 |  | Praveen Singh | 20 |  | Moved to April Task
29 | 25-01-2018 | Report Amendment at Reviewing Stage
30 | 25-01-2018 | Invoice Cancellationa and Regeneration
30 | 25-01-2018 | MDI Reports given by Mr.Mutul
31 | 31-01-2018 | Creation Of Pharma Master for Staging Server | 20 | 2018-01-01 | 2018-01-01 | Pratyush | 9 | 9 | Done
INDEX
Completed
Working
Discussion Required
Hold

## Jan-2020
ITC ERP TASK DETAIL(Jan-2020)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2020-01-06 | Regarding Points to be clear : Client Feedback Points | 1 | 2020-01-06 | 2020-01-09 | 2020-01-09 | Praveen Singh | 3 | Done
2 | 2020-01-15 | Software Updation | 2 | 2020-01-15 | 2020-01-15 | 2020-01-15 | Praveen Singh | 1 | Done
3 | 2020-01-03 | Sales Report Detail- To be considered on priority | 3 | 2020-01-15 | 2020-01-28 | 2020-01-28 | Praveen Singh | 15 | Done
4 | 2020-01-27 | Regarding Chennai report formats to be incorporated in LIMS : | 4 | 2020-01-27 | 2020-01-31 | 2020-01-31 | Praveen Singh | 9 | Done
5 | 2020-01-27 | Please change approval date to 25.01.2020 from 27.01.2020(QH) | 5 | 2020-01-29 | 2020-01-29 | 2020-01-29 | Praveen Singh | 1 | Done
6 | 2020-01-28 | Rest of the invoices(QH) | 6 | 2020-01-29 | 2020-01-29 | 2020-01-29 | Praveen Singh | 1 | Done
7 | 2020-01-31 | Chand Sir | 7 | 2020-01-31 |  |  | Chand Sir | 4 | Done
[7 empty] | Total | 34
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs