## Oct-2020
S.No. | Task Name | Priority | Estimated Hours | Status
1 | Implementation of Financial Year: Creation of Financial Year Master Adding of New col in Invoice Master table and applying of logic for updation of Financial Year at the time of Invoive Generation Updation of Finacial Year data in all generated invoices | 1 | 18 | Done
2 | Incorporation of Column in Sales Report Detail: Invoicing Customer Code Invoicing Customer State | 2 | 2 | Done
3 | Incorporation of Column in Account Sales Detail Billing Month Financial Year | 3 | 3 | Done
4 | Changes required in Employee Sales Target Report.Values should be displayed date wise in place of MTD Wise.- will discuss as per your ease |  |  | Moved to Next month
5 | APEDA Format-Debugging | 4 |  | Moved to Next month
6 | Query Hours- 12.10.2020[Removal of Tax Slab-F02-2009290625,F02-2009290624,F02-2009290623,F02-2009290622,F02-2009290621,F02-2009290620,F02-2009290619,F02-2009290618,F02-2009290617,F02-2009280609,F02-2009280608,F02-2009280607,F02-2009280606,F02-2009280605,F02-2009280604,F02-2009280603,F02-2009280602,F02-2009280601,F02-2009280600] | 5 | 2 | Done
7 | EIC Format :- New Changes: a)Add one more column of "Validation Protocol" on Product Test Form whose value will be defined parameter wise at the time of master creation and display that variable under Validation Protocol in EIC report" b)Reanaming of two variables: Nature of sample - Type & Nature of Product(First page) LOQ/CCA/acc as applicable - Limit of Determination CC(symbol of alpha )/LOQ as applicable c)Disclaimer value in EIC format wil be fixed as per the user requirement and will not come from Standard master table. - will provide soon | 6 | 8 | Done
8 | Changes on Chennai Report Format:- i)Completed on:- will be the date when analyst has updated result of last parameter of particular sample. ii)Date of Report :- will be the date when report is finalized by Technical Manager iii)Incorporate one more signature of Microbiologist in Chennai report(same of Panchkula report format) as presently we have only two signatures. | 7 | 12 | Done