## Dec-2021
S.No. | Date | Detail | Priority | Estimated Hours | Status | Comment
1 | 2021-12-14 | Colour provision to highlight order having no test request form updated in Sales -Orders Dashboard | 4 | 5 | Done
2 | 2021-12-14 | Colour provision to highlight 'Account Unhold' samples in 'Scheduler' screen for the scheduling purpose. | 7 | 18 | Done
Points:
Master window for listing of all Account Hold Orders
Refreshing of list upon scheduling the Account Hold Orders
3 | 2021-12-14 | Issue in circulation of of Scheduled TAT ,Order Confirmation mail | 2 | 16 | Done | This hours may vary as it is still in progress
4 | 2021-12-14 | Issue in sharing of test reports & Invoices manually on the click of Check box. | 1 | 16
5 | 2021-12-14 | Provision to incorporate 'Sample Checklist' template in LIMS during 'Sample Receiving' stage. |  | 95
Points:This will be required in chennai only
Sample Receving Window:
Sample Receiving window like order booking
HTML Design of Check list form for add/edit
New check list form add/edit with sample reciving form.This for will ne added in same sample receiving form
Order Booking Listing:
Download of above form IN PDF format.This button will be on listing page
PDF Template Design
Provision to upload Image of sample in 'Order Booking'
Points:This will be required in chennai only
Multiple any file upload on add/edit sample Receiving window -
6 | 2021-12-14 | F01-2111130341 & F01-2111130341 - Group & Discipline Issue | 3 | 2 | Done
7 | 2021-12-22 | Uploading of sales excecutive name in customer master using CSV - CUSTOMERCODE,SALESEXECODE | 8 | 8 | Done
8 | 2021-12-22 | Option Of Multiple bank Account for Invoice generation |  | 55
Points:
Bank Master
Linking of Bank master with Customer
Option for setting default bank Account
Displaying of this bank detail on Invoice PDF and Software view.If no bank account added here, then system will select default as current system
9 | 2021-12-22 | Displaying of Batch No. on Sales->Report window for all roles and Mail Status Column on Report Window(Report) and Invoice Invoice Window(Invoice) | 5 | 6 | Done
10 | 2021-12-22 | Displaying of Invoicing Customer - Contact Person name,Contact Person Email and Mobile on clicking the customer column on Sales->Invoice Listing | 6 | 4 | Done
11 | 2021-12-22 | Provision for entering the tax percentage in customer master and based on this percentage, generation of invoice |  |  |  | Confirmation provided by Client