## Oct2021
S.No. | Date | Detail | Priority | Estimated Hours | Status | Comment
1 | 2021-09-04 | Back date provision in 'Others' department of Chennai branch | 5 | 5 | Done
2 | 2021-05-03 | New Format of Cosmetics | 6 | 20
3 | 2021-09-04 | QR code in test reports | 7
4 | 2021-09-04 | Uploading of ITC rate list from back end in 'Parameter' master & 'Product Tests' master for Food & Pharma |  | 9 0f 25 | Done | Completed for Cosmetics and Ayurveda Department.Remaining for other department
5 | 2021-09-04 | Nabl New Logo Implementation in Test Report. | 1 | 16 | Done
6 | 2021-10-11 | Change in provison of Authorised signatory in Food-Panchkula report template | 2 | 36 | Done
Presently -Three signatures are coming as brief below:-
First Signature - Microbiologist
Second Signature - Reviewer
Third Signature - Authorised Signatory
Changes Required-
First Signature - Replace label 'Authorized Signatory'- to 'Authorized Signatory- Biological'
Second Signature -(a) Replace Label 'Reviewer' with'Authorized Signatory-Residue in Food'
(b) Signature of section incharge of HPLC,LCMSMS,GCMSMS will come here when report will be approved by section incharge.
© Signature come if parameters of relevant instrument is available as same as Microbiological.
Third Signatue- No change
Points:
1.Creation of New Master 'Report Signatures'.
2.Logic Creation for Saving of Authorized Sign in the db table ‘order_report_middle_authorized_sign_dtl’ based on equipment selected in above table.
3.Implementing middle authorized sign in the PDF Report of Panchkula Food Report.
4.Implementing middle authorized sign in the Software View of Panchkula Food Order Process Stage.
7 | 2021-10-11 | Provision to add detector name,column name, running time & no. of injections in Analyst role for HPLC,LCMSMS,GCMSMS equipment while entering the result.The details of variables are as follows:- | 3 | 60 | Done
Detector name - Linked with equipment name . Standard list will be provided .
Column Name - Linked with equipment name. Master form will be created.
Running time - Value entered by user.
No. of Injections- Value entered by user.
Instance Name
Points:
1.Creation of Column Name Mater
2.Creation of Instance Name Master
3.Conditional based Analyst Window Design/Development
4.Change on Generate Invoice Window
8 | 2021-10-11 | Time line for the API discussed. Details are already shared in mail.
9 | 2021-10-11 | Format of Pesticide Residue -Apeda available in Food Chennai to be cloned in Pharma-Chennai | 4 | 16 | Done
Points:
1.New PDF report implemenation for Pharma Chennai
2.Checkbox Option in Generate window popup in case of Pharma Chennai