## May-2021
S.No. | Date | Detail | Priority | Estimated Hours | Status
1 | 2021-04-16 | PDF Report : Border issue of Discipline Wise PDF Report in Chennai Branch | 1 | 5 | Done
2 | 2021-04-16 | Credit Approval Process - The details are as below:- (a) One check box of "Credit Approval" will be provided on order booking form.(On Add and Edit Form) "(b) One selection of Check box , one pop up will be opened having values Approved by(Name),date(Date),Credit Period(No of days),date upto amount(date) will be received .On Editing , user can only edit the field and not able to remove the checkbox, and it will be done admin, order booker can only view it. to be entered by order booker.(All field are required)" c) The new customers having "Credit Approval" check box selected will not put on hold and proceed for further stages. d) MIS-Report : Branch,Department,Customer Name,Customer Code, City,Order No,Order Date,Form Detail | 3 | 32 | Done
3 | 2021-04-16 | Account hold for Existing Customers :- Step1:- Provision to upload excel having values of outstanding amount & > 90 outstanding amount Customer name,city wise on daily basis Step 2:- On every upload previous data will be replaced by new updated data. Step 3:- At the time of order booking as like new customer software will check the details of Outstanding amount for existing customers Step 4:- If customer is existing customer having outstanding value but there is no outstanding >90 days then customer will not put on hold & proceed for further stages. Step 5:- If customer is existing customer having outstanding value & also outstanding >90 days then customer will put on hold. Step 6:- Existing customer put "on Hold" will be displyed in CRM role under new tab of "Hold & UnHold Customer" tab only to those users to whom rights are given by Administrator in Employee master form as discussed. Step 7:- User will check the payment status and "Unhold" customer. Step 8 :- Provision of auto email to the user on click of Check box for "Hold" customer. Step 9:- Mail part given for existing customer hold will be different for new customer hold. Step10 :- Alert on user dashboard regarding the "hold" customers Step 11:- Maintain the category of "New " & "Existing" customer for the clarity of the user. |  | Not Yet Discussed
4 | 2021-04-16 | Form 39 & Form 39 A:- (a) Form 39 A is same as that of Form 39 only the difference of character"A". (b) Software has to decide which format will be shared with customer depending upon the value selected in customer master c) Format to be selected is totally dependent upon Customer type defined in the customer master. |  | Not Yet Discussed
5 | 2021-05-03 | Incorporate provision of Discipline & Group in Panchkula report format of Food & Environment.(In 3 PDF Blades) | 2 | 24 | Done
6 | 2021-05-03 | New Format of Cosmetics |  | Not Yet Discussed
7 | 2021-05-03 | Emailing for hold customers :- To - mail of customer CC- mail of person unholding the customer, Mail id of CRM & Sales Executives (Email Id of CRM will be selected Branch & Department wise) 1.Master - branch,Department,CRM Name,CRM Email, Status 2.Include email of added CRM User while sending the mail of hold to the customer.Manually email to customer on selecting the checknox window on CRM Window | 4 | 10 | Done