## Apr-2019
ITC ERP TASK DETAIL(Apr-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-04-03 | Remove columns Storage name and merge its value with storage condition. In product name please write sample name in place of test master name: Changes on Manual notification to the customer:- a)Remove columns Storage name and merge its value with storage condition. b)In product name please write sample name in place of test master name. c)Testing of above changes on Drish Staging Server(itc.drishinfo.com). | 1 | 2019-04-03 | 2019-04-03 | 2019-04-03 | Praveen Singh(QH) | 2 | 2 | Done
2 | 2019-04-08 | In TAT Report of MIS,after reverting any report the below should be empty: -Reviewing, -Finalizing, -Approving, -Dispatching. [ Client-word : As discussed telephonically please check the issue, when we reverting any report from any stage(invoicing,dispatching,dispatched) after approving of report then report status column in TAT report should be blank and value in all the columns(reviewing, approving,dispatching)should be blank. ] | 2 | 2019-04-08 | 2019-04-08 | 2019-04-08 | Praveen Singh(QH) | 1 | 1 | Done
3 | 2019-04-09 | Integration of back-date booking in Stability Module while converting the Stability Order to Order with listed conditional logic: If there is a admin login,then admin can select the date from date-picker and by default current date will be display. If there is a Order Booker Login,then by default only current date will be display with no date-picker option. [Client-word : As per our discussion please open back date booking for stability samples in administrator login.] | 3 | 2019-04-09 | 2019-04-09 | 2019-04-09 | Praveen Singh(QH) | 1 | 1 | Done
4 | 2019-04-09 | On PDF Generation of all Report at once in Invoice Section: On clicking the 'Generate Report' button,a popup window will open. And a popup window will have listed option: Reports without Report-To Option with Generate Button Report with Report-To Option with Generate Button 3.On Clicking the Generate button, the separate PDF will be Generated. | 4 | 2019-04-09 | 2019-04-09 | 2019-04-09 | Ruby(QH) | 2 | 3 | Done
5 | 2019-04-09 | Automation of Orders,Order Status,Reports,Invoices of Web Module | 5 | 2019-04-09 | 2019-04-22 | 2019-04-22 | Praveen Singh | 50 | 48 | Done
6 | 2019-04-11 | Documentation : Quotation/PI Module Process Flow: | 6 | 2019-04-11 | 2019-04-16 | 2019-04-16 | Praveen Singh | 16 | 12 | Done
7 | 2019-04-16 | 1)TAT-Report : Incorporation of instrument name in TAT Report 2)Expected Due Date Calculation : Please update cut off time as 4:30 in place of .01:30 in the calculation of expected due date. | 7 | 2019-04-16 | 2019-04-16 | 2019-04-16 | Praveen Singh(QH) | 1 | 1 | Done
8 | 2019-04-17 | Software Updation | 8 | 2019-04-17 | 2019-04-17 | 2019-04-17 | Praveen Singh(QH) | 1 | 1 | Done
9 | 2019-04-18 | Multiple time option to enter dispatching detail for reports & invoices | 9 | 2019-04-18 | 2019-04-18 | 2019-04-18 | Praveen Singh | 7 | 9 | Done
10 | 2019-04-24 | ITC Web Module : Regarding Automation of Orders,Order Status,Reports,Invoices : Revised List : Changes : | 10 | 2019-04-24 | 2019-04-30 | 2019-04-30 | Praveen Singh | 32 | 34 | Done
[7 empty] | Total | 113 | 112