## Aug-2019
ITC ERP TASK DETAIL(Aug-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-08-01 | Scheduled MIS-TAT : Changes : | 1 | 2019-08-01 | 2019-08-07 | 2019-08-07 | Praveen Singh | 14 | 14 | Done
2 | 2019-08-02 | Regarding Customer master with executive names | 2 | 2019-08-02 | 2019-08-02 | 2019-08-02 | Praveen Singh | 1 | 1 | Done
3 | 2019-08-07 | Food Report Format for "Others" in Panchkula | 3 | 2019-08-07 | 2019-08-08 | 2019-08-08 | Praveen Singh | 5 | 5 | Done
4 | 2019-08-07 | Stability Module Formats for DSM(HTML Design) | 4 | 2019-08-08 | 2019-08-09 | 2019-08-09 | Praveen Singh | 16 | 16 | Done
5 | 2019-08-09 | Stability Module Formats for DSM : Changes : | 5 | 2019-08-09 | 2019-08-22 | 2019-08-22 | Praveen Singh | 26 | 26 | Done
6 | 2019-08-20 | QH-Regarding Query Hour- 20.08.2019 | 6 | 2019-08-20 | 2019-08-20 | 2019-08-20 | Praveen Singh | 1 | 1 | Done
7 | 2019-08-22 | Regarding correction of Sales Executive Name Linking in MIS | 7 | 2019-08-22 | 2019-08-31 | 2019-08-31 | Praveen Singh | 28 | 28 | Done
8 | 2019-08-30 | QH-Regarding Query Hour- 30-Aug-2019 : Saving of Booking Sample Amount at the time of Booking an Order: | 8 | 2019-08-30 | 2019-08-30 | 2019-08-30 | Praveen Singh | 2 | 2 | Done
[7 empty] | TOTAL | 93 | 93
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs