## Aug-2018
ITC ERP TASK DETAIL(Aug-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-08-04 | A)Client feedback Points: 1)In (1) Order Cancellation task:Updated the records of all cancelled orders in newly created table `order_cancellation_dtls`. 2)In (8) MIS Reports-(b) Amended Reports Task:Updated the records of all amended orders in newly created table `order_amended_dtl`. 3)Approved date is showing as 01.01.1970-I. 4)Approved date is showing as 01.01.1970-II. 5)Allowing user to accept dash if po-number is not available. | 1 | 2018-08-04 | 2018-08-04 | 2018-08-04 | Praveen Singh | 8 | 8 | Done
2 | 2018-08-06 | 1)Order Form : Editing of Customer Detail Section: a)Billing Type b)Invoicing Type c)Discount Type d)Discount Value 2)Please change approval name to Indra Rai.Order No.'s are: a)F01-1807110692 b)F01-1807110696 c)F01-1807140849 d)F01-1807130794 3)In below report microbiologist will be Parkash Kaur in place of Udayveer: a)F01-1806281522 | 2 | 2018-08-06 | 2018-08-06 | 2018-08-06 | Praveen Singh | 8 | 8 | Done
3 | 2018-08-09 | Software Update on ITC Live/Staging Server | 3 | 2018-08-09 | 2018-08-09 | 2018-08-09 | Praveen Singh | 2 | 2 | Done
4 | 2018-08-10 | Client feedback Points: 1.Invoice wise report printing-without Header and Footer. 2.Andra/Telangana Invoice Format-Label of ServiceTax will be service Amount. 3.Sales Report by accounts for reconciliation of invoices Mis-Report:Account Sales Detail-GST,Payable Amount Rounding. 4.Tree view of the fixed rate Customer. 5)Testing of Order Editing Modules: a)Order Booking Form : Changes in displaying of Invoicing,Billing,Discount Type Selectbox in case of following: Case I: If invoicing of any order is not completed,then all options of Invoicing,Billing,Discount Type will be displayed. Case II: If invoicing of any order is completed,then only selected options of Invoicing,Billing,Discount Type will be displayed. b)Order Booking Form :Changes on displaying of Parameter Rate in listed cases: Case I : If User changes the Customer Detail by selecting it from Customer Selectbox while editing. Case II : If User changes the Invoicing Detail by selecting it from Invoicing Type Selectbox while editing. 6)Tested the Order Confirmation Mail using Cron Job on ITC Live Server. | 4 | 2018-08-10 | 2018-08-10 | 2018-08-10 | Praveen Singh | 9 | 9 | Done
5 | 2018-08-13 | Client feedback Points:Points available in Documents: 1.Order Booking : Tree View for fixed Rate Customers. 2.Environment Report:Table border of Test Report. 3.Invoice : Insertion of Dispatched Detail data of all department in the Invoice Dispatch Detail Table. 4.Amendment Report : Insertion of Amended Report data in the order Detail Amended Table. 5.Order Cancellation: Insertion of Cancelled Report data in the order Cancellation Detail Table. 6.Chennai Test Report Format: a)Received On : Order Booking Date b)Commenced On : First Parameter scheduled date of an order. c)Best Before End : Remove this Line d)Customer Reference No : Ref. No./Ref. Date e)Unit Column: Remove this Column 7.Customer Master : Export to Excel data is not showing all columns of Customer Master Table. 8.MIS-Report / Delay Status Report:Don't Include Interlaboratory/Compensatory Order in count. | 5 | 2018-08-13 | 2018-08-13 | 2018-08-13 | Praveen Singh | 9 | 9 | Done
6 | 2018-08-14 | A)Client feedback Points: 1.New bill format of Andhra/Telangana: Changes Discussed with Client: On Invoice Generate Criteria Popup: a)Implement a checkbox with label 'State-Wise'. b)If User Select the Checkbox,then system will generate the State-Wise Invoice Templete, c)And If User uncheck the Checkbox,then system will generate Normal Invoice Templete. On Invoice Listing Page: a)Implement a Popup with Button 'Normal'/'State-Wise which will prompt upon clicking the button View Invoice. b)If User Select the 'Normal' button,then system will generate Normal Invoice Templete, c)And If User Select the 'State-Wise' button,then system will generate State-Wise Invoice Templete. 2.Implemented the Email Templete of Water Department regarding Listed Section: a)Order Booking Confirmation, b)Reports and b)Invoices 3.Uploaded the Email Templete of Water Department regarding Listed Section: a)Order Booking Confirmation, b)Reports and b)Invoices | 6 | 2018-08-14 | 2018-08-14 | 2018-08-14 | Praveen Singh | 6 | 6 | Done
7 | 2018-08-11 | POINT-3-Provision of Section Incharge for reviewing of report: (a)Common instrument for multiple section incharges:- Challenge:- In this case the parameter of common instrument will be displayed on the window of both section incharges and it will not be shifted into reviewing stage until it is not reviewed by both section incharges Solution :- if one incharge approve parameter of common instrument then it will be by default remove from other incharge end. (b)Pendency of reports will be role wise not user name wise :- Challenge :- If after adding the result of some parameters we changed the role of section incharge from one user to another user then system will not displayed all the pending reports of section incharge to the new use. Solution:- Righrts will be role wise not the user name wise. (c)Stage of sample :- Challenge:- Stage of sample shifted to section incharge after the complete testing of all parameters of sample Solution :- If testing of parameters of one section is completed then it will be shifted to section incharge irrespective of the status of parameters of other sections in the same sample | 7 | 2018-08-16 | 2018-08-21 | 2018-08-21 | Praveen Singh | 24 | 24 | Done
8 | 2018-08-20 | Implementation of Template Design and Testing of Order Process Stage for New Department Water: a)Testing Stage. b)Section-Incharge Stage. c)Reviewing Stage. d)Finalizing Stage. e)Approving Stage. f)Invoicing g)Dispatching h)Dispatched | 8 | 2018-08-21 | 2018-08-22 | 2018-08-22 | Praveen Singh | 12 | 12 | Done
9 | 2018-08-23 | Software Update on ITC Live Server for listed task: 1)POINT-3-Provision of Section Incharge for reviewing of report: 2)Implementation of Template Design for New Department 'Water'. | 9 | 2018-08-23 | 2018-08-23 | 2018-08-23 | Praveen Singh | 1 | 1 | Done
10 | 2018-08-27 | Editing of listed two parameter by the Reviewer in all departments: 1)Description Parameter: i)Food ii)Environment iii)Building iv)Water v)Textile vi)Helmet vii)Ayurvedic viii)Pharma 2)Reference to protocol parameter: i)Pharma | 10 | 2018-08-27 | 2018-08-27 | 2018-08-27 | Ruby | 8 | 8 | Done
11 | 2018-08-28 | A)Client Feedback Points: 1.Resolved (please add general information) 2.Submitted sample is optional and is not applicable for all.Please remove 3.Part D has been mentioned which is not required 4.Please remove, only remarks would be enough 5.Instead of Other details , please change it to :Sample Submission type 6.Options to be added are:- Submitted and -Sampled by Lab Rep. 7.Also environment reports are generated in 2 different formats, please take a note of it and do the needful. (for e.g. E02-1807300234 & E02-18073002120 are in two different formats) will be rectified by you. 8.Issued to client Name.Not required in all pages, only to be mentioned in first page. 9.Can we enable this button on user end(in point 2). Please open on user end. 10.Provide provision of cancellation & regeneration of invoices button on invoicer end. | 11 | 2018-08-28 | 2018-08-28 | 2018-08-28 | Praveen Singh | 3 | 3 | Done