## Aug-2018
ITC ERP TASK DETAIL(Aug-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-08-04 | A)Client feedback Points: 1)In (1) Order Cancellation task:Updated the records of all cancelled orders in newly created table `order_cancellation_dtls`. 2)In (8) MIS Reports-(b) Amended Reports Task:Updated the records of all amended orders in newly created table `order_amended_dtl`. 3)Approved date is showing as 01.01.1970-I. 4)Approved date is showing as 01.01.1970-II. 5)Allowing user to accept dash if po-number is not available. | 1 | 2018-08-04 | 2018-08-04 | 2018-08-04 | Praveen Singh | 8 | 8 | Done
2 | 2018-08-06 | 1)Order Form : Editing of Customer Detail Section: a)Billing Type b)Invoicing Type c)Discount Type d)Discount Value 2)Please change approval name to Indra Rai.Order No.'s are: a)F01-1807110692 b)F01-1807110696 c)F01-1807140849 d)F01-1807130794 3)In below report microbiologist will be Parkash Kaur in place of Udayveer: a)F01-1806281522 | 2 | 2018-08-06 | 2018-08-06 | 2018-08-06 | Praveen Singh | 8 | 8 | Done
3 | 2018-08-09 | Software Update on ITC Live/Staging Server | 3 | 2018-08-09 | 2018-08-09 | 2018-08-09 | Praveen Singh | 2 | 2 | Done
4 | 2018-08-10 | Client feedback Points: 1.Invoice wise report printing-without Header and Footer. 2.Andra/Telangana Invoice Format-Label of ServiceTax will be service Amount. 3.Sales Report by accounts for reconciliation of invoices Mis-Report:Account Sales Detail-GST,Payable Amount Rounding. 4.Tree view of the fixed rate Customer. 5)Testing of Order Editing Modules: a)Order Booking Form : Changes in displaying of Invoicing,Billing,Discount Type Selectbox in case of following: Case I: If invoicing of any order is not completed,then all options of Invoicing,Billing,Discount Type will be displayed. Case II: If invoicing of any order is completed,then only selected options of Invoicing,Billing,Discount Type will be displayed. b)Order Booking Form :Changes on displaying of Parameter Rate in listed cases: Case I : If User changes the Customer Detail by selecting it from Customer Selectbox while editing. Case II : If User changes the Invoicing Detail by selecting it from Invoicing Type Selectbox while editing. 6)Tested the Order Confirmation Mail using Cron Job on ITC Live Server. | 4 | 2018-08-10 | 2018-08-10 | 2018-08-10 | Praveen Singh | 9 | 9 | Done
5 | 2018-08-13 | Client feedback Points:Points available in Documents: 1.Order Booking : Tree View for fixed Rate Customers. 2.Environment Report:Table border of Test Report. 3.Invoice : Insertion of Dispatched Detail data of all department in the Invoice Dispatch Detail Table. 4.Amendment Report : Insertion of Amended Report data in the order Detail Amended Table. 5.Order Cancellation: Insertion of Cancelled Report data in the order Cancellation Detail Table. 6.Chennai Test Report Format: a)Received On : Order Booking Date b)Commenced On : First Parameter scheduled date of an order. c)Best Before End : Remove this Line d)Customer Reference No : Ref. No./Ref. Date e)Unit Column: Remove this Column 7.Customer Master : Export to Excel data is not showing all columns of Customer Master Table. 8.MIS-Report / Delay Status Report:Don't Include Interlaboratory/Compensatory Order in count. | 5 | 2018-08-13 | 2018-08-13 | 2018-08-13 | Praveen Singh | 9 | 9 | Done
6 | 2018-08-14 | A)Client feedback Points: 1.New bill format of Andhra/Telangana: Changes Discussed with Client: On Invoice Generate Criteria Popup: a)Implement a checkbox with label 'State-Wise'. b)If User Select the Checkbox,then system will generate the State-Wise Invoice Templete, c)And If User uncheck the Checkbox,then system will generate Normal Invoice Templete. On Invoice Listing Page: a)Implement a Popup with Button 'Normal'/'State-Wise which will prompt upon clicking the button View Invoice. b)If User Select the 'Normal' button,then system will generate Normal Invoice Templete, c)And If User Select the 'State-Wise' button,then system will generate State-Wise Invoice Templete. 2.Implemented the Email Templete of Water Department regarding Listed Section: a)Order Booking Confirmation, b)Reports and b)Invoices 3.Uploaded the Email Templete of Water Department regarding Listed Section: a)Order Booking Confirmation, b)Reports and b)Invoices | 6 | 2018-08-14 | 2018-08-14 | 2018-08-14 | Praveen Singh | 6 | 6 | Done
7 | 2018-08-11 | POINT-3-Provision of Section Incharge for reviewing of report: (a)Common instrument for multiple section incharges:- Challenge:- In this case the parameter of common instrument will be displayed on the window of both section incharges and it will not be shifted into reviewing stage until it is not reviewed by both section incharges Solution :- if one incharge approve parameter of common instrument then it will be by default remove from other incharge end. (b)Pendency of reports will be role wise not user name wise :- Challenge :- If after adding the result of some parameters we changed the role of section incharge from one user to another user then system will not displayed all the pending reports of section incharge to the new use. Solution:- Righrts will be role wise not the user name wise. (c)Stage of sample :- Challenge:- Stage of sample shifted to section incharge after the complete testing of all parameters of sample Solution :- If testing of parameters of one section is completed then it will be shifted to section incharge irrespective of the status of parameters of other sections in the same sample | 7 | 2018-08-16 | 2018-08-21 | 2018-08-21 | Praveen Singh | 24 | 24 | Done
8 | 2018-08-20 | Implementation of Template Design and Testing of Order Process Stage for New Department Water: a)Testing Stage. b)Section-Incharge Stage. c)Reviewing Stage. d)Finalizing Stage. e)Approving Stage. f)Invoicing g)Dispatching h)Dispatched | 8 | 2018-08-21 | 2018-08-22 | 2018-08-22 | Praveen Singh | 12 | 12 | Done
9 | 2018-08-23 | Software Update on ITC Live Server for listed task: 1)POINT-3-Provision of Section Incharge for reviewing of report: 2)Implementation of Template Design for New Department 'Water'. | 9 | 2018-08-23 | 2018-08-23 | 2018-08-23 | Praveen Singh | 1 | 1 | Done
10 | 2018-08-27 | Editing of listed two parameter by the Reviewer in all departments: 1)Description Parameter: i)Food ii)Environment iii)Building iv)Water v)Textile vi)Helmet vii)Ayurvedic viii)Pharma 2)Reference to protocol parameter: i)Pharma | 10 | 2018-08-27 | 2018-08-27 | 2018-08-27 | Ruby | 8 | 8 | Done
11 | 2018-08-28 | A)Client Feedback Points: 1.Resolved (please add general information) 2.Submitted sample is optional and is not applicable for all.Please remove 3.Part D has been mentioned which is not required 4.Please remove, only remarks would be enough 5.Instead of Other details , please change it to :Sample Submission type 6.Options to be added are:- Submitted and -Sampled by Lab Rep. 7.Also environment reports are generated in 2 different formats, please take a note of it and do the needful. (for e.g. E02-1807300234 & E02-18073002120 are in two different formats) will be rectified by you. 8.Issued to client Name.Not required in all pages, only to be mentioned in first page. 9.Can we enable this button on user end(in point 2). Please open on user end. 10.Provide provision of cancellation & regeneration of invoices button on invoicer end. | 11 | 2018-08-28 | 2018-08-28 | 2018-08-28 | Praveen Singh | 3 | 3 | Done

## Sept-2018
ITC ERP TASK DETAIL(Sept-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-09-04 | Implementation of listed validation on Employee Creation Module: 1)Apply validation if any User is removing the Sales Person role. 2)Apply validation if any User assigning the Sales Person Role. | 1 | 2018-09-04 | 2018-09-04 | 2018-09-04 | Ruby | 4 | 4 | Done
2 | 2018-09-04 | Client Feedback Points: (a) To correct previous data in which we don't have status of completed or uncompleted but sample status is dispatched, please correct that data for the accurate value in POP UP REMINDERS. Update date of completion same as reviewing date. Update this only for the correction of previous data not for current data. (b) TAT % - This value will be update everytime according to the value of Total due & Overdue not whole day after 05:00 pm. (c) Scheduling-Jobs :- The data of concerning analyst will be reflected irrespective of all. (d) Implemented a provision for Invoice-generator for viewing the cancelled Invoices on invoice listing Page. (e) Implemented a provision for Invoice-generator for the generation of Debit Note PDF on Debit Notes listing Page. (f) Implemented a provision for Invoice-generator for the generation of Credit Note PDF on Credit Notes listing Page. | 2 | 2018-09-04 | 2018-09-04 | 2018-09-04 | Praveen Singh | 2 | 2 | Done
3 | 2018-08-30 | (A)Creation of NABL Code at the time of approval(QA) by following the listed points: i)1-6 : Integration of Accreditation Cerificate Number according to Branch. ii)7-8 : Integration of financial year(Report Approving Year) like '18' iii)9 : Integration of multilocation code '0' for main location and '1','2','3'.. for sub-location. iv)10-17 : Integration of 8 digit code according to branch wise. v)18 : Integration of 'F'/'P'.F if all Test Parmeter of an order has NABL Scope defined else for mix 'P'. (B)Re-generation of NABL Code at the time of approval(QA) in case of amendment of Report by following the above listed points. | 3 | 2018-08-30 | 2018-09-01 | 2018-09-01 | Praveen Singh | 55 | 52 | Done
4 | 2018-09-01 | NABL Code Generation(NEW MODIFICATION): 1)Keep ninth digit zero. no need ti incorporate department in it. 2)To determine whether parameter is in NABL scope or not :- Only we have to give provision in Product Test to be checked or unchecked by the master creator for NABL & non-NABL scope of a parameter. WORKING FLOW: STEP-1 : 9th digit changes in Accreditation Master Creation. STEP-2 : Implementation of provision in the final test master for defining the parameter within the scope or not at the time of adding parameter in the Test Master Creation. STEP-3 : Implementing the Final Test Master Creation changes and 9th digit changes in NABL Code generation steps. STEP-4 : Rename the label from NABL code to NABL ULR No. in all Test Report Templates of all listed below department both in Software view and PDF view. | 4 | 2018-09-06 | 2018-09-07 | 2018-09-07 | Praveen Singh | 16 | 16 | Done
5 | 2018-09-10 | Implementation of Decimal Place for Test Result for all Department: Test Parameter Changes: i)Adding of decimal place field in Test Parameter Creation. ii)Editing of decimal place field in Test Parameter Creation. iii)Listing of decimal place field in Test Parameter Creation. B)Product Test Master Changes: i)Displaying of decimal place values in decimal value checkbox in Test Master Creation. ii)Adding of decimal place field in Test Master Creation. iii)Editing of decimal place field in Test Master Creation. iv)Listing of decimal place field in Test Master Creation. C)Order Booking Changes: a)Adding: i)Displaying of decimal place values in decimal value in an input box while listing the Test Parameter. ii)Saving of decimal place values in decimal value field in order booking. b)Editing: i)Displaying of saved decimal place values in decimal value in an input box while listing the Test Parameter. ii)Updating of decimal place values in decimal value field in order booking. D)Record updation: i)Updating of Decimal Place value in Order Parameter Detail of all booked Orders by analying the STD Value From and STD Value To | 5 | 2018-09-10 | 2018-09-13 | 2018-09-13 | Praveen Singh | 24 | 24 | Done
6 | 2018-09-13 | Implementation Logic of Department Due Date : STEP 1 : If difference between Expected Due Date and Booking Date is less than equal to 3,then Department Due/Report Due Date will be same as Expected Due Date. STEP 2 : If difference between Expected Due Date and Booking Date is greater than 3,then Department Due/Report Due Date will be one less than Expected Due Date. STEP 3 : If an Order has Microbiological instrument,then CASE 1 and CASE 2 will not be applicable.And Department Due/Report Due Date will be same as Expected Due Date. STEP 4 : If Customer has Customer-wise-tat defined,then Expected Due Date / Department Due / Report Due Date will be directly calculated from TAT Days irrespective of weekly off,sunday & +1 of after 2:00 pm conditions. | 6 | 2018-09-13 | 2018-09-14 | 2018-09-14 | Praveen Singh | 5 | 8 | Done
7 | 2018-09-13 | Implementation of InvoicingTo provision in Invoice Cancellation & Re-Generation: STEP 1 : Changes in Invoice Generation: i)Saving of invoicingTo data in invoice detail at the time of Invoicing Generation if any order has an InvoicingTo data. ii)If InvoicingTo has a data,then displaying of InvoicingTo detail in view of Invoice in Software both in Normal/State-wise. iii)If InvoicingTo has a data,then displaying of InvoicingTo detail in view of Invoice in PDF both in Normal/State-wise. STEP 2 : Changes in Invoice Re-Generation: i)If User changes the InvoicingTo data,then new invoice will be generated according to InvoicingTo data. ii)If Changed InvoicingTo has a data,then displaying of Changed InvoicingTo detail in view of Invoice in Software both in Normal/State-wise. iii)If Changed InvoicingTo has a data,then displaying of Changed InvoicingTo detail in view of Invoice in PDF both in Normal/State-wise. STEP 3 : Changes in Credit/Debit Notes. i)If InvoicingTo has a data,then displaying of InvoicingTo detail in view of Credit/Debit Note in Software. ii)If InvoicingTo has a data,then displaying of InvoicingTo detail in view of Credit/Debit Note in PDF View. STEP 4 : Record Updation: i)Updation of InvoicingTo data in all generated invoices. | 7 | 2018-09-15 | 2018-09-18 | 2018-09-18 | Praveen Singh | 18 | 18 | Done
8 | 2018-09-19 | Process Flow and Estimation for Order Confirmation Template Implementation Task below: STEP-1 : Creation of New Templates for Order Confirmation Mail for listed Departments: i)Food ii)Pharma iii)Ayurvedic iv)Environment v)Water vi)Helmet vii)Building viii)Textile STEP-2 : Integration of New Templates in Order Confirmation Detail(Mail Body) for each departments. Step-3 : Mailing of Order Confirmation with attachment using CRON JOB/Auto Mailing(Mainly involves attachment testing department wise). | 8 | 2018-09-20 | 2018-09-25 | 2018-09-25 | Praveen Singh | 16 | 16 | Done
9 | 2018-09-21 | Client Feedback Points: (a) In Order Booking P01-1808290007 i want to change discount value to No Discount but system is neither changing nor showing any message. (b) same problem i faced in food also. (c) In Customer master when we want to inactive or edit any email id then system is showing email id already exist. (d) In order booking for F01-1808070430 we had defined PO no. & date but at the time of editing of order booking system is showing messasge of "Error! PO No. is required." (e) In any new order booking hold & PO detail is not working simultaneously. | 9 | 2018-09-21 | 2018-09-21 | 2018-09-21 | Praveen Singh | 1 | 1 | Done
10 | 2018-09-24 | Chennai Report Format Changes: STEP 1 : Implementation of Instrument Column in Test Report Format while generation of Test Report both for FOOD & ENV. STEP 2 : Implementation of Instrument Column in Order Confirmation Mail Format while sending a Order Confirmation Mail both for FOOD & ENV. STEP 3 : a)Adding of Remarks(from Order booking form) field in-front of Sample Submission Type and labeling it to 'Sampling Details' in Test Report Format and Order Confirmation Mail Format both for FOOD & ENV. b)'Sampling Details' will be displayed in Test Report only if Sales-Samples is 'Sampled By Lab Rep' otherwise not both in Test Report Format and Order Confirmation Mail Format both for FOOD & ENV. | 10 | 2018-09-26 | 2018-09-27 | 2018-09-27 | Praveen Singh | 6 | 6 | Done
11 | 2018-09-27 | AUTOMATICALLY GENERATION-New Modification in NABL Code generation task below: STEP-1 : Changes On Generation of NABL Code at the time of approval(QA) automatically by the System if any one of the parameter used in report is in NABL scope(F/P) irrespective of Approval has checked the Right Logo checkbox on Generate Report Criteria Popup Window or not. STEP-2 : Changes on 10-17 Code generation due to addition of Prefix 'TC'. STEP-3 : System will not considered standard parameter(like Reference to protocol,Description etc.) in the calculation of "F" & "P". STEP-4 : Displaying of Right Logo checkbox CHECKED on Generate Report Criteria Popup Window if Test report is applicable for Generation of NABL Code.If not,then Right Logo checkbox will not display and user cannot able to generate the Right Logo in Test report as well. STEP-5 : Changing the Label of Right Logo checkbox to NABL Code Applicable on Generate Report Criteria Popup. | 11 | 2018-09-27 | 2018-09-28 | 2018-09-28 | Praveen Singh | 6 | 6 | Done
12 | 2018-09-29 | Uploading of NABL Scope Parameters Status in Product Test Detail On ITC Live Server of listed Departments: i)Food ii)Ayurvedic iii)Building iv)Environment v)Helmet vi)Textile | 12 | 2018-09-29 | 2018-09-29 | 2018-09-29 | Praveen Singh | 4 | 4 | Done