## Feb-2019
ITC ERP TASK DETAIL(Feb-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-01-22 | STABILITY-MODULE : F) PDF Report Format of Stability Modules: | 1 | 2019-01-22 | 2019-02-04 | 2019-02-04 | Praveen Singh | 31 | 23 | Done
2 | 2019-02-16 | STABILITY-MODULE :Software Update | 2 | 2019-02-16 | 2019-02-16 | 2019-02-16 | Praveen Singh | 2 | 2 | Done
3 | 2019-02-22 | STABILITY-MODULE : Please complete the below listed task of stability module:- (a) Remove unique ness of Start Date. (b) Manual notification to the customer. | 3 | 2019-02-25 | 2019-02-27 | 2019-02-27 | Praveen Singh | 8 | 8 | Done
4 | 2019-02-22 | STABILITY-MODULE : Please complete the below listed task of stability module:- (c) Master form to define storage condition. | 4 | 2019-02-25 | 2019-02-25 | 2019-02-25 | Ruby | 3 | 2 | Done
5 | 2019-02-19 | NABL SCOPE MODULE : -Discussion with client and Praveen sir. -Checking the bug reported by client on mail and fix it. - Client discussion and fix nabl scope issue mail done by deepika ma'am. | 5 | 2019-02-19 | 2019-02-19 | 2019-02-20 | Ruby/Praveen Singh | 2 | 14 | Done
[7 empty] | TOTAL | 46 | 49

## Summary
Stability Module
Consumed Hrs wrt Scope | 170 out of 200
Consumed Hrs without Scope | 25 out of 200