## Jan-2019
ITC ERP TASK DETAIL(Jan-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
Billed Hours
1 | 2019-01-03 | Deactivation of one feature of NABL Notification : Remove the use of special symbol "*" from the report in which NABL ULR no. is not defined. | 1 | 2019-01-22 | 2019-01-22 | 2019-01-22 | Praveen Singh | 5 | 5 | Done
2 | 2019-01-16 | Revised Task List 16-Jan-2019 : TASK-(A): Incorporate Branch code in Invoice-No. : | 2 | 2019-01-25 | 2019-01-28 | 2019-01-28 | Praveen Singh | 16 | 16 | Done
3 | 2019-01-16 | Revised Task List 16-Jan-2019 : TASK-(B): Branch code in holiday master: | 3 | 2019-01-23 | 2019-01-24 | 2019-01-24 | Praveen Singh | 9 | 9 | Done
4 | 2019-01-16 | Revised Task List 16-Jan-2019 : TASK-(C): No confirmation mail will be sent to customer on changing of analyst name after Scheduling: | 4 | 2019-01-23 | 2019-01-23 | 2019-01-23 | Praveen Singh | 8 | 8 | Done
5 | 2019-01-16 | Revised Task List 16-Jan-2019 : TASK-(D): Incorporation of country in invoicing structure or wherever it is required: | 5 | 2019-01-23 | 2019-01-29 | 2019-01-29 | Ruby | 24 | 24 | Done
6 | 2019-01-14 | ERP Training : Database Training | 6 | 2019-01-14 | 2019-01-14 | 2019-01-15 | Praveen Singh | 8 | 8 | Done
7 | 2019-01-14 | Customer Module:As per our discussion please incorporate email ids from + option in export to excel button. | 7 | 2019-01-31 | 2019-01-31 | 2019-01-31 | Ruby | 3 | 3 | Done
[7 empty] | TOTAL | 73 | 73