## June-2019
ITC ERP TASK DETAIL(June-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-06-01 | Regarding new tasks:[63.5 Approved Hours] (b) Signature of microbiologist (c) Dynamic Header & Footer of mail (d) Provision of account hold Extra Task Added:[1.5 Extra Hours consumed] (a)In TAT report add one new column explaining the reason of "Pending" entered by analyst instrument wise.Example(HPLC-Std.not available) etc. (b)In TAT report add one new col. of section incharge as presently all the reports pending in section incharge are showing pending under Reviewer. | 1 | 2019-06-01 | 2019-06-14 | 2019-06-14 | Praveen Singh (63.5 + 1.5) | 65 | 65 | Done |  | Extra Task added by the client and (1-2) extra hours also approved by the client in advance if extra task not managed in approved hours.
2 | 2019-06-04 | Client Feedback Points : i)Pending Process added by the Tester on Job Listing Page. ii)Section Incharge Permission Reallocation Process : If any section incharge is deactivated or its permission has been modified by the Admin. | 2 | 2019-06-04 | 2019-06-04 | 2019-06-04 | Praveen Singh(QH) | 2 | 2 | Done
3 | 2019-06-14 | Regarding changes in test report formats for NABL:- (a) Customer Defined Information (b) To write authorized signatory in place of Technical Manager (c) Description in Part C of test report (d) Order booking no. will be different than test report no. | 3 | 2019-06-14 | 2019-06-19 | 2019-06-19 | Praveen Singh | 30 | 30 | Done
4 | 2019-06-19 | TAT Mail Scheduling | 4 | 2019-06-19 | 2019-06-27 | 2019-06-27 | Praveen Singh [28 + 2(QH)] | 30 | 28.5 | Done
5 | 2019-06-26 | NABL Scope Updation from Excel in FOOD & ENV Department: | 5 | 2019-06-27 | 2019-06-27 | 2019-06-27 | Praveen Singh (QH) | 2 | 2 | Done |  | Continued in July-2019
6 | 2019-06-28 | Regarding 9th digit of NABL ULR no. -- Very Very Urgent | 6 | 2019-06-28 | 2019-06-29 | 2019-06-29 | Praveen Singh | 12 | 11.5 | Done |  | Continued in July-2019
[7 empty] | Total | 141 | 139