## March-2019
ITC ERP TASK DETAIL(March-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-03-08 | Regarding Customer Wise TAT : A)Generation of Expected Due Date : STEP 1 : If Customer has Customer-wise-tat defined and there is no Microbiological Instrument in it,then Expected Due Date will be calculated according to STEP 3. STEP 2 : If Customer has Customer-wise-tat defined or there is a Microbiological Instrument in it,then Expected Due Date will be calculated by the maximum TAT defined for a test parameter of a particular order irrespective of weekly off,sunday & +1 of after 2:00 pm conditions. STEP 3 : If Customer hasn't Customer-wise-tat defined and there is no Microbiological Instrument in it,then Expected Due Date will be calculated by the System normally. B)Provision for Re-Calculation of Expected Due Date in Case of Customer Wise TAT while Editing the Order: STEP 1 : Enabling the disabled TAT in Days field from editing window while user click on Editing Button of an Order. STEP 2 : Implementation of Expected Due Date Calculation Logic while Editing the Order in case of Customer Wise TAT. C) Keeping the testing time of ICPMS ,ICPOES & AAS as 3 days in all test masters. [Client-word :Regarding Customer Wise TAT: In customer wise TAT ,presently the order booker add the TAT(in days) at the time of order booking and system calculate Expected Due Date on the basis of entered value irrespective of holidays. Change required :- In the calculation of expected due date we want to include list of holidays and time conditions. Also the option to edit the expected due date in this case if user has entered wrongly from order booking. ] | 1 | 2019-03-08 | 2019-03-08 | 2019-03-08 | Praveen Singh(A) | 8 | 9 | Done
2 | 2019-03-19 | Implementation of listed Equipment Type in TAT MIS-Report: -Elisa -UPLCMSMS [Client-word:Incorporation of instrument name in TAT Report] | 2 | 2019-03-19 | 2019-03-19 | 2019-03-19 | Praveen Singh(Q) | 1 | 2 | Done
3 | 2019-03-27 | As per our discussion please incorporate these instruments in TAT report. GC TLC MALVERN MASTERSIZER GLUCOMETER GC-ECD HPTLC UV-SPECTROPHOTOMETER Please keep same category in consecutive columns. Example- GC, GC-FID(Nucon) , GC-FID(Agilent), GC-FID-HS, GC-ECD in a sequence. | 3 | 2019-03-27 | 2019-03-27 | 2019-03-27 | Praveen Singh(Q) | 1 | 1 | Done
4 | 2019-03-27 | Creation of Default Order Process Flow from Testing Stage to Approving Stage if any new Product Category/Department created and order booked in that New Category/New Department in ERP. | 4 | 2019-03-27 | 2019-03-27 | 2019-03-27 | Praveen Singh(A) | 5 | 7 | Done
5 | 2019-03-01 | STABILITY INVOICING MODULE(Documentation and DB-Design) | 5 | 2019-03-01 | 2019-03-01 | 2019-03-01 | Praveen Singh | 10 | 10 | Done
6 | 2019-03-12 | Software Updation: -Updated Code on Drish Live Server from SVN. -Updated DB on Drish Live Server. -Updated Code on Drish Dev Staging Server from SVN. -Updated DB on Drish Dev Staging Server. -Created the Software Package for Live Server Updation. -Updated Code on ITC Live Server with Latest Code. -Updated DB on ITC Live Staging Server. | 6 | 2019-03-12 | 2019-03-12 | 2019-03-12 | Praveen Singh | 1 | 2 | Done
[7 empty] | TOTAL | 26 | 31