## Nov-2018
ITC ERP TASK DETAIL(Nov-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-11-02 | Regarding provision of section incharge and NABL logo in ERP: (a) In section incharge provision how a person is able to approve reports of those instruments whose rights is not given to him. Example:- in case of Food, we have one checkbox of ALL. If we will not select that check box then no report is displayed to Indra Madam under Section Incharge role and if she selects that check box then all reports will be displayed to her. While approving one report of chemical section by default complete report is approved(if it has parameter of instrument section also).-Done (b) How a NABL logo will be applied on chennai reports when NABL logo is not incorporated in their report header.-Working On | 1 | 2018-11-02 | 2018-11-03 | 2018-11-03 | Praveen Singh | 1 | 1 | Done
2 | 2018-11-02 | Regarding test master of food to be used since today: (a)Please share the list of test masters we had used since today in Food department Panchkula. | 2 | 2018-11-02 | 2018-11-02 | 2018-11-02 | Praveen Singh | 1 | 1 | Done
3 | 2018-11-12 | Client Feedback Point: 1.The reports approve yesterday have the same problem. The total no. of reports are as follows :- F01-1811020187, F01-1811020186 .F01-1811020181, F01-1811020163, F01-1811020160, F01-1811020148, F01-1811020147, F01-1811020146, F01-1811020145, F01-1811020144, F01-1811020143, F01-1811020128, F01-1811020127, F01-1811020126, F01-1811020117, F01-1810311583, F01-1810311582, F01-1810311581, F01-1810311578, F01-1810311574, F01-1810311572, F01-1810311571, F01-1810311559, F01-1810311553, F01-1810311540, F01-1810311539, F01-1810311538, F01-1810311535, F01-1810301524, F01-1810301523, F01-1810301520, F01-1810301519, F01-1810301518, F01-1810301517, F01-1810301516, F01-1810301514, F01-1810301511, F01-1810301506, F01-1810301470, F01-1810291449, F01-1810291402, F01-1810291397, F01-1810271360, F01-1810271355, F01-1810261327, F01-1810311579, F01-1810311573, F01-1810311567, F01-1810311558, F01-1810311557, F01-1810311556, F01-1810231150, 2.Please change the status of these samples to Invoicing from Booking. The order booking no.'s are F01-1712291460 &F01-1712291459. | 3 | 2018-11-12 | 2018-11-12 | 2018-11-12 | Praveen Singh | 2 | 2 | Done
4 | 2018-11-13 | Client feedback Points: 1)Overlaping of Report:Please rectify these reports also"- f01-18072301372, f01-18072301375, f01-18072301380, F01-18103101560, F01-18103101561, F01-18103001515 2)Regarding provision of section incharge and NABL logo in ERP:: Please update this Live server so that problem of "P" in NABL ULR no. will be resolved. | 4 | 2018-11-13 | 2018-11-13 | 2018-11-13 | Praveen Singh | 1 | 1 | Done
5 | 2018-11-27 | A)Implementation of New Test Report Right hand Side Logo in all department in Panchkula Branch: i)Food ii)Pharma iii)Water iv)Helmet v)Ayurveda vi)Building vii)Textile viii)Environment B)User Feedback Points: i)Error in editing of listed Orders due to deletion of all test parameter by the Users: i)E02-1811190107, ii)E02-1811190108, iii)E02-1811200152, iv)E02-1811200153 | 5 | 2018-11-27 | 2018-11-27 | 2018-11-27 | Praveen Singh | 4 | 4 | Done
6 | 2018-11-28 | Client Requirement(Multi Session Concept): 1.Stopping User to open New Tab in any Browser(At a time one browser) .If user opens one browser multiple time ,then in each browser only one tab. 2.Testing in multiple browser like Mozilla,Chrome etc. | 6 | 2018-11-28 | 2018-11-28 | 2018-11-28 | Praveen Singh | 4 | 4 | Done
7 | 2018-11-28 | New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(a) In case of "F" also we have to keep NABL logo optional presently it is mandatory: | 7 | 2018-11-28 | 2018-11-28 | 2018-11-28 | Praveen Singh | 6 | 6 | Done
8 | 2018-11-28 | New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(c) In case of "F" and "P", we have to define non-NABL scope parameters on the test report using '*' in front of parameter name and one remark will be printed in remark box ('*' represents test parameters not covered under NABL Scope.) | 8 | 2018-11-29 | 2018-11-30 | 2018-11-30 | Praveen Singh | 12 | 12 | Done
9 | 2018-11-28 | New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(d) The reports in which no NABL ULR no. is not defined, we have to use '*' front of all parameter category to represent non NABL scope parameters and one remark will be printed in remark box( '*' represents parameter categories not covered under NABL scope.) | 9 | 2018-12-01 | 2018-12-03 | 2018-12-03 | Praveen Singh | 12 | 12 | Done
10 | 2018-11-28 | New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(e) In case of Outsource sample we have to use '**' to represent parameters tested outside the lab. How to add provision will need discussion.(subcontract user): | 10 | 2018-12-03 | 2018-12-03 | 2018-12-03 | Praveen Singh | 7 | 7 | Done
11 | 2018-11-28 | New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(g) For every department we have to keep provision to keep limit column optional by providing check box at the time of "Approval to QA": | 11 | 2018-12-04 | 2018-12-04 | 2018-12-04 | Praveen Singh | 8 | 8 | Done