## Oct-2018
ITC ERP TASK DETAIL(Oct-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-10-01 | Blocking of back date booking for Parameters in scope of NABL: STEP-1 : Displaying of NABL Scope Column in Adding and Editing of Order in an Order Form. STEP-2 : Integration of Logic : Blocking of back date booking if any of the selected test Parameter in an particular booking is in NABL Scope at the time of booking. STEP-3 : Displaying of Message 'Order cannot be booked as Test Parameter lies in NABL Scope.' if any user try to book an order of NABL Scope Parameter in back date. | 1 | 2018-10-03 | 2018-10-03 | 2018-10-03 | Praveen Singh | 4 | 4 | Done
2 | 2018-10-04 | In all MIS report add column of total by default. (a) Daily Booking Detail :- In the column sample amount( the amount on ehich sample is booked) system is showing zero value. (b) Party Wise Sample Count Report -Date Wise :- Total in last column (c) Party Wise Sample Count Report -Month Wise :- Total in last column (d)Sales related reports are as follows:- Sales Report Detail Daily Invoice Detail Daily sales Detail Account sales detail All reports are related to sale value therefore the sale value should be same. (e) Booking Count related reports are as follows:- Daily Booking Detail Sample Log Status TAT Report All reports are related to order booking therefore values of common fields will be same in all reports. | 2 | 2018-10-09 | 2018-10-09 | 2018-10-09 | Praveen Singh | 1 | 1 | Done
3 | 2018-10-12 | Client Feedback Point: Regarding Customer change error in Order Booking of Chennai: We booked 8 samples on the name of Interstellar Testing Centre Pvt. Ltd. Chennai on 09/10/2018 in Chennai location now i want to change the name of customer to Kwality Milk Foods LTd.( from Admin end) but system is showing error message "No Customer Invoicing type defined". Please check and update. | 3 | 2018-10-12 | 2018-10-12 | 2018-10-12 | Praveen Singh | 2 | 2 | Done
4 | 2018-10-23 | Client Feedback Point: (a) System is again considering holidays & weekly offs in expected due date of sample. Please check the logic thoroughly why it is happening again & again. I am attaching the data of pharma for reference. (b) In NABL ULR no. generation system is considering only ,'F' in 18th digit whereas in some cases 'P' is applicable. (c) User is not able to enter result in these two report no.P01-1810160102 & P01-1809080257 | 4 | 2018-10-23 | 2018-10-23 | 2018-10-23 | Praveen Singh | 1 | 1 | Done