## Sept-2019
ITC ERP TASK DETAIL(Sept-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-08-30 | QH-Query Hour-30.08.2019 | 1 | 2019-09-02 | 2019-09-02 | 2019-09-02 | Praveen Singh | 2 | 2 | Done
2 | 2019-09-03 | Software Updation | 2 | 2019-09-03 | 2019-09-03 | 2019-09-03 | Praveen Singh(QH) | 2 | 2 | Done
3 | 2019-09-04 | Urgent - Regarding Himalaya Monthly Tracker | 3 | 2019-09-04 | 2019-09-10 | 2019-09-10 | Praveen Singh | 4 | 4 | Done
4 | 2019-09-13 | Regarding date change in Microbiologist Signature | 4 | 2019-09-13 | 2019-09-16 | 2019-09-16 | Praveen Singh | 5 | 5 | Done
5 | 2019-09-16 | Changes & Corrections required in Customer Master | 5 | 2019-09-16 | 2019-09-23 | 2019-09-23 | Praveen Singh | 25 | 25 | Done
6 | 2019-09-19 | Regarding Shifting of ITC Project to New Server | 6 | 2019-09-19 | 2019-09-24 | 2019-09-24 | Praveen Singh | 11 | 11 | Done
7 | 2019-09-21 | Integration of User Log Activity Functionality | 7 | 2019-09-23 | 2019-09-23 | 2019-09-23 | Praveen Singh | 3 | 3 | Done
8 | 2019-09-25 | Correction in Daily Sales Detail | 8 | 2019-09-25 | 2019-09-25 | 2019-09-25 | Praveen Singh | 3 | 3 | Done
9 | 2019-09-27 | Regarding Protocol Review Remarks in all departments other than Pharma | 9 | 2019-09-27 | 2019-09-27 | 2019-09-27 | Praveen Singh | 3 | 3 | Done
10 | 2019-09-30 | Chand Sir | 10 |  |  |  | Chand Sir | 6 | 6 | Done
[7 empty] | Total | 64 | 64
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs