## Sept-2019
ITC ERP TASK DETAIL(Sept-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-08-30 | QH-Query Hour-30.08.2019 | 1 | 2019-09-02 | 2019-09-02 | 2019-09-02 | Praveen Singh | 2 | 2 | Done
2 | 2019-09-03 | Software Updation | 2 | 2019-09-03 | 2019-09-03 | 2019-09-03 | Praveen Singh(QH) | 2 | 2 | Done
3 | 2019-09-04 | Urgent - Regarding Himalaya Monthly Tracker | 3 | 2019-09-04 | 2019-09-10 | 2019-09-10 | Praveen Singh | 4 | 4 | Done
4 | 2019-09-10 | Sales Related MIS-Report Validation Regarding Credit Note Amount | 4 | 2019-09-10 | 2019-09-12 | 2019-09-12 | Praveen Singh | 9 | 9 | Done
5 | 2019-09-13 | Regarding date change in Microbiologist Signature | 5 | 2019-09-13 | 2019-09-16 | 2019-09-16 | Praveen Singh | 5 | 5 | Done
6 | 2019-09-16 | Changes & Corrections required in Customer Master | 6 | 2019-09-16 | 2019-09-23 | 2019-09-23 | Praveen Singh | 25 | 25 | Done
7 | 2019-09-19 | Regarding Shifting of ITC Project to New Server and involvement with Tester | 7 | 2019-09-19 | 2019-09-24 | 2019-09-24 | Praveen Singh | 11 | 11 | Done
8 | 2019-09-21 | Integration of User Log Activity Functionality | 8 | 2019-09-23 | 2019-09-23 | 2019-09-23 | Praveen Singh | 3 | 3 | Done
9 | 2019-09-25 | Correction in Daily Sales Detail | 9 | 2019-09-25 | 2019-09-25 | 2019-09-25 | Praveen Singh | 3 | 3 | Done
10 | 2019-09-27 | Regarding Protocol Review Remarks in all departments other than Pharma | 10 | 2019-09-27 | 2019-09-27 | 2019-09-27 | Praveen Singh | 3 | 3 | Done
11 | 2019-09-27 | ITC New Server : Debugging & Optimization of the SQL Query | 11 | 2019-09-27 | 2019-09-30 | 2019-09-30 | Praveen Singh | 12 | 12 | Done
12 | 2019-09-30 | Chand Sir | 12 |  |  |  | Chand Sir | 15 | 15 | Done
[7 empty] | Total | 94 | 94
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs

## Oct-2019
ITC ERP TASK DETAIL(Oct-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-10-01 | Regarding Very-Very Urgent task of Chennai Branch | 1 | 2019-10-01 | 2019-10-04 | 2019-10-04 | Praveen-Singh | 5 | 5 | Done
2 | 2019-09-26 | Regarding issue in calculation of department due date | 2 | 2019-10-05 | 2019-10-19 | 2019-10-19 | 2019-10-19 | 16 | 16 | Done
3 | 2019-09-27 | Sales Executive List to be uploaded in LIMS | 3 | 2019-10-11 | 2019-10-11 | 2019-10-11 | Praveen-Singh(QH) | 1 | 1 | Done
4 | 2019-10-01 | ITC New Server : Debugging & Optimization of the SQL Query | 4 | 2019-10-19 | 2019-10-19 | 2019-10-19 | Praveen Singh | 17 | 16.5 | Done
5 | 2019-10-01 | Optimization of Report Landing Page according to Role Users. | 5 | 2019-10-31 | 2019-10-31 | 2019-10-31 | Praveen Singh | 5 | 5 | Done
6 | 2019-10-01 | Performance Optimization | 6 |  |  |  | Chand Sir | 45 | 45 | Done
[7 empty] | Total | 89 | 88.5
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs

## Nov-2019
ITC ERP TASK DETAIL(Nov-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-11-01 | Query hour- 19.10.2019 : Merging of Customer Name and Invoicing Customer Name. | 1 | 2019-11-01 | 2019-11-01 | 2019-11-01 | Praveen-Singh | 2 | 2 | Done
2 | 2019-11-08 | Software Updation | 2 | 2019-11-08 | 2019-11-08 | 2019-11-08 | Praveen Singh(QH) | 2 | 2 | Done
4 | 2019-10-18 | Regarding Chennai Report Format | 4 | 2019-11-09 | 2019-11-22 | 2019-11-22 | Praveen-Singh | 44 | 44 | Done
4 | 2019-11-25 | Software Updation | 4 | 2019-11-25 | 2019-11-25 | 2019-11-25 | Praveen Singh(QH) | 2 | 2 | Done
5 | 2019-11-30 | Chand Sir | 5 | 2019-11-30 |  |  | Chand Sir | 6 | 6 | Done
[7 empty] | Total | 56 | 56
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs

## Dec-2019
ITC ERP TASK DETAIL(Dec-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2019-11-27 | Points to be corrected-Chennai reporting | 1 | 2019-12-04 | 2019-12-12 | 2019-12-12 | Praveen-Singh | 10 | Done
2 | 2019-12-09 | Client Feedback Points: i)Addressed the error in Invoice Generation for PHRAMA Department. ii)Checked the Scheduled Mail Sending Error both in Application and Server Level with co-0rdibation with Networking Team. | 2 | 2019-12-09 | 2019-12-09 | 2019-12-09 | Praveen-Singh | 2 | Done
3 | 2019-12-13 | Software Updation | 3 | 2019-12-13 | 2019-12-13 | 2019-12-13 | Praveen Singh(QH) | 1 | Done
4 | 2019-12-12 | Regarding stack report for environment | 4 | 2019-12-12 | 2019-12-19 | 2019-12-19 | Praveen-Singh | 9 | Done
5 | 2019-12-19 | Regarding Points to be clear(9(A)+2(Q)) | 5 | 2019-12-19 | 2019-12-31 | 2019-12-31 | Praveen-Singh | 11 | Done
6 | 2019-12-01 | Chand Sir | 6 | 2019-12-31 |  |  | Chand Sir | 4 | Done
[7 empty] | Total | 37
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs

## Jan-2020
ITC ERP TASK DETAIL(Jan-2020)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2020-01-06 | Regarding Points to be clear : Client Feedback Points | 1 | 2020-01-06 | 2020-01-09 | 2020-01-09 | Praveen Singh | 3.5 | 3 | Done
2 | 2020-01-15 | Software Updation | 2 | 2020-01-15 | 2020-01-15 | 2020-01-15 | Praveen Singh | 1 | 1 | Done
3 | 2020-01-03 | Sales Report Detail- To be considered on priority | 3 | 2020-01-15 | 2020-01-28 | 2020-01-28 | Praveen Singh | 16 | 15 | Done
4 | 2020-01-27 | Regarding Chennai report formats to be incorporated in LIMS : | 4 | 2020-01-27 | 2020-01-31 | 2020-01-31 | Praveen Singh | 50 | 9 | Done
5 | 2020-01-27 | Please change approval date to 25.01.2020 from 27.01.2020(QH) | 5 | 2020-01-29 | 2020-01-29 | 2020-01-29 | Praveen Singh | 1 | 1 | Done
6 | 2020-01-28 | Rest of the invoices(QH) | 6 | 2020-01-29 | 2020-01-29 | 2020-01-29 | Praveen Singh | 1 | 1 | Done
7 | 2019-12-01 | Chand Sir | 7 | 2019-12-31 |  |  | Chand Sir | 5 | 4 | Done
[7 empty] | Total | 72.5 | 34
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs

## Feb-2020
ITC ERP TASK DETAIL(Feb-2020)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2020-01-27 | Regarding Chennai report formats to be incorporated in LIMS : | 1 | 2020-01-27 | 2020-02-13 | 2020-02-13 | Praveen Singh | 41 | 41 | Done
2 | 2020-02-04 | Client Side Visit regarding below points: i)Task Discussion ii)New Scope Discussion iii)Documentation/Mockup creation of New Scope | 2 | 2020-02-04 | 2020-02-04 | 2020-02-04 | Praveen Singh | 5 | 5 | Done
3 | 2020-02-14 | Web Portal : Auto Synchronization of Report/Invoice/VOC using CRON JOB Scheduler | 3 | 2020-02-14 | 2020-02-15 | 2020-02-15 | Praveen Singh | 9 | 8.5 | Done
4 | 2020-02-17 | Regarding Task List | 4 | 2020-02-17 | 2020-02-20 | 2020-02-20 | Praveen Singh | 4 | 4 | Done
5 | 2020-02-24 | Changes : APEDA Chennai report formats to be incorporated in LIMS | 5 | 2020-02-24 | 2020-02-29 | 2020-02-29 | Praveen Singh | 14 | 13.5 | Done
6 | 2019-12-01 | Chand Sir | 6 | 2020-02-01 |  |  | Chand Sir | 4 | 4 | Done
[7 empty] | Total | 77 | 76
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs

## April-2021
ITC ERP TASK DETAIL(April-2021)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2021-04-02 | Sales Excutive names update in LIMS Goutam Panda(GoutamPanda453) to Debabrata Bera(DebabrataBera507) Sant Kumar(SantKumar120) to Pramod(Pramod479) | 1 | 2021-04-13 | 2021-04-13 | 2021-04-13 | Praveen-Singh | 1 | Done
2 | 2021-04-02 | While adding new parameter from Job sheet print NABL scope is not incorporated by software. | 2 | 2021-04-06 | 2021-04-06 | 2021-04-06 | Ruby Thakur | 4 | Done
3 | 2021-04-02 | Incorporate below line under Terms & conditions of Invoice.“We are falling under MSMED Act. Please release the payment within 45 days or else Compound interest @12.75% P.A will be chargeable” | 3 | 2021-04-17 | 2021-04-17 | 2021-04-17 | Praveen-Singh | 2 | Done
4 | 2021-04-02 | Scheduling Jobs - Under Sample wise provision please incorporate department & instrument names column Scheduling Jobs - Under Parameter wise provision please incorporate Department name column | 4 | 2021-04-19 | 2021-04-19 | 2021-04-19 | Praveen-Singh | 3 | Done
5 | 2021-04-05 | Account Hold provision for New Customers Step 1:- New Customer code will be created. Step 2:- Order Booking will be performed. Step 3:- On save of order booking softwarewill checked the data of order booking for customer in last 6 months. Step 4:- If no order booking was found,customer will be considered as "New Customer". Step 5:- Software will put these customer "On Hold" automatically with reason of "Account Hold" Step 6:- New customer put "on Hold" will be displyed in CRM role under new tab of "Hold & UnHold Customer" tab only to those users to whom rights are given by Administrator in Employee master form as discussed. Step 7:- User will check the payment status and "Unhold" customer. Step 8 :- Provision of auto email to the user on click of Check box for "Hold" customer. Step9 :- Alert on user dashboard regarding the "hold" customers | 5 | 2021-04-06 | 2021-04-14 | 2021-04-14 | Praveen-Singh | 37 | Done
6 | 2021-04-05 | Please change the user name of stability modules from Administrator to Karamvir (KaramvirKalsi323) | 6 | 2021-04-14 | 2021-04-14 | 2021-04-14 | Praveen-Singh | 1 | Done
7 | 16/04/2021 | Alert - For new customer put on hold highlight with different colour and will come on top | 7 | 2021-04-19 | 2021-04-19 | 2021-04-19 | Praveen-Singh | 1 | Done
8 | 16/04/2021 | Emailing for hold customers : To - mail of customer CC- mail of person unholding the customer, Mail id of CRM & Sales Executives(Email Id of CRM will be selected Branch & Department wise) | 8 | 2021-04-17 | 2021-04-17 | 2021-04-17 | Praveen-Singh | 1 | Done
9 | 16/04/2021 | Provision of Unhold customers will work Branch wise. | 9 | 2021-04-19 | 2021-04-19 | 2021-04-19 | Praveen-Singh | 2 | Done
10 | 2020-12-01 | Chand Sir | 10 | 2021-04-01 | 2021-04-30 | 2021-04-30 | Chand Sir | 3 | Done
[7 empty] | Total | 55