## April-2022
ITC ERP TASK DETAIL(April-2022)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Developer | Expected/Approved Hours | Dev Status
1 | 2022-03-21 | Provision to edit GST tax slab and amount in generated invoice. | 1 | 2022-04-11 | 2022-04-13 | Praveen-Singh | 15 | Done
2 | 2022-04-09 | QH : Blocker points of LIMS | 2 | 2022-04-09 | 2022-04-11 | Praveen-Singh | 3 | Done
3 | 2022-04-09 | Sample Detail Design Modification : Test Report Template - Form 39 ,Cos -24 & Form 50 | 3 | 2022-04-26 | 2022-04-28 | Praveen-Singh | 25 | Done
4 | 2022-02-08 | QH : Client Feedback Points : Test report Format :C01-2204260850,C01-2204190599,C01-2204150551,C01-2203230614 ,616 Cos -24 first page is coming blank.Please correct NABL logo in ayurvedic report no. A01-2204010001 and A01- 2204010003. P01-2203260014, P01-2203260015 First page is coming blank. | 4 | 2022-04-01 | 2022-04-30 | Praveen Singh | 2 | Done
5 | 2022-04-26 | Regarding 'Voice of Customer' auto email circulated on 01st of every month : Deactivating | 5 | 2022-04-28 | 2022-04-28 | Praveen Singh | 1 | Done
6 | 2022-04-29 | Provision to define Parent parameter name for the 'Parent Parameter Invoicing' drop down list by applying check box on'Test Parameter Name' | 6 | 2022-04-29 | 2022-04-30 | Praveen Singh | 6 | Done
7 | 2022-04-29 | Incorporate one column of Test Parameter Code in Master ->Tests-> Product Test tab on Dashboard & Export to excel button. | 7 | 2022-04-30 | 2022-04-30 | Praveen Singh | 1 | Done
8 | 2022-04-29 | Incorporate one column of Test Parameter Code in Scheduling->Jobs->Parameter wise Listing on Dashboard & Export to excel button. | 8 | 2022-04-30 | 2022-04-30 | Praveen Singh | 2 | Done
9 | 2022-04-29 | Incorporate one column of Test Parameter Code along with Test Parameter name in MIS->ITC Standard Price Vs Sample wise Pricing . | 9 | 2022-04-30 | 2022-04-30 | Praveen Singh | 1 | Done
10 | 2022-01-01 | Chand Sir | 10 | 2022-04-01 | 2022-04-30 | Chand Sir | 4 | Done
[6 empty] | Total | 60