## Feb-2021
ITC ERP TASK DETAIL(Feb-2021)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2021-02-10 | Regarding Errors in STF of stability protocol | 1 | 2021-02-12 | 2021-02-12 | 2021-02-12 | Praveen Singh | 1 | Done |  | QH
2 | 2021-02-10 | Selecting of Dynamic Field in order booking from Master | 2 | 2021-02-16 | 2021-02-16 | 2021-02-16 | Anjana garg | 9 | Done
3 | 2021-02-10 | Block editing of Customer name,address,city,state from user end. Changes will be done by Administrator only. | 3 | 2021-02-19 | 2021-02-19 | 2021-02-19 | Anjana garg | 6 | Done
4 | 2021-02-10 | Display Check box of "EIC Report" on Approval Dashboard for Food Department only. | 4 | 2021-02-19 | 2021-02-19 | 2021-02-19 | Praveen Singh | 3 | Done
5 | 2021-02-10 | Incorporate column of GST No. & Regulation in Daily Booking Detail | 5 | 2021-02-20 | 2021-02-22 | 2021-02-22 | Praveen Singh | 4 | Done
6 | 2021-02-10 | Incorporate Discipline & Group in Building template | 6 | 2021-02-23 | 2021-02-27 | 2021-02-27 | Praveen Singh | 18 | Done
7 | 2021-02-10 | Incorporate Form 39 A in Cosmetics Chennai | 7 | 2021-02-24 | 2021-02-27 | 2021-02-27 | Praveen Singh | 14 | Done
8 | 2021-10-02 | Regarding updating the Order Amount in case of inter-laboratory and Compensatory orders | 8 | 2-24-2021 | 2-24-2021 | 2-24-2021 | Praveen Singh | 3 | Done
[7 empty] | Total | 58