## FEB-2018
ITC ERP TASK DETAIL(FEB-2018)
S.No. | Date | Detail | Priority | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 31-01-2018 | Uploading of Pharma Master on Staging Server(CSV to Sql Data Uploading): | 21 | 2018-02-02 | 2018-02-02 | Praveen Singh | 9 | 9 | Done
2 | 31-01-2018 | Testing of Helmet Department Go-Live Process Flow | 22 | 2018-02-01 | 2018-02-02 | Ruby | 9 | 9 | Done
3 | 31-01-2018 | Testing of Building Department Go-Live Process Flow | 23 | 2018-02-02 | 2018-02-02 | Ruby | 9 | 9 | Done
4 | 2018-01-02 | Testing of Textile Department Go-Live Process Flow | 27 | 2018-02-03 | 2018-02-03 | Ruby | 9 | 9 | Done
5 | 2018-01-02 | Testing of Environment Department Go-Live Process Flow | 28 | 2018-02-05 | 2018-02-05 | Ruby | 9 | 9 | Done
6 | 2018-01-02 | Creation Of Helmet Master from Staging Server | 25 | 2018-02-01 | 2018-02-01 | Pratyush | 8 | 8 | Done
7 | 2018-01-02 | Removing of Old Pharma Master | 26 | 2018-02-02 | 2018-02-02 | Praveen Singh | 7 | 7 | Done
8 | 2018-02-02 | Pharma Points of Testing
(a) | 1 | For pharma we do the sample receiving on reception only on current samples,no receiving will be done in case of back date samples. Booking User should have provision to do the booking without the sample receiving code. | 29 | 2018-02-09 | 2018-02-09 | Praveen Singh | 2 | 16 | Done
(b) |  | In Pharma,Manufacturing license no. is product specific for a particular customer. Booking user will define it at the time of booking according to product category. | 30 | 2018-02-03 | 2018-02-03 | Praveen Singh | 10 | 10 | Done
(c) | 2 | For Header note we have some standard notes which will be incorporated for the user ease and user should also have option to type any other header note.. | 31 | 2018-02-02 | 2018-02-02 | Praveen Singh | 3 | 3 | Done | In place of showing all header notes from Booking,Update only below standard list at the time of Booking
Each Film Coated Tablet Contains
Each Uncoated Tablet Contains
Composition
Each Hard Gelatin Capsule Contains
Each Enteric Coated Tablet Contains
Each ml Contains
Each Mouth Dissolving Tablet Contains
Each Vial Contains
Each Bolus Contains
(d) | 3 | In Job order, if a testing parameter don't have method then in place of displaying N/A,it will be blank. | 32 | 2018-02-02 | 2018-02-02 | Praveen Singh | 3 | 3 | Done
(e) | 4 | Like Description in food , In Pharma there are two parameters Reference to Protocol & Description have no instrument. | 33 | 2018-02-02 | 2018-02-02 | Praveen Singh | 1 | 1 | Done
9 | 2018-02-02 | Cloning of Order Booking | 34
10 | 2018-03-02 | Go-Live Process of Pharma Department(Overall Process Testing): a)In Analytical sheet, we should have two coloumns for claim and for pharma header note will be included in Assay Category b)In Scheduling Jobs ,text box to define reason of pendency is not disp laying. c)System is displaying server error at the time of reviewing of report.-Pharma d)Final print out of report is not correct. e)Label "Date of start of analysis" will be removed from Final report. | 35 | 2018-02-06 | 2018-02-06 | Ruby | 12 | 12 | Done | Claim limit value will also be displayed along with claim.
11 | 2018-03-02 | Back Date Booking Provision in Pharma Department | 39 | 2018-02-12 | 2018-02-12 | Praveen Singh | 16 | 16 | Done
12 | 31-01-2018 | Uploading of Helmet Master on Live Server(CSV to Sql Data Uploading): | 40 | 2018-02-08 | 2018-02-08 | Praveen Singh | 3 | 3 | Done
13 | 2018-03-02 | 1)If Invoicing-To will be in different name then tax slab will be according to invoicing to name in place of booking client name. 2)Displaying of Deparment Due date to Analyst in place of Expected Due Date | 38 | 2018-02-06 | 2018-02-06 | Praveen Singh | 8 | 8 | Done
14 | 2018-05-02 | Testing of Ayurvedic Department Go-Live Process Flow | 41 | 2018-02-13 | 2018-02-13 | Ruby | 9 | 9 | Done
15 | 2018-07-02 | Signatures of reviewer and finalier are not updated in the pharma software. | 44 | 2018-02-13 | 2018-02-13 | Praveen Singh | 5 | 5 | Done
16 | 2018-07-02 | In analystical sheet, only single printout will be taken for one instrument, if user want to take the printout of sheet again then, the approval from QA will be mandatory. The user is able to take the prinout of blank sheet from the scheduler no. of times according to the requirement and system will maintain the count of blank sheet taken by the analyst for a particular sample. I case of printing of analytical sheet for a particular instrument only those parameters will be displayed at the time of printing which was booked by the user.
17 | 2018-07-02 | There sholud be a provision to send the report with equipment & Without equipment at the the time of finalization by Finalizer and Dispatcher for printing | 45 | 2018-02-19 | 2018-02-19 | Pratyush | 13 | 13 | Done
18 | 2018-07-02 | Helmet:- In Scheduling, assign job prints order no's will be related to the department of scheduler. | 46 | 2018-02-13 | 2018-02-13 | Ruby | 3 | 3 | Done
19 | 2018-07-02 | Text body of order confirmation mail will be changed for helmet and other departments. | 47 | 2018-02-13 | 2018-02-13 | Praveen Singh | 8 | 8 | Done
20 | 2018-07-02 | Creation of Ayurvedic Department Master On ITC Ayurvedic Staging Server: | 48 | 2018-02-08 | 2018-02-08 | Pratyush | 18 | 18 | Done
21 | 2018-12-02 | Creation and Uploading of Pharma Master from Staging Server to Live Server(CSV To SQL) | 26 | 2018-02-17 | 2018-02-17 | Praveen Singh | 27 | 27 | Done
22 | 2018-12-02 | Software Updation | 24 | 2018-02-12 | 2018-02-12 | Praveen Singh | 2 | 2 | Done
23 | 2018-12-02 | Testing Ayurvedic Department ITC Dev Ayurvedic Staging Server | 24 | 2018-02-12 | 2018-02-12 | Pratyush | 8 | 8 | Done
24 | 13-02-2018 | Put Check Boxes in front of samples in invoicing for the user to select or deselect the no. of samples for invoicing. | 27 | 2018-02-13 | 2018-02-13 | Ruby | 5 | 5 | Done
25 | 13-02-2018 | Display the list of parameters and their amount in the pop up at the time of Generate Invoices on any location to make it easier for user to cross check the rates. | 28 | 2018-02-16 | 2018-02-16 | Ruby | 8 | 8 | Done
26 | 2018-05-02 | Testing of Ayurvedic Department Go-Live Process Flow | 41 | 2018-02-13 | 2018-02-13 | Pratu | 9 | 9 | Done
27 | 16-02-2018 | The Report format of ayurvedic will be same as pharma and header format is different.Scan copy is provided to Parveen. | 29 | 2018-02-19 | 2018-02-19 | Ruby | 12 | 8 | Done
28 | 16-02-2018 | The signature on the report will be of the last reviewer who confirms irrespective of save(action) count. | 49 | 2018-02-19 | 2018-02-19 | Pratyush | 5 | 5 | Done
29 | 16-02-2018 | Test Master and Assay Master Category Changes all over the Pharma Section.Real Time Stability Note will be displayed above test parameters and header note will be displayed between test master and assay master. | 52 | 2018-02-21 | 2018-02-21 | Ruby | 6 | 6 | Done
31 | 16-02-2018 | In Pharma back date booking,at the time of finalization there should be an option to select date of finalization .By default the date of reviewing will be displayed to the the finalizer and date of finalization will be displayed to the Approval to QA. | 56 | 2018-02-23 | 2018-02-23 | Ruby | 9 | 12 | Done
33 | 16-02-2018 | Partial Report Provision-
34 | 16-02-2018 | Pin Code in Customer Master & Country wise state and city. | 52 | 2018-02-22 | 2018-02-22 | Pratyush | 18 | 18 | Done
35 | 17-02-2018 | Invoicing will be done on the basis of parameter name and instrument irresctive of method | 51 | 2018-02-20 | 2018-02-20 | Praveen Singh | 12 | 12 | Done
36 | 19-02-2018 | Signatures of User(Alok & Dharmendra) on Finalizer and Approval Order Stage | 53 | 2018-02-21 | 2018-02-21 | Praveen Singh | 5 | 5 | Done
37 | 20-02-2018 | Booking - Invoicing Rate Issue. Reviewing - Report Date and Report Code Generation Issue. Finalizing - Signature Updation of Reviewer Issue. Approval - Signature Updation of Reviewer and Finalizer Issue. | 54 | 2018-02-22 | 2018-02-22 | Praveen Singh | 9 | 9 | Done
38 | 20-02-2018 | Displaying of Department Due Date in Scheduling and Changing of Expected Due date will change the Report DUe date and Department DUe Date | 55 | 2018-02-23 | 2018-02-23 | Praveen SIngh | 5 | 5 | Done
39 | 20-02-2018 | Creation of New Role for Master Creation for the Users | 56 | 2018-02-23 | 2018-02-23 | Pratyush | 6 | 6 | Done
40 | 2018-12-02 | Software Updation | 24 | 2018-02-20 | 2018-02-20 | Praveen Singh | 2 | 2 | Done
41 | 22-02-2018 | Uploading of Ayurvedic Master on Live Server | 57 | 2018-02-23 | 2018-02-23 | Pratyush | 8 | 8 | Done
42 | 23-02-2018 | Reporting Listing Changes: 1)Displaying of dispatched button of dispatched Orders. Invoicing Listing Changes: 2)Displaying of pagination on all invoicing listing. 3)Displaying of Pagination in viewing of all generated orders. | 58 | 2018-02-24 | 2018-02-24 | Praveen Singh | 7 | 7 | Done
43 | 22-02-2018 | Uploading of Textile Master on Staging Server | 59 | 2018-02-24 | 2018-02-24 | Pratyush | 8 | 8 | Done
44 | 26-02-2018 | Search Buttons on all Invoicing Structure | 60 | 2018-02-27 | 2018-02-27 | Pratyush | 9 | 9 | Done
45 | 26-02-2018 | Department Filter on Order Number Selectbox in Job Sheet Print in Scheduling | 62 | 2018-02-28 | 2018-02-28 | Pratyush | 7 | 7 | Done
46 | 26-02-2018 | Invoice generation will be department wise | 61 | 2018-02-26 | 2018-02-26 | Praveen Singh | 7 | 7 | Done
47 | 26-02-2018 | Invoicing Structure for adding rates will be department wise | 63 | 2018-02-28 | 2018-03-01 | Ruby | 18 | 18 | Done
48 | 26-02-2018 | In the report format of food, Part -A Sample information the fields with N/A will not be displayed in report. | 65 | 2018-02-28 | 2018-02-28 | Pratyush | 9 | 9 | Done
49 | 27-02-2018 | Name and Signature Implementation on Helment Order Process Stages.Removing of Equipment Column. | 64 | 2018-02-27 | 2018-02-27 | Praveen Singh | 7 | 7 | Done
INDEX
Completed
Working
Discussion Required
Hold

## Oct-2018
ITC ERP TASK DETAIL(Oct-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-10-01 | Blocking of back date booking for Parameters in scope of NABL: STEP-1 : Displaying of NABL Scope Column in Adding and Editing of Order in an Order Form. STEP-2 : Integration of Logic : Blocking of back date booking if any of the selected test Parameter in an particular booking is in NABL Scope at the time of booking. STEP-3 : Displaying of Message 'Order cannot be booked as Test Parameter lies in NABL Scope.' if any user try to book an order of NABL Scope Parameter in back date. | 1 | 2018-10-03 | 2018-10-03 | 2018-10-03 | Praveen Singh(Approved) | 4 | 4
2 | 2018-10-04 | In all MIS report add column of total by default. (a) Daily Booking Detail :- In the column sample amount( the amount on ehich sample is booked) system is showing zero value. (b) Party Wise Sample Count Report -Date Wise :- Total in last column (c) Party Wise Sample Count Report -Month Wise :- Total in last column (d)Sales related reports are as follows:- Sales Report Detail Daily Invoice Detail Daily sales Detail Account sales detail All reports are related to sale value therefore the sale value should be same. (e) Booking Count related reports are as follows:- Daily Booking Detail Sample Log Status TAT Report All reports are related to order booking therefore values of common fields will be same in all reports. | 2 | 2018-10-09 | 2018-10-09 | 2018-10-09 | Praveen Singh(Query) | 1 | 1
3 | 2018-10-12 | Client Feedback Point: Regarding Customer change error in Order Booking of Chennai: We booked 8 samples on the name of Interstellar Testing Centre Pvt. Ltd. Chennai on 09/10/2018 in Chennai location now i want to change the name of customer to Kwality Milk Foods LTd.( from Admin end) but system is showing error message "No Customer Invoicing type defined". Please check and update. | 3 | 2018-10-12 | 2018-10-12 | 2018-10-12 | Praveen Singh(Query) | 2 | 2 | Done
4 | 2018-10-23 | Client Feedback Point: (a) System is again considering holidays & weekly offs in expected due date of sample. Please check the logic thoroughly why it is happening again & again. I am attaching the data of pharma for reference. (b) In NABL ULR no. generation system is considering only ,'F' in 18th digit whereas in some cases 'P' is applicable. (c) User is not able to enter result in these two report no.P01-1810160102 & P01-1809080257 | 4 | 2018-10-23 | 2018-10-23 | 2018-10-23 | Praveen Singh(Query) | 1 | 1 | Done

## June-2021
ITC ERP TASK DETAIL(June-2021)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2021-05-07 | Sales Executive Names Updation /uploading in Customer Master[CSV Uploading] | 1 | 2021-06-16 | 2021-06-16 | 2021-06-16 | Praveen Singh | 2 | Done
2 | 2021-04-16 | Account hold for Existing Customers :- Step1:- Provision to upload excel having values of outstanding amount & > 90 outstanding amount Customer name,city wise on daily basis Step 2:- On every upload previous data will be replaced by new updated data. Step 3:- At the time of order booking as like new customer software will check the details of Outstanding amount for existing customers Step 4:- If customer is existing customer having outstanding value but there is no outstanding >90 days then customer will not put on hold & proceed for further stages. Step 5:- If customer is existing customer having outstanding value & also outstanding >90 days then customer will put on hold. Step 6:- Existing customer put "on Hold" will be displyed in CRM role under new tab of "Hold & UnHold Customer" tab only to those users to whom rights are given by Administrator in Employee master form as discussed. Step 7:- User will check the payment status and "Unhold" customer. Step 8 :- Provision of auto email to the user on click of Check box for "Hold" customer. Step 9:- Mail part given for existing customer hold will be different for new customer hold. Step10 :- Alert on user dashboard regarding the "hold" customers Step 11:- Maintain the category of "New " & "Existing" customer for the clarity of the user. | 2 | 2021-06-16 | 2021-06-28 | 2021-06-28 | Praveen Singh | 36 | Done
3 | 2021-04-16 | Form 39 & Form 39 A:- (a) Form 39 A is same as that of Form 39 only the difference of character"A". (b) Software has to decide which format will be shared with customer depending upon the value selected in customer master © Format to be selected is totally dependent upon Customer type defined in the customer master. Process: Master Form : Branch ,Department,Custermer type(Govt. Pvt) Type Dropdown and Report Type dropdown(Form 39 A,Form 39)-Only for Pharma Department Based on above master, Pharma Report Header will change- PDF Only WIthout form 39 - Option on Report Generation window.For only Pharma department-New Report Blade- | 3 | 2021-06-21 | 2021-06-30 | 2021-06-30 | Praveen Singh | 18 | Done
4 | 2021-06-19 | Expected and Department Due date debugging and resolution over zoom call | 4 | 2021-06-19 | 2021-06-19 | 2021-06-19 | Praveen Singh | 3 | Done
5 | 2021-06-01 | Chand Sir | 5 | 2021-06-01 | 31/06/2021 | 31/06/2021 | Chand Sir | 4 | Done
[7 empty] | Total | 63