## Nov-2018
ITC ERP TASK DETAIL(Nov-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-11-02 | Regarding provision of section incharge and NABL logo in ERP: (a) In section incharge provision how a person is able to approve reports of those instruments whose rights is not given to him. Example:- in case of Food, we have one checkbox of ALL. If we will not select that check box then no report is displayed to Indra Madam under Section Incharge role and if she selects that check box then all reports will be displayed to her. While approving one report of chemical section by default complete report is approved(if it has parameter of instrument section also).-Done (b) How a NABL logo will be applied on chennai reports when NABL logo is not incorporated in their report header.-Working On | 1 | 2018-11-02 | 2018-11-03 |  | Praveen-Singh(Approved) | 1 | 1 | Done
2 | 2018-11-02 | Regarding test master of food to be used since today: (a)Please share the list of test masters we had used since today in Food department Panchkula. | 2 | 2018-11-02 | 2018-11-02 | 2018-11-02 | Praveen-Singh(Approved) | 1 | 1 | Done
3 | 2018-11-12 | Client Feedback Point: 1.The reports approve yesterday have the same problem. The total no. of reports are as follows :- F01-1811020187, F01-1811020186 .F01-1811020181, F01-1811020163, F01-1811020160, F01-1811020148, F01-1811020147, F01-1811020146, F01-1811020145, F01-1811020144, F01-1811020143, F01-1811020128, F01-1811020127, F01-1811020126, F01-1811020117, F01-1810311583, F01-1810311582, F01-1810311581, F01-1810311578, F01-1810311574, F01-1810311572, F01-1810311571, F01-1810311559, F01-1810311553, F01-1810311540, F01-1810311539, F01-1810311538, F01-1810311535, F01-1810301524, F01-1810301523, F01-1810301520, F01-1810301519, F01-1810301518, F01-1810301517, F01-1810301516, F01-1810301514, F01-1810301511, F01-1810301506, F01-1810301470, F01-1810291449, F01-1810291402, F01-1810291397, F01-1810271360, F01-1810271355, F01-1810261327, F01-1810311579, F01-1810311573, F01-1810311567, F01-1810311558, F01-1810311557, F01-1810311556, F01-1810231150, 2.Please change the status of these samples to Invoicing from Booking. The order booking no.'s are F01-1712291460 &F01-1712291459. | 3 | 2018-11-12 | 2018-11-12 | 2018-11-12 | Praveen Singh | 2 | 2 | Done
4 | 2018-11-13 | Client feedback Points: 1)Overlaping of Report:Please rectify these reports also"- f01-18072301372, f01-18072301375, f01-18072301380, F01-18103101560, F01-18103101561, F01-18103001515 2)Regarding provision of section incharge and NABL logo in ERP:: Please update this Live server so that problem of "P" in NABL ULR no. will be resolved. | 4 | 2018-11-13 | 2018-11-13 | 2018-11-13 | Praveen Singh | 1 | 1 | Done
5 | 2018-11-27 | A)Implementation of New Test Report Right hand Side Logo in all department in Panchkula Branch: i)Food ii)Pharma iii)Water iv)Helmet v)Ayurveda vi)Building vii)Textile viii)Environment B)User Feedback Points: i)Error in editing of listed Orders due to deletion of all test parameter by the Users: i)E02-1811190107, ii)E02-1811190108, iii)E02-1811200152, iv)E02-1811200153 | 5 | 2018-11-27 | 2018-11-27 | 2018-11-27 | Praveen Singh | 4 | 4 | Done
6 | 2018-11-28 | Client Requirement(Multi Session Concept): 1.Stopping User to open New Tab in any Browser(At a time one browser) .If user opens one browser multiple time ,then in each browser only one tab. 2.Testing in multiple browser like Mozilla,Chrome etc. | 6 | 2018-11-28 | 2018-11-28 | 2018-11-28 | Praveen Singh | 4 | 4 | Done
7 | 2018-11-28 | New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(a) In case of "F" also we have to keep NABL logo optional presently it is mandatory: | 7 | 2018-11-28 | 2018-11-28 | 2018-11-28 | Praveen Singh | 6 | 6 | Done
8 | 2018-11-28 | New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(c) In case of "F" and "P", we have to define non-NABL scope parameters on the test report using '*' in front of parameter name and one remark will be printed in remark box ('*' represents test parameters not covered under NABL Scope.) | 8 | 2018-11-29 | 2018-11-30 | 2018-11-30 | Praveen Singh | 12 | 12 | Done
9 | 2018-11-28 | New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(d) The reports in which no NABL ULR no. is not defined, we have to use '*' front of all parameter category to represent non NABL scope parameters and one remark will be printed in remark box( '*' represents parameter categories not covered under NABL scope.) | 9 | 2018-12-01 | 2018-12-03 | 2018-12-03 | Praveen Singh | 12 | 12 | Done
10 | 2018-11-28 | New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(e) In case of Outsource sample we have to use '**' to represent parameters tested outside the lab. How to add provision will need discussion.(subcontract user): | 10 | 2018-12-03 | 2018-12-03 | 2018-12-03 | Praveen Singh | 7 | 7 | Done
11 | 2018-11-28 | New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(g) For every department we have to keep provision to keep limit column optional by providing check box at the time of "Approval to QA": | 11 | 2018-12-04 | 2018-12-04 | 2018-12-04 | Praveen Singh | 8 | 8 | Done

## Dec-2018
ITC ERP TASK DETAIL(Dec-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
STABILITY-MODULE
1 | 2018-12-06 | Process Flow Document and Estimation | 1 | 2018-12-06 | 2018-12-06 | 2018-12-06 | Praveen Singh | 9 | 9 | Done
2 | 2018-12-19 | Creation of Database Structure | 3 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Praveen Singh | 5 | 5 | Done
3 | 2018-12-24 | Adding of stability order Mock-up Creation | 2 | 2018-12-24 | 2018-12-24 | 2018-12-24 | Praveen Singh | 6 | 6 | Done
OTHER-MODULE
1 | 2018-12-03 | 1)User-Role-Wise : Implementation of Multi Session Script-Stopping User to Open New Tab of Software: a)Creating a provision in the administrator end to assign the multi-session condition according to their roles assigned. b)Stopping User to open New Tab in any Browser(At a time one browser) according to user role assigned in step-1.-Working On c)Testing in multiple browser like Mozilla,Chrome etc. | 1 | 2018-12-03 | 2018-12-03 | 2018-12-03 | Praveen Singh(Approved) | 6 | 7 | Done
2 | 2018-12-07 | Client Feedback Points: 1)Removal of amendment rights of Test Report from "Approval to QA" end and keeping it to "Administrator" end only. 2)Shifting of these reports to reviewing stage: i)E02-1811300218, ii)E02-1811300219, iii)E02-1811300212, iv)F02-1812040057 3)Restricting User:All parameters are removed from the sample. | 2 | 2018-12-07 | 2018-12-07 | 2018-12-07 | Praveen Singh(Query Hour) | 3 | 3 | Done |  | Maam 3 task has taken a 4 Hrs.
3 | 2018-12-11 | Regarding Credit Note / Debit Note / Account Sales Report Task: STEP-1 : CREDIT NOTE: 1)Changes on adding of credit note(Against invoice no./Against fresh ref. no.) : On inputting the Amount, system will automatically calculate the CGST-SGST/IGST/Net Amount Value according to the tax slab of Selected Customer. 2)Changes on viewing of particular Credit Note for remarks column in software Against invoice no. 3)Changes on PDF Generation of particular Credit Note for remarks column Against invoice no. 4)Viewing of particular Credit Note with remarks column in software Against fresh ref. no.(New Design Implementation) 5)PDF Generation of particular Credit Note with remarks column Against fresh ref. no. (New Design Implementation) STEP-2 : DEBIT NOTE: 1)Changes on adding of Debit Note(Against invoice no./Against fresh ref. no.) : On inputting the Amount, system will automatically calculate the CGST-SGST/IGST/Net Amount Value according to the tax slab of Selected Customer. 2)Changes on viewing of particular Debit Note for remarks column in software Against invoice no. 3)Changes on PDF Generation of particular Debit Note for remarks column Against invoice no. 4)Viewing of particular Debit Note with remarks column in software Against fresh ref. no. (New Design Implementation) 5)PDF Generation of particular Debit Note with remarks column Against fresh ref. no. (New Design Implementation) STEP-3 : MIS-REPORT: Account sales detail Report : 1)Including of Credit note date and remarks column in viewing of report in software. 2)Including of Credit note date and remarks column in excel download of report. 3)Including of Debit note date and remarks column in viewing of report in software. 4)Including of Debit note date and remarks column in excel download of report. | 3 | 2018-12-11 | 2018-12-13 | 2018-12-13 | Praveen Singh(Approved) | 16 | 20 | Done
4 | 2018-12-13 | Client Feedback Points: Shifting of below Orders to Section-Incharge to Reviewing: E02-1812030001,E02-1812030002,E02-1812030003,E02-1812030004,E02-1812040007,E02-1812040008,E02-181205002,E02-1812030005 | 4 | 2018-12-13 | 2018-12-13 | 2018-12-13 | Praveen Singh(Query) | 2 | 2 | Done
5 | 2018-12-21 | This is regarding the updation of NABL notification points in ERP uploaded on 19.12.2018, due to non-clarification of one point of NABL uploaded on 19.12.2018 it is requested to deactivate that function from live server on urgent basis from all departments. The detail of point is as below:- --Remove higlighting of non-NABL parameters using special symbol "*" and outsource parameters using "**" in all conditions. | 5 | 2018-12-21 | 2018-12-21 | 2018-12-21 | Praveen Singh(Approved) | 3 | 3 | Done

## June-2022
ITC ERP TASK DETAIL(June-2022)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Developer | Expected/Approved Hours | Status
1 | 2022-05-05 | Incorporation of Extra details in standard report template of Chennai. | 1 | 2022-06-06 | 2022-06-07 | Praveen-Singh | 8 | Done
2 | 2022-06-07 | QH -Software Updation | 2 | 2022-06-07 | 2022-06-07 | Praveen-Singh | 2 | Done
3 | 2022-06-07 | QH -Software Updation Feedback Point Resolution:All reports of Cosmetics & Others are stuck in 'Section InCharge' : QH : 1.00 Hour ¦ I have also increased the date-picker backdate selection to 300 days on Date of Start of Analysis and Date of completion of Analysis fields on tester window of all department and branches : QH : 1.00 Hour | 3 | 2022-06-08 | 2022-06-08 | Praveen-Singh | 2 | Done
4 | 2022-06-07 | QH -Software Updation Feedback Point Resolution: Issue of Cosmetics is coming in Textile also. ¦ Blank screen is coming in Cosmetics & Others in case of 'Finalizer' role. ¦ Group & Discipline is not coming in chennai food template | 4 | 2022-06-09 | 2022-06-09 | Praveen-Singh | 3 | Done
5 | 2022-05-05 | Data Updation Using Script : Provision to capture 'Date of start of analysis' & 'Date of completion of Analysis' | 5 | 2022-06-13 | 2022-06-29 | Praveen-Singh | 10 | Done
6 | 2022-05-05 | QR Code generation in all report templates : Food Department : Only In Part Wise PDF Format Report (Tested in Food Department by using any qrcode image) | 6 | 2022-06-21 | 2022-06-21 | Praveen-Singh | 7 | Done
7 | 2022-05-05 | Incorporate 'Sampler Name' in Order Booking Form/Create new role of 'Sampler' to define in Employee master | 7 | 2022-06-30 | 2022-07-04 | Praveen-Singh | 16 | Done
8 | 2022-05-05 | Incorporate Discipline & Group in Building template | 8 | 2022-07-04 | 2022-07-05 | Praveen-Singh | 8 | Done
9 | 2022-05-01 | Chand Sir | 9 | 2022-06-01 | 2022-06-30 | Chand Sir | 4 | Done
[6 empty] | Total | 60