## Feb-2019
ITC ERP TASK DETAIL(Feb-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-01-22 | STABILITY-MODULE : F) PDF Report Format of Stability Modules: | 1 | 2019-01-22 | 2019-02-04 | 2019-02-04 | Praveen Singh | 31 | 23 | Done
2 | 2019-02-16 | STABILITY-MODULE :Software Update | 2 | 2019-02-16 | 2019-02-16 | 2019-02-16 | Praveen Singh | 2 | 2 | Done
3 | 2019-02-22 | STABILITY-MODULE : Please complete the below listed task of stability module:- (a) Remove unique ness of Start Date. (b) Manual notification to the customer. | 3 | 2019-02-25 | 2019-02-27 | 2019-02-27 | Praveen Singh | 8 | 8 | Done
4 | 2019-02-22 | STABILITY-MODULE : Please complete the below listed task of stability module:- (c) Master form to define storage condition. | 4 | 2019-02-25 | 2019-02-25 | 2019-02-25 | Ruby | 3 | 2 | Done
5 | 2019-02-19 | NABL SCOPE MODULE : -Discussion with client and Praveen sir. -Checking the bug reported by client on mail and fix it. -Client discussion and fix nabl scope issue mail done by deepika ma'am. | 5 | 2019-02-19 | 2019-02-19 | 2019-02-20 | Ruby/Praveen Singh | 2 | 14 | Done

## Apr-2019
ITC ERP TASK DETAIL(Apr-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-04-03 | Remove columns Storage name and merge its value with storage condition. In product name please write sample name in place of test master name: Changes on Manual notification to the customer:- a)Remove columns Storage name and merge its value with storage condition. b)In product name please write sample name in place of test master name. c)Testing of above changes on Drish Staging Server(itc.drishinfo.com). | 1 | 2019-04-03 | 2019-04-03 | 2019-04-03 | Praveen Singh(QH) | 2 | 2 | Done
2 | 2019-04-08 | In TAT Report of MIS,after reverting any report the below should be empty: -Reviewing, -Finalizing, -Approving, -Dispatching. [ Client-word : As discussed telephonically please check the issue, when we reverting any report from any stage(invoicing,dispatching,dispatched) after approving of report then report status column in TAT report should be blank and value in all the columns(reviewing, approving,dispatching)should be blank. ] | 2 | 2019-04-08 | 2019-04-08 | 2019-04-08 | Praveen Singh(QH) | 1 | 1 | Done
3 | 2019-04-09 | Integration of back-date booking in Stability Module while converting the Stability Order to Order with listed conditional logic: If there is a admin login,then admin can select the date from date-picker and by default current date will be display. If there is a Order Booker Login,then by default only current date will be display with no date-picker option. [Client-word : As per our discussion please open back date booking for stability samples in administrator login.] | 3 | 2019-04-09 | 2019-04-09 | 2019-04-09 | Praveen Singh(QH) | 1 | 1 | Done
4 | 2019-04-09 | On PDF Generation of all Report at once in Invoice Section: On clicking the 'Generate Report' button,a popup window will open. And a popup window will have listed option: Reports without Report-To Option with Generate Button Report with Report-To Option with Generate Button 3.On Clicking the Generate button, the separate PDF will be Generated. | 4 | 2019-04-09 | 2019-04-09 | 2019-04-09 | Ruby(QH) | 2 | 3 | Done
5 | 2019-04-09 | Automation of Orders,Order Status,Reports,Invoices of Web Module | 5 | 2019-04-09 | 2019-04-30 | 2019-04-30 | Praveen Singh | 50 | 48 | Done
6 | 2019-04-11 | Documentation : Quotation/PI Module Process Flow: | 6 | 2019-04-11 | 2019-04-16 | 2019-04-16 | Praveen Singh | 16 | 12 | Done
7 | 2019-04-16 | 1)TAT-Report : Incorporation of instrument name in TAT Report 2)Expected Due Date Calculation : Please update cut off time as 4:30 in place of .01:30 in the calculation of expected due date. | 7 | 2019-04-16 | 2019-04-16 | 2019-04-16 | Praveen Singh(QH) | 1 | 1 | Done
8 | 2019-04-17 | Software Updation | 8 | 2019-04-17 | 2019-04-17 | 2019-04-17 | Praveen Singh(QH) | 1 | 1 | Done
9 | 2019-04-18 | Multiple time option to enter dispatching detail for reports & invoices | 9 | 2019-04-18 | 2019-04-18 | 2019-04-18 | Praveen Singh | 7 | 9 | Done
10 | 2019-04-22 | Inventory Module Documentation | 10 | 2019-04-22 |  |  | Praveen Singh | 24 | 12 | Shifted to May-2019 Month
11 | 2019-04-24 | ITC Web Module : Regarding Automation of Orders,Order Status,Reports,Invoices : Revised List : Changes : | 11 | 2019-04-24 | 2019-04-29 | 2019-04-29 | Praveen Singh | 32 | 34 | Done
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs

## Aug-2019
ITC ERP TASK DETAIL(Aug-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-08-01 | Scheduled MIS-TAT : Changes : | 1 | 2019-08-01 | 2019-08-07 | 2019-08-07 | Praveen Singh | 14 | 14 | Done
2 | 2019-08-02 | Regarding Customer master with executive names | 2 | 2019-08-02 | 2019-08-02 | 2019-08-02 | Praveen Singh | 1 | 1 | Done
3 | 2019-08-07 | Food Report Format for "Others" in Panchkula | 3 | 2019-08-07 | 2019-08-08 | 2019-08-08 | Praveen Singh | 5 | 5 | Done
4 | 2019-08-07 | Stability Module Formats for DSM(HTML Design) | 4 | 2019-08-08 | 2019-08-09 | 2019-08-09 | Praveen Singh | 16 | 16 | Done
5 | 2019-08-09 | Stability Module Formats for DSM : Changes : | 5 | 2019-08-09 | 2019-08-22 | 2019-08-22 | Praveen Singh | 26 | 26 | Done
6 | 2019-08-20 | Regarding Query Hour- 20.08.2019 | 6 | 2019-08-20 | 2019-08-20 | 2019-08-20 | Praveen Singh | 1 | 1 | Done
7 | 2019-08-22 | Regarding correction of Sales Executive Name Linking in MIS | 7 | 2019-08-22 | 2019-08-31 | 2019-08-31 | Praveen Singh | 28 | 28 | Done
8 | 2019-08-30 | Regarding Query Hour- 30-Aug-2019 : Saving of Booking Sample Amount at the time of Booking an Order: | 8 | 2019-08-30 | 2019-08-30 | 2019-08-30 | Praveen Singh | 2 | 2 | Done
[7 empty] | Total | 93 | 93
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs

## Sept-2019
ITC ERP TASK DETAIL(Sept-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-08-30 | QH-Query Hour-30.08.2019 | 1 | 2019-09-02 | 2019-09-02 | 2019-09-02 | Praveen Singh | 2 | 2 | Done
2 | 2019-09-03 | Software Updation | 2 | 2019-09-03 | 2019-09-03 | 2019-09-03 | Praveen Singh(QH) | 2 | 2 | Done
3 | 2019-09-04 | Urgent - Regarding Himalaya Monthly Tracker | 3 | 2019-09-04 | 2019-09-10 | 2019-09-10 | Praveen Singh | 4 | 4 | Done
4 | 2019-09-10 | Sales Related MIS-Report Validation Regarding Credit Note Amount | 4 | 2019-09-10 | 2019-09-12 | 2019-09-12 | Praveen Singh | 9 | 9 | Done
5 | 2019-09-13 | Regarding date change in Microbiologist Signature | 5 | 2019-09-13 | 2019-09-16 | 2019-09-16 | Praveen Singh | 5 | 5 | Done
6 | 2019-09-16 | Changes & Corrections required in Customer Master | 6 | 2019-09-16 | 2019-09-23 | 2019-09-23 | Praveen Singh | 25 | 25 | Done
7 | 2019-09-19 | Regarding Shifting of ITC Project to New Server and involvement with Tester | 7 | 2019-09-19 | 2019-09-24 | 2019-09-24 | Praveen Singh | 11 | 11 | Done
8 | 2019-09-21 | Integration of User Log Activity Functionality | 8 | 2019-09-23 | 2019-09-23 | 2019-09-23 | Praveen Singh | 3 | 3 | Done
9 | 2019-09-25 | Correction in Daily Sales Detail | 9 | 2019-09-25 | 2019-09-25 | 2019-09-25 | Praveen Singh | 3 | 3 | Done
10 | 2019-09-27 | Regarding Protocol Review Remarks in all departments other than Pharma | 10 | 2019-09-27 | 2019-09-27 | 2019-09-27 | Praveen Singh | 3 | 3 | Done
11 | 2019-09-27 | ITC New Server : Debugging & Optimization of the SQL Query | 11 | 2019-09-27 | 2019-09-30 | 2019-09-30 | Praveen Singh | 12 | 12 | Done
12 | 2019-09-30 | Chand Sir | 12 |  |  |  | Chand Sir | 15 | 15 | Done
[7 empty] | Total | 94 | 94
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs

## Oct-2019
ITC ERP TASK DETAIL(Oct-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-10-01 | Regarding Very-Very Urgent task of Chennai Branch | 1 | 2019-10-01 | 2019-10-04 | 2019-10-04 | Praveen-Singh | 5 | 5 | Done
2 | 2019-09-26 | Regarding issue in calculation of department due date | 2 | 2019-10-05 | 2019-10-19 | 2019-10-19 | 2019-10-19 | 16 | 16 | Done
3 | 2019-09-27 | Sales Executive List to be uploaded in LIMS | 3 | 2019-10-11 | 2019-10-11 | 2019-10-11 | Praveen-Singh(QH) | 1 | 1 | Done
4 | 2019-10-01 | ITC New Server : Debugging & Optimization of the SQL Query | 4 | 2019-10-19 | 2019-10-19 | 2019-10-19 | Praveen Singh | 17 | 16.5 | Done
5 | 2019-10-01 | Optimization of Report Landing Page according to Role Users. | 5 | 2019-10-31 | 2019-10-31 | 2019-10-31 | Praveen Singh | 5 | 5 | Done
6 | 2019-10-01 | Performance Optimization | 6 |  |  |  | Chand Sir | 45 | 45 | Done
[7 empty] | Total | 89 | 88.5
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs

## Nov-2019
ITC ERP TASK DETAIL(Nov-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2019-11-01 | Query hour- 19.10.2019 : Merging of Customer Name and Invoicing Customer Name. | 1 | 2019-11-01 | 2019-11-01 | 2019-11-01 | Praveen-Singh | 2 | 2 | Done
2 | 2019-11-08 | Software Updation | 2 | 2019-11-08 | 2019-11-08 | 2019-11-08 | Praveen Singh(QH) | 2 | 2 | Done
4 | 2019-10-18 | Regarding Chennai Report Format | 4 | 2019-11-09 | 2019-11-22 | 2019-11-22 | Praveen-Singh | 44 | 44 | Done
4 | 2019-11-25 | Software Updation | 4 | 2019-11-25 | 2019-11-25 | 2019-11-25 | Praveen Singh(QH) | 2 | 2 | Done
5 | 2019-11-30 | Chand Sir | 5 | 2019-11-30 |  |  | Chand Sir | 6 | 6 | Done
[7 empty] | Total | 56 | 56
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs

## Dec-2019
ITC ERP TASK DETAIL(Dec-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2019-11-27 | Points to be corrected-Chennai reporting | 1 | 2019-12-04 | 2019-12-12 | 2019-12-12 | Praveen-Singh | 10 | Done
2 | 2019-12-09 | Client Feedback Points: i)Addressed the error in Invoice Generation for PHRAMA Department. ii)Checked the Scheduled Mail Sending Error both in Application and Server Level with co-0rdibation with Networking Team. | 2 | 2019-12-09 | 2019-12-09 | 2019-12-09 | Praveen-Singh | 2 | Done
3 | 2019-12-13 | Software Updation | 3 | 2019-12-13 | 2019-12-13 | 2019-12-13 | Praveen Singh(QH) | 1 | Done
4 | 2019-12-12 | Regarding stack report for environment | 4 | 2019-12-12 | 2019-12-19 | 2019-12-19 | Praveen-Singh | 9 | Done
5 | 2019-12-19 | Regarding Points to be clear(9(A)+2(Q)) | 5 | 2019-12-19 | 2019-12-31 | 2019-12-31 | Praveen-Singh | 11 | Done
6 | 2019-12-01 | Chand Sir | 6 | 2019-12-31 |  |  | Chand Sir | 4 | Done
[7 empty] | Total | 37
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs

## Jan-2020
ITC ERP TASK DETAIL(Jan-2020)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2020-01-06 | Regarding Points to be clear : Client Feedback Points | 1 | 2020-01-06 | 2020-01-09 | 2020-01-09 | Praveen Singh | 3.5 | 3 | Done
2 | 2020-01-15 | Software Updation | 2 | 2020-01-15 | 2020-01-15 | 2020-01-15 | Praveen Singh | 1 | 1 | Done
3 | 2020-01-03 | Sales Report Detail- To be considered on priority | 3 | 2020-01-15 | 2020-01-28 | 2020-01-28 | Praveen Singh | 16 | 15 | Done
4 | 2020-01-27 | Regarding Chennai report formats to be incorporated in LIMS : | 4 | 2020-01-27 | 2020-01-31 | 2020-01-31 | Praveen Singh | 50 | 9 | Done
5 | 2020-01-27 | Please change approval date to 25.01.2020 from 27.01.2020(QH) | 5 | 2020-01-29 | 2020-01-29 | 2020-01-29 | Praveen Singh | 1 | 1 | Done
6 | 2020-01-28 | Rest of the invoices(QH) | 6 | 2020-01-29 | 2020-01-29 | 2020-01-29 | Praveen Singh | 1 | 1 | Done
7 | 2019-12-01 | Chand Sir | 7 | 2019-12-31 |  |  | Chand Sir | 5 | 4 | Done
[7 empty] | Total | 72.5 | 34
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs

## March-2022
ITC ERP TASK DETAIL(Mar-2022)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Developer | Expected/Approved Hours | Dev Status
1 | 2022-03-05 | Incorporate Discipline & Group in Water template | 1 | 2022-03-05 | 2022-03-07 | Praveen Singh | 8 | Done
2 | 2022-03-10 | QH : Correction of dynamic defined field for listed Order Booking nos. : F02-2203040414,F02-2203040366,F02-2203040371,F02-2203040376,F02-2203040381,F02-2203040386,F02-2203040388,F02-2203040393 & F02-2203040398 | 2 | 2022-03-10 | 2022-03-10 | Praveen Singh | 1 | Done
3 | 2022-03-11 | QH -Software Updation and Feedback Point Resolution | 3 | 2022-03-11 | 2022-03-11 | Praveen-Singh | 2 | Done
4 | 2022-03-21 | Sendinblue Process Document Study and its Implementation | 4 | 2022-03-21 | 2022-03-24 | Praveen-Singh | 7 | Done
5 | 2022-03-21 | Provision to edit GST tax slab and amount in generated invoice. | 5 | 2022-03-28 | 2022-03-31 | Praveen-Singh | 25 | Done
6 | 2022-03-21 | QH : Removal of dummy mail id from customer email addresses | 6 | 2022-03-28 | 2022-03-28 | Praveen Singh | 2 | Done
7 | 2022-03-29 | QH : Addressed the PDF Format Issue coming in below reports: O01-2202140030,P01-2203020138,P01-2203020136,P01-2203020139 & P01-2203020137 | 7 | 2022-03-29 | 2022-03-29 | Praveen Singh | 1 | Done
8 | 2022-03-01 | Chand Sir |  | 2022-03-01 | 2022-03-31 | Chand Sir | 4 | Done
[6 empty] | Total | 50