## May-2021
ITC ERP TASK DETAIL(May-2021)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2021-04-16 | PDF Report : Border issue of Discipline Wise PDF Report in Chennai Branch | 1 | 2021-05-06 | 2021-05-06 | 2021-05-06 | Praveen-Singh | 5 | Done
2 | 2021-04-16 | Credit Approval Process - The details are as below:- (a) One check box of "Credit Approval" will be provided on order booking form. (b) One selection of Check box , one pop up will be opened having values Approved by,date,Credit Period ,date upto amount will be received to be entered by order booker. © The new customers having "Credit Approval" check box selected will not put on hold and proceed for further stages. | 3 | 2021-05-14 | 2021-05-19 | 2021-05-19 | Praveen-Singh | 32 | Done
5 | 2021-05-03 | Incorporate provision of Discipline & Group in Panchkula report format of Food & Environment.(In 3 PDF Blades) | 2 | 2021-05-07 | 2021-05-12 | 2021-05-12 | Praveen-Singh | 24 | Done
7 | 2021-05-03 | Emailing for hold customers :- To - mail of customer CC- mail of person unholding the customer, Mail id of CRM & Sales Executives (Email Id of CRM will be selected Branch & Department wise) 1.Master - branch,Department,CRM Name,CRM Email, Status 2.Include email of added CRM User while sending the mail of hold to the customer.Manually email to customer on selecting the checknox window on CRM Window | 4 | 2021-05-20 | 2021-05-21 | 2021-05-21 | Praveen-Singh | 10 | Done
8 | 2021-04-16 | Chand Sir | 5 | 2021-05-01 | 2021-05-31 | 2021-05-31 | Chand Sir | 4 | Done
[7 empty] | Total | 75