## Nov-2018
ITC ERP TASK DETAIL(Nov-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-11-02 | Regarding provision of section incharge and NABL logo in ERP: (a) In section incharge provision how a person is able to approve reports of those instruments whose rights is not given to him. Example:- in case of Food, we have one checkbox of ALL. If we will not select that check box then no report is displayed to Indra Madam under Section Incharge role and if she selects that check box then all reports will be displayed to her. While approving one report of chemical section by default complete report is approved(if it has parameter of instrument section also).-Done (b) How a NABL logo will be applied on chennai reports when NABL logo is not incorporated in their report header.-Working On | 1 | 2018-11-02 | 2018-11-03 |  | Praveen-Singh(Approved) | 1 | 1 | Done
2 | 2018-11-02 | Regarding test master of food to be used since today: (a)Please share the list of test masters we had used since today in Food department Panchkula. | 2 | 2018-11-02 | 2018-11-02 | 2018-11-02 | Praveen-Singh(Approved) | 1 | 1 | Done
3 | 2018-11-12 | Client Feedback Point: 1.The reports approve yesterday have the same problem. The total no. of reports are as follows :- F01-1811020187, F01-1811020186 .F01-1811020181, F01-1811020163, F01-1811020160, F01-1811020148, F01-1811020147, F01-1811020146, F01-1811020145, F01-1811020144, F01-1811020143, F01-1811020128, F01-1811020127, F01-1811020126, F01-1811020117, F01-1810311583, F01-1810311582, F01-1810311581, F01-1810311578, F01-1810311574, F01-1810311572, F01-1810311571, F01-1810311559, F01-1810311553, F01-1810311540, F01-1810311539, F01-1810311538, F01-1810311535, F01-1810301524, F01-1810301523, F01-1810301520, F01-1810301519, F01-1810301518, F01-1810301517, F01-1810301516, F01-1810301514, F01-1810301511, F01-1810301506, F01-1810301470, F01-1810291449, F01-1810291402, F01-1810291397, F01-1810271360, F01-1810271355, F01-1810261327, F01-1810311579, F01-1810311573, F01-1810311567, F01-1810311558, F01-1810311557, F01-1810311556, F01-1810231150, 2.Please change the status of these samples to Invoicing from Booking. The order booking no.'s are F01-1712291460 &F01-1712291459. | 3 | 2018-11-12 | 2018-11-12 | 2018-11-12 | Praveen Singh | 2 | 2 | Done
4 | 2018-11-13 | Client feedback Points: 1)Overlaping of Report:Please rectify these reports also"- f01-18072301372, f01-18072301375, f01-18072301380, F01-18103101560, F01-18103101561, F01-18103001515 2)Regarding provision of section incharge and NABL logo in ERP:: Please update this Live server so that problem of "P" in NABL ULR no. will be resolved. | 4 | 2018-11-13 | 2018-11-13 | 2018-11-13 | Praveen Singh | 1 | 1 | Done
5 | 2018-11-27 | A)Implementation of New Test Report Right hand Side Logo in all department in Panchkula Branch: i)Food ii)Pharma iii)Water iv)Helmet v)Ayurveda vi)Building vii)Textile viii)Environment B)User Feedback Points: i)Error in editing of listed Orders due to deletion of all test parameter by the Users: i)E02-1811190107, ii)E02-1811190108, iii)E02-1811200152, iv)E02-1811200153 | 5 | 2018-11-27 | 2018-11-27 | 2018-11-27 | Praveen Singh | 4 | 4 | Done
6 | 2018-11-28 | Client Requirement(Multi Session Concept): 1.Stopping User to open New Tab in any Browser(At a time one browser) .If user opens one browser multiple time ,then in each browser only one tab. 2.Testing in multiple browser like Mozilla,Chrome etc. | 6 | 2018-11-28 | 2018-11-28 | 2018-11-28 | Praveen Singh | 4 | 4 | Done
7 | 2018-11-28 | New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(a) In case of "F" also we have to keep NABL logo optional presently it is mandatory: | 7 | 2018-11-28 | 2018-11-28 | 2018-11-28 | Praveen Singh | 6 | 6 | Done
8 | 2018-11-28 | New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(c) In case of "F" and "P", we have to define non-NABL scope parameters on the test report using '*' in front of parameter name and one remark will be printed in remark box ('*' represents test parameters not covered under NABL Scope.) | 8 | 2018-11-29 | 2018-11-30 | 2018-11-30 | Praveen Singh | 12 | 12 | Done
9 | 2018-11-28 | New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(d) The reports in which no NABL ULR no. is not defined, we have to use '*' front of all parameter category to represent non NABL scope parameters and one remark will be printed in remark box( '*' represents parameter categories not covered under NABL scope.) | 9 | 2018-12-01 | 2018-12-03 | 2018-12-03 | Praveen Singh | 12 | 12 | Done
10 | 2018-11-28 | New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(e) In case of Outsource sample we have to use '**' to represent parameters tested outside the lab. How to add provision will need discussion.(subcontract user): | 10 | 2018-12-03 | 2018-12-03 | 2018-12-03 | Praveen Singh | 7 | 7 | Done
11 | 2018-11-28 | New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(g) For every department we have to keep provision to keep limit column optional by providing check box at the time of "Approval to QA": | 11 | 2018-12-04 | 2018-12-04 | 2018-12-04 | Praveen Singh | 8 | 8 | Done

## Dec-2018
ITC ERP TASK DETAIL(Dec-2018)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
STABILITY-MODULE
1 | 2018-12-06 | Process Flow Document and Estimation | 1 | 2018-12-06 | 2018-12-06 | 2018-12-06 | Praveen Singh | 9 | 9 | Done
2 | 2018-12-19 | Creation of Database Structure | 3 | 2018-12-19 | 2018-12-19 | 2018-12-19 | Praveen Singh | 5 | 5 | Done
3 | 2018-12-24 | Adding of stability order Mock-up Creation | 2 | 2018-12-24 | 2018-12-24 | 2018-12-24 | Praveen Singh | 6 | 6 | Done
OTHER-MODULE
1 | 2018-12-03 | 1)User-Role-Wise : Implementation of Multi Session Script-Stopping User to Open New Tab of Software: a)Creating a provision in the administrator end to assign the multi-session condition according to their roles assigned. b)Stopping User to open New Tab in any Browser(At a time one browser) according to user role assigned in step-1.-Working On c)Testing in multiple browser like Mozilla,Chrome etc. | 1 | 2018-12-03 | 2018-12-03 | 2018-12-03 | Praveen Singh(Approved) | 6 | 7 | Done
2 | 2018-12-07 | Client Feedback Points: 1)Removal of amendment rights of Test Report from "Approval to QA" end and keeping it to "Administrator" end only. 2)Shifting of these reports to reviewing stage: i)E02-1811300218, ii)E02-1811300219, iii)E02-1811300212, iv)F02-1812040057 3)Restricting User:All parameters are removed from the sample. | 2 | 2018-12-07 | 2018-12-07 | 2018-12-07 | Praveen Singh(Query Hour) | 3 | 3 | Done |  | Maam 3 task has taken a 4 Hrs.
3 | 2018-12-11 | Regarding Credit Note / Debit Note / Account Sales Report Task: STEP-1 : CREDIT NOTE: 1)Changes on adding of credit note(Against invoice no./Against fresh ref. no.) : On inputting the Amount, system will automatically calculate the CGST-SGST/IGST/Net Amount Value according to the tax slab of Selected Customer. 2)Changes on viewing of particular Credit Note for remarks column in software Against invoice no. 3)Changes on PDF Generation of particular Credit Note for remarks column Against invoice no. 4)Viewing of particular Credit Note with remarks column in software Against fresh ref. no.(New Design Implementation) 5)PDF Generation of particular Credit Note with remarks column Against fresh ref. no. (New Design Implementation) STEP-2 : DEBIT NOTE: 1)Changes on adding of Debit Note(Against invoice no./Against fresh ref. no.) : On inputting the Amount, system will automatically calculate the CGST-SGST/IGST/Net Amount Value according to the tax slab of Selected Customer. 2)Changes on viewing of particular Debit Note for remarks column in software Against invoice no. 3)Changes on PDF Generation of particular Debit Note for remarks column Against invoice no. 4)Viewing of particular Debit Note with remarks column in software Against fresh ref. no. (New Design Implementation) 5)PDF Generation of particular Debit Note with remarks column Against fresh ref. no. (New Design Implementation) STEP-3 : MIS-REPORT: Account sales detail Report : 1)Including of Credit note date and remarks column in viewing of report in software. 2)Including of Credit note date and remarks column in excel download of report. 3)Including of Debit note date and remarks column in viewing of report in software. 4)Including of Debit note date and remarks column in excel download of report. | 3 | 2018-12-11 | 2018-12-13 | 2018-12-13 | Praveen Singh(Approved) | 16 | 20 | Done
4 | 2018-12-13 | Client Feedback Points: Shifting of below Orders to Section-Incharge to Reviewing: E02-1812030001,E02-1812030002,E02-1812030003,E02-1812030004,E02-1812040007,E02-1812040008,E02-181205002,E02-1812030005 | 4 | 2018-12-13 | 2018-12-13 | 2018-12-13 | Praveen Singh(Query) | 2 | 2 | Done
5 | 2018-12-21 | This is regarding the updation of NABL notification points in ERP uploaded on 19.12.2018, due to non-clarification of one point of NABL uploaded on 19.12.2018 it is requested to deactivate that function from live server on urgent basis from all departments. The detail of point is as below:- --Remove higlighting of non-NABL parameters using special symbol "*" and outsource parameters using "**" in all conditions. | 5 | 2018-12-21 | 2018-12-21 | 2018-12-21 | Praveen Singh(Approved) | 3 | 3 | Done

## Dec-2019
ITC ERP TASK DETAIL(Dec-2019)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2019-11-27 | Points to be corrected-Chennai reporting | 1 | 2019-12-04 | 2019-12-12 | 2019-12-12 | Praveen-Singh | 10 | Done
2 | 2019-12-09 | Client Feedback Points: i)Addressed the error in Invoice Generation for PHRAMA Department. ii)Checked the Scheduled Mail Sending Error both in Application and Server Level with co-0rdibation with Networking Team. | 2 | 2019-12-09 | 2019-12-09 | 2019-12-09 | Praveen-Singh | 2 | Done
3 | 2019-12-13 | Software Updation | 3 | 2019-12-13 | 2019-12-13 | 2019-12-13 | Praveen Singh(QH) | 1 | Done
4 | 2019-12-12 | Regarding stack report for environment | 4 | 2019-12-12 | 2019-12-19 | 2019-12-19 | Praveen-Singh | 9 | Done
5 | 2019-12-19 | Regarding Points to be clear(9(A)+2(Q)) | 5 | 2019-12-19 | 2019-12-31 | 2019-12-31 | Praveen-Singh | 11 | Done
6 | 2019-12-01 | Chand Sir | 6 | 2019-12-31 |  |  | Chand Sir | 4 | Done
[7 empty] | Total | 37
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs

## Jan-2020
ITC ERP TASK DETAIL(Jan-2020)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2020-01-06 | Regarding Points to be clear : Client Feedback Points | 1 | 2020-01-06 | 2020-01-09 | 2020-01-09 | Praveen Singh | 3.5 | 3 | Done
2 | 2020-01-15 | Software Updation | 2 | 2020-01-15 | 2020-01-15 | 2020-01-15 | Praveen Singh | 1 | 1 | Done
3 | 2020-01-03 | Sales Report Detail- To be considered on priority | 3 | 2020-01-15 | 2020-01-28 | 2020-01-28 | Praveen Singh | 16 | 15 | Done
4 | 2020-01-27 | Regarding Chennai report formats to be incorporated in LIMS : | 4 | 2020-01-27 | 2020-01-31 | 2020-01-31 | Praveen Singh | 50 | 9 | Done
5 | 2020-01-27 | Please change approval date to 25.01.2020 from 27.01.2020(QH) | 5 | 2020-01-29 | 2020-01-29 | 2020-01-29 | Praveen Singh | 1 | 1 | Done
6 | 2020-01-28 | Rest of the invoices(QH) | 6 | 2020-01-29 | 2020-01-29 | 2020-01-29 | Praveen Singh | 1 | 1 | Done
7 | 2019-12-01 | Chand Sir | 7 | 2019-12-31 |  |  | Chand Sir | 5 | 4 | Done
[7 empty] | Total | 72.5 | 34
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs

## May-2021
ITC ERP TASK DETAIL(May-2021)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2021-04-16 | PDF Report : Border issue of Discipline Wise PDF Report in Chennai Branch | 1 | 2021-05-06 | 2021-05-06 | 2021-05-06 | Praveen-Singh | 5 | 5 | Done
2 | 2021-04-16 | Credit Approval Process - The details are as below:- | 3 | 2021-05-14 | 2021-05-19 | 2021-05-19 | Praveen-Singh | 32 | 29.5 | Done
(a) One check box of "Credit Approval" will be provided on order booking form.
(b) One selection of Check box , one pop up will be opened having values Approved by,date,Credit Period ,date upto amount will be received
to be entered by order booker.
© The new customers having "Credit Approval" check box selected will not put on hold and proceed for further stages.
3 | 2021-04-16 | Account hold for Existing Customers :-
Step1:- Provision to upload excel having values of outstanding amount & > 90 outstanding amount Customer name,city wise on daily basis
Step 2:- On every upload previous data will be replaced by new updated data.
Step 3:- At the time of order booking as like new customer software will check the details of Outstanding amount for existing customers
Step 4:- If customer is existing customer having outstanding value but there is no outstanding >90 days then customer will not put on hold & proceed for further stages.
Step 5:- If customer is existing customer having outstanding value & also outstanding >90 days then customer will put on hold.
Step 6:- Existing customer put "on Hold" will be displyed in CRM role under new tab of "Hold & UnHold Customer" tab only to those users to whom rights are given by Administrator in Employee master form as discussed.
Step 7:- User will check the payment status and "Unhold" customer.
Step 8 :- Provision of auto email to the user on click of Check box for "Hold" customer.
Step 9:- Mail part given for existing customer hold will be different for new customer hold.
Step10 :- Alert on user dashboard regarding the "hold" customers
Step 11:- Maintain the category of "New " & "Existing" customer for the clarity of the user.
4 | 2021-04-16 | Form 39 & Form 39 A:-
(a) Form 39 A is same as that of Form 39 only the difference of character"A".
(b) Software has to decide which format will be shared with customer depending upon the value selected in customer master
© Format to be selected is totally dependent upon Customer type defined in the customer master.
5 | 2021-05-03 | Incorporate provision of Discipline & Group in Panchkula report format of Food & Environment.(In 3 PDF Blades) | 2 | 2021-05-07 | 2021-05-12 | 2021-05-12 | Praveen-Singh | 24 | 24 | Done
6 | 2021-05-03 | New Format of Cosmetics
7 | 2021-05-03 | Emailing for hold customers :- To - mail of customer CC- mail of person unholding the customer, Mail id of CRM & Sales Executives (Email Id of CRM will be selected Branch & Department wise) 1.Master - branch,Department,CRM Name,CRM Email, Status 2.Include email of added CRM User while sending the mail of hold to the customer.Manually email to customer on selecting the checknox window on CRM Window | 4 | 2021-05-20 | 2021-05-21 | 2021-05-21 | Praveen-Singh | 10 | 9 | Done
8 | 2021-04-16 | Chand Sir | 5 | 2021-05-01 | 2021-05-31 | 2021-05-31 | Chand Sir | 4 | 4 | Done |  |  | Chand Sir | 8 | 2020-10-01 | 2020-10-30 | 2020-10-30 | Chand Sir | 4 | 4 | Done
[7 empty] | Total | 75 | 71.5

## June-2021
ITC ERP TASK DETAIL(June-2021)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2021-05-07 | Sales Executive Names Updation /uploading in Customer Master[CSV Uploading] | 1 | 2021-06-06 | 2021-06-06 | 2021-06-06 | Praveen Singh | 2 | 2 | Done
2 | 2021-04-16 | Account hold for Existing Customers :- Step1:- Provision to upload excel having values of outstanding amount & > 90 outstanding amount Customer name,city wise on daily basis Step 2:- On every upload previous data will be replaced by new updated data. Step 3:- At the time of order booking as like new customer software will check the details of Outstanding amount for existing customers Step 4:- If customer is existing customer having outstanding value but there is no outstanding >90 days then customer will not put on hold & proceed for further stages. Step 5:- If customer is existing customer having outstanding value & also outstanding >90 days then customer will put on hold. Step 6:- Existing customer put "on Hold" will be displyed in CRM role under new tab of "Hold & UnHold Customer" tab only to those users to whom rights are given by Administrator in Employee master form as discussed. Step 7:- User will check the payment status and "Unhold" customer. Step 8 :- Provision of auto email to the user on click of Check box for "Hold" customer. Step 9:- Mail part given for existing customer hold will be different for new customer hold. Step10 :- Alert on user dashboard regarding the "hold" customers Step 11:- Maintain the category of "New " & "Existing" customer for the clarity of the user. | 2 | 2021-06-16 | 2021-06-28 | 2021-06-28 | Praveen Singh | 36 | 30.5 | Done
3 | 2021-04-16 | Form 39 & Form 39 A:- (a) Form 39 A is same as that of Form 39 only the difference of character"A". (b) Software has to decide which format will be shared with customer depending upon the value selected in customer master © Format to be selected is totally dependent upon Customer type defined in the customer master. Process: Master Form : Branch ,Department,Custermer type(Govt. Pvt) Type Dropdown and Report Type dropdown(Form 39 A,Form 39)-Only for Pharma Department Based on above master, Pharma Report Header will change- PDF Only WIthout form 39 - Option on Report Generation window.For only Pharma department-New Report Blade- | 3 | 2021-06-21 | 2021-06-30 | 2021-06-30 | Praveen Singh/Ruby | 18 | 17 | Done
4 | 2021-05-03 | New Format of Cosmetics
5 | 2021-05-03 | Auto mailing on expected due date change popup window on Job Sheet Print.Enabling the right for CRM Role for accessing the Job Sheet Window on Scheduling Menu
6 | 2021-06-19 | Expected and Department Due date debugging and resolution over zoom call | 4 | 2021-06-19 | 2021-06-19 | 2021-06-19 | Praveen Singh | 3 | 3 | Done
7 | 2021-06-30 | Chand Sir | 5 | 2021-06-01 | 2021-06-30 | 2021-05-31 | Chand Sir | 4 | 4 | Done |  |  | Chand Sir | 8 | 2020-10-01 | 2020-10-30 | 2020-10-30 | Chand Sir | 4 | 4 | Done
[7 empty] | Total | 63 | 56.5

## May-2022
ITC ERP TASK DETAIL(May-2022)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Developer | Expected/Approved Hours | Dev Status
1 | 2022-05-05 | QH : Modification : Sample Detail Design Modification : Test Report Template - Form 39 ,Cos -24 & Form 50 | 1 | 2022-05-05 | 2022-05-05 | Praveen-Singh | 1 | Done
2 | 2022-05-05 | Provision to capture 'Date of start of analysis' & 'Date of completion of Analysis' | 2 | 2022-05-18 |  | Praveen-Singh | 40 | Done
3 | 2022-05-05 | Pharma Back Date Booking Issue | 3 | 2022-05-25 | 2022-05-25 | Praveen-Singh | 2 | Done
4 | 2022-05-05 | Confirmation in cut off time for +1 Day addition in Expected Due Date & Department Due - Either 02:00 Pm or 04:00 pm.(+1 is not added in department due date calculation if sample is booking after cut off time): | 4 | 2022-05-25 | 2022-05-25 | Praveen-Singh | 5 | Done
5 | 2022-05-05 | Recalculation of Expected Due Date & Department Due Date on addition of parameter from 'Scheduling- Job sheet Print' | 5 | 2022-05-26 | 2022-05-26 | Praveen-Singh | 4 | Done
6 | 2022-05-05 | Test Parameter Master - Provision to enable or disbale text editor.By default it should be disabled. | 6 | 2022-05-27 | 2022-05-27 | Praveen-Singh | 7 | Done
7 | 2022-05-05 | Provision to display NABL scope against parameter in section incharge | 7 | 2022-05-30 | 2022-05-30 | Praveen-Singh | 8 | Done
8 | 2022-05-01 | Chand Sir | 8 | 2022-05-01 | 2022-05-31 | Chand Sir | 3 | Done
[6 empty] | Total | 70