## Oct-2021
ITC ERP TASK DETAIL(Oct-2021)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2021-04-09 | Back date provision in 'Others' department of Chennai branch | 1 | 2021-10-05 | 2021-10-06 |  | Praveen Singh | 6 | Done
2 | 2021-04-10 | Queries resolution after software Update(Query Hours) | 2 | 2021-10-05 | 2021-10-05 |  | Praveen Singh | 2 | Done
3 | 2021-10-06 | API Creation : Invoice Data of LIMS for Tally Package | 3 | 2021-10-06 | 2021-10-06 |  | Praveen Singh | 2 | Done
4 | 2021-04-09 | Nabl New Logo Implementation in Test Report. | 4 | 2021-10-07 | 2021-10-13 |  | Praveen Singh | 16 | Done
5 | 2021-10-11 | Change in provision of Authorized signatory in Food-Panchkula report template | 5 | 2021-10-18 | 2021-10-28 |  | Praveen Singh | 36 | Done
6 | 2021-10-11 | Format of Pesticide Residue -Apeda available in Food Chennai to be cloned in Pharma-Chennai | 6 | 2021-10-29 | 2021-11-01 |  | Praveen Singh | 16 | Done
7 | 2021-10-01 | Chand Sir | 7 | 2021-10-01 | 2021-10-30 |  | Chand Sir | 6 | Done
[7 empty] | Total | 84