## March-2018
ITC ERP TASK DETAIL(March-2018)
S.No. | Date | Detail | Priority | Exp.Due Date | Rect. Date | Developer | Expected Hours | Actual Hours | Dev Status | Tester Status | Remarks
1 | 2018-01-03 | Ayurvedic Order Process Changes on listed Stages On Web and PDF View: 1.Reviewer:User Name and Signature Updation and Removal of NABL located just below the Logo. 2.Finalizer:User Name and Signature Updation and Removal of NABL located just below the Logo. 3.Approval:User Name and Signature Updation and Removal of NABL located just below the Logo. | 1 | 2018-03-05 | 2018-03-05 | Pratyush | 9 | 9 | Done
2 | 2018-01-03 | Building Order Process Changes on listed Stages On Web and PDF View: 1.Reviewer:User Name and Signature Updation and Removal of NABL located just below the Logo. 2.Finalizer:User Name and Signature Updation and Removal of NABL located just below the Logo. 3.Approval:User Name and Signature Updation and Removal of NABL located just below the Logo. | 2 | 2018-03-05 | 2018-03-05 | Pratyush | 8 | 8 | Done
3 | 2018-01-03 | User Assigned Department Wise in Scheduling | 3 | 2018-03-01 | 2018-03-01 | Praveen Singh | 9 | 9 | Done
4 | 2018-01-03 | Switching of User Role | 4 | 2018-03-05 | 2018-03-05 | Praveen Singh | 8 | 8 | Done
5 | 2018-01-03 | Creation and Uploading of Pharma Master on Live Server: | 5 | 2018-03-08 | 2018-03-08 | Praveen Singh | 28 | 27 | Done
6 | 2018-05-03 | In all departments, reviewing date will be the current date and report finalization date and report approval to QA date will also be the current date irrespective of report review date. | 6 | 2018-03-07 | 2018-03-07 | Ruby | 12 | 10 | Done
7 | 2018-05-03 | Testing of Switching of User Role(Task shifted due to Pharma-Master-Uploading) | 7 | 2018-03-06 | 2018-03-06 | Pratyush | 9 | 9 | Done
8 | 2018-05-03 | Report Ammendment- Option to type report ammenment no on the reviewer window and suffix 'A' should be added on the end of report and Date of reviewing and Date of Completion will be the current date. (a) In the reviewing level, Reviewer have option to add "A" at the end of report no. (b) In the case of ammended report, Date of completion will be the date of reviewing. | 8 | 2018-03-08 | 2018-03-12 | Ruby | 18 | 18 | Done
9 | 2018-05-03 | We should Save copy of previous report and ammended report in the system.
10 | 2018-07-03 | Dispatcher Permission to Print an report. | 9 | 2018-03-07 | 2018-03-07 | Pratyush | 8 | 8 | Done
11 | 2018-07-03 | Software Updation | 24 | 2018-03-07 | 2018-03-07 | Praveen Singh | 2 | 2 | Done
12 | 2018-08-03 | Party Ref Date/Letter Date on Ayurvedic Reports | 10 | 2018-03-08 | 2018-03-08 | Pratyush | 8 | 8 | Done
13 | 2018-09-03 | User Manual Creation-Order and Master Creation | 11 | 2018-03-12 | 2018-03-12 | Pratyush | 18 | 18 | Done
14 | 2018-09-03 | Users Feedback Points regarding: 1.Invoicing-Food: i.Re-creation of Invoice ii.Amendment of Invoice 2.Report Format-Ayurvedic 3.Test Parameter Updation-Pharma: i.Method should be Null ii.Claim Dependent should be Zero | 12 | 2018-03-09 | 2018-03-09 | Praveen-Singh | 8 | 8 | Done
15 | 2018-12-03 | Calculation of Calim Value for Alpha-numeric Value. | 13 | 2018-03-12 | 2018-03-12 | Praveen Singh | 8 | 7 | Done
16 | 2018-12-03 | Displaying of dispatched detail in Invocier and Dispatcher | 14 | 2018-03-13 | 2018-03-13 | Pratyush | 8 | 8 | Done
17 | 2018-12-03 | Displaying of Product Master Name in a Product Master Alias in State-Wise-Product and Customer-Wise-Product Invocing | 15 | 2018-03-13 | 2018-03-14 | Ruby | 8 | 10 | Done
18 | 2018-12-03 | ENV Report PDF Change:Requirement Label Changes in case of IS:10500 Test Standard in Environment Test Report.If Test Standard is IS:10500,then add 'Acceptable Limit-Permissible Limit in absence of alternative Source' with Label Requirement. | 16 | 2018-03-13 | 2018-03-13 | Praveen Singh | 8 | 8 | Done
19 | 14-03-2018 | Displaying of Party Ref. No on Order Process Stage of Ayurvedic Department | 17 | 2018-03-14 | 2018-03-14 | Ruby | 8 | 8 | Done
20 | 14-03-2018 | Customer-wise-Parameter Rates Updation | 18 | 2018-03-14 | 2018-03-14 | Pratyush | 8 | 8 | Done
21 | 14-03-2018 | Uploading of Invoicing Rate of State-wise Invoicing Structure in Pharma Deparment | 19 | 2018-03-14 | 2018-03-14 | Praveen Singh | 8 | 8 | Done
22 | 15-03-2018 | Microbiological Signature on Ayurvedic Report | 20 | 2018-03-15 | 2018-03-15 | Pratyush | 8 | 8 | Done
23 | 15-03-2018 | New Report Format Implementation on Environment Report Template regarding General Parameter seperation | 21 | 2018-03-19 | 2018-03-19 | Ruby | 16 | 16 | Done
24 | 15-03-2018 | Dispalying of Customer-name with Cityname in Submitted By Field in Pharma Test Report | 23 | 2018-03-15 | 2018-03-15 | Praveen Singh | 3 | 3 | Done
25 | 15-03-2018 | Uploading of Invoicing Rate-Customer-Wise-Product Invoicing Structure in Pharma Deparment and Addressing of User Feedbacks. | 22 | 2018-03-16 | 2018-03-16 | Praveen Singh | 13 | 13 | Done
26 | 15-03-2018 | In Pharma backdate Booking, Review date will be the default date for further Order Process Stage .i.e in datepicker of Finalizer and Approval. Remove all dates from Finalizer and Approval Signature | 24 | 2018-03-16 | 2018-03-16 | Pratyush | 8 | 8 | Done
27 | 15-03-2018 | Rounding of Standard value from and Standard value to according to Standard Value Type ie Numeric,Alphanumeric,NA in all Departments | 26 | 2018-03-17 | 2018-03-17 | Pratyush | 8 | 8 | Done
28 | 15-03-2018 | Uploading of Invoicing Rate-Customer-Wise-Parameter Invoicing Structure in Pharma Deparment and Addressing of User Feedbacks. | 27 | 2018-03-17 | 2018-03-17 | Praveen Singh | 9 | 9 | Done
29 | 16-03-2018 | Creation of Food Staging Server for Chennai Team | [6 empty] | Moved to April 2018
30 | 19-03-2018 | MIS Report: Daily Invoicing Report as Excel Format | 28 | 2018-03-20 | 2018-03-20 | Pratyush | 16 | 16 | Done
31 | 19-03-2018 | Cloning of Order Booking as New Order using Save as Option | 29 | 2018-03-20 | 2018-03-20 | Praveen Singh | 12 | 12 | Done
32 | 20-03-2018 | Integration of Invoice Number in Credit and Debit Note of Payment Module. | 30 | 2018-03-21 | 2018-03-21 | Ruby | 8 | 8 | Done
33 | 20-03-2018 | Displaying of Batch No with search in Order Listing and option to refresh the Invoicing Structure at the time of Booking | 31 | 2018-03-21 | 2018-03-21 | Praveen Singh | 5 | 5 | Done
34 | 21-03-2018 | Creation of Detector Master according to Equipment. | 32 | 2018-03-21 | 2018-03-21 | Ruby | 5 | 5 | Done
35 | 21-03-2018 | Test Master Creation(Step-2)-Option to Select Detector in selectbox | 33 | 2018-03-23 | 2018-03-23 | Ruby | 8 | 8 | Done
36 | 21-03-2018 | New Invoicing Structure : Customer Wise Assay Parameter-Option for adding of rates using new Customer Wise Assay Parameter form | 34 | 2018-03-24 | 2018-03-24 | Praveen Singh | 24 | 20 | Done
37 | 21-03-2018 | Creation of Test Master for Partial Report and Part-Wise Report | 37 | 2018-03-23 | 2018-03-23 | Pratyush | 16 | 15 | Done
38 | 2018-04-01 | Software Updation | 38 | 2018-03-22 | 2018-03-22 | Praveen Singh | 2 | 2 | Done
39 | 21-03-2018 | Customer Wise Assay Parameter integration with Order Booking Form-Option to enter running time as combo box and no of Injection as Input.Also allow user to book an order only if rate is available. | 35 |  |  |  | 16 |  | Moved to April Task List
40 | 21-03-2018 | Customer Wise Assay Parameter integration with generation of Invoice | 36 | [5 empty] | Moved to April Task List
41 | 22-03-2018 | Users Feedback Points(Approval and Invoicing): 1.Invoicing- Amendment of Invoice. 2.Approval - Report Format Change in Environment / Water Department(General Information and Observation) | 39 | 2018-03-22 | 2018-03-22 | Praveen Singh | 2 | 2 | Done
42 | 23-03-2018 | Allowing Order Booking with checking the Invoicing in case of Pharma Department in Customer-wise-Parameter Invoicing and Addressing of User Feedback Points | 40 | 2018-03-23 | 2018-03-23 | Praveen Singh | 3 | 3 | Done
43 | 23-03-2018 | Report Changes in Ayurvedic Department listed in a Hard Copy | 41 | 2018-03-23 | 2018-03-28 | Pratyush | 9 | 11 | Done
44 | 23-03-2018 | Department wise Mail Body Intergration changes | 42 | 2018-03-26 | 2018-03-26 | Pratyush | 8 | 8 | Done
45 | 24-03-2018 | Invoicer should able to take a print out of report | 43 | 2018-03-27 | 2018-03-30 | Pratyush | 8 | 8 | Done
46 | 24-03-2018 | All department Except Food : There sholud be a provision to send the report with equipment & Without equipment at the the time of finalization by Finalizer and Dispatcher for printing | 44 | 2018-03-27 | 2018-03-28 | Ruby | 16 | 16 | Done
47 | 28-03-2018 | Meeting and discussion with Client. | 46 | 28-03-2018 | 28-03-2018 | Praveen Singh | 4 | 4 | Done
48 | 28-03-2018 | Pharma User Feedback Points: 1.Fixed Rates displaying Issue. 2.Displaying of sample according to the saved Invoicing Rate in case of Pharma department in Customer Wise Product Invoicing. 3.Limit having ? Mark. 4.Invoicing Error on editing of Orders 5.Header and footer Notes dissappears on displaying Invoicing Erroe at the time of Booking. 6.After Dispatched, the order again standing for Invoicing with amendment. | 45 | 2018-03-29 |  | Praveen Singh | 16 | 14 | Done
49 | 29-03-2018 | Report PDF Format : Error to be Checked - In Order Booking Form if supplied by & manufactured by is blank then on final report Part A system automatically keep submitteb by col. blank. | 47 | 2018-03-29 | 2018-03-30 | Ruby | 3 | 3 | Done
50 | 29-03-2018 | Duplicacy Check- Order Booking Form :- if a sample of particular batch for a corresponding client already exists then then system will display a warning message to the user having the previous order booking date and order no and asked for permission of user to proceed for booking ,. If user press "Yes" then booking will be continued and if user select "No" then booking will not be proceed.
51 | 30-03-2018 | Error to be checked :- The sorting of parameter(top & down) is not functioning properly. | 49 | 2018-03-30 | 2018-03-30 | Ruby | 4 | 4 | Done
52 | 30-03-2018 | In Scheduling,Job sheet print if user want to leave one col. of of standard value from & to blank then system is not allowing to do that.And Provision to Update Standard Value Type also | 50 | 2018-03-31 | 2018-03-31 | Ruby | 8 | 8 | Done
53 | 30-03-2018 | Testing of Order Booking in case of Customer Wise Product/Fixed Rate Invoicing Structure. | 51 | 2018-03-30 | 2018-03-30 | Pratyush | 8 | 8 | Done
54 | 30-03-2018 | Pharma User Feedback Points: 1.Booking Date and Booking Code Changes. 2.Reporting Date and Reporting Code Changes. 3.Invoicing Type and invoicing rate modification. | 52 | 2018-03-30 | 2018-03-30 | Praveen Singh | 5 | 5 | Done
55 | 28-03-2018 | Meeting and discussion with Client regarding Scope-2 Document | 53 | 2018-03-30 | 2018-03-30 | Praveen Singh | 2 | 2 | Done
56 | 31-03-2018 | Software Updation | 54 | 2018-03-31 |  | Praveen Singh | 2 | 2 | Done
57 | 31-03-2018 | Ayurvedic Report Format Implementation(New Changes) 1.Sample Information Detail 2.View Level changes on all Stages. 3.PDF Report Format Changes. 4.Removal of Date of Completion 5.Page Setup. | 55 | 2018-03-31 | 2018-03-31 | Pratyush | 8 | 8 | Done
58 | 31-03-2018 | Clearance of Invoicing Issues of all Department | 54 | 2018-03-31 |  | Praveen Singh | 6 | 6 | Done
INDEX
Completed
Working
Discussion Required
Hold
Moved

## July-2021
ITC ERP TASK DETAIL(July-2021)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 14.07.2021 | NABL Symbol coming in Form 50 under Cosmetics department is not proper. | 1 | 2021-07-21 | 2021-07-21 | 2021-07-21 | Praveen Singh | 1 | Done
2 | 14.07.2021 | Disclaimer to be revised : Refer below details- Designing issue in final pdf template 1. The report is only for the sample tested. 2. Total liability of ITC Labs is limited to invoiced amount. 3. The test report shall not be reproduced except in full without the written approval of the laboratory. 4. If samples not consumed during analysis, it will be stored and retain as per company policy. 5. Samples not withdrawn by us unless otherwise stated. 6. Test report in full or parts shall not be used for promotional or publicity purposes. 7. Legal disputes are subjected to Panchkula Jurisdiction only | 2 | 2021-07-22 | 2021-07-24 | 2021-07-24 | Praveen-Singh | 4 | Done
3 | 14.07.2021 | Company Address: To be represented as given below Interstellar Testing Centre Pvt. Ltd. 86, Industrial Area, Phase-I, Panchkula-134109 (Haryana) Phone: (O) 0172-2561543, 2565825 E-mail: customersupport@itclabs.com Visit us: www.itclabs.com | 3 | 2021-07-24 | 2021-07-24 | 2021-07-24 | Praveen-Singh | 2 | Done
4 | 14.07.2021 | As discussed the sample condition is one of the requirement of ISO 17025-Make it mandatory in order booking and display in Reviewing & Final pdf templates of Food,Environment,Building,Cosmetics,Helmet,Technical Pesticides,Water under Sample Name in Sample Information Part A | 7 | 2021-07-30 | 2021-07-30 | 2021-07-30 | Praveen-Singh | 24 | Done
5 | 14.07.2021 | Data to be enter in Test Standard in Order Booking(Routine Analysis,Method Validation & Verification,Shelf Life Study) In case of stability booking software will automatically displaye value in drop down list. In case of method validation & verification software will ask for the rate of sample to be entered by order booker. Points: Make this field required Display the Sals Report Detail - default value 'Routine Analysis'(1 yrs). In case of Stablility Order- Display the Stability Study related Option in dropdown In case of method validation & verification software will ask for the sample amount (Input Type*) to be entered by order booker. Rename the dropdown lebel as 'Analysis Type'.It will replace the sample amount with order booker entered amount.It will be placed after TAT Days. Updating records for 1 year in order booking table with default value 'Routine Analysis' if defined standard is NULL | 8 | 2021-07-28 | 2021-07-28 | 2021-07-28 | Praveen-Singh | 15 | Done
6 | 14.07.2021 | Value of Test Standard entered in order booking will be displayed in Invoicer Dashboard as a new column. Point : Displaying of Analysis Type on Invoice Generation Window Under Reports for Invoicing. | 4 | 2021-07-24 | 2021-07-24 | 2021-07-24 | Praveen-Singh | 2 | Done
7 | 14.07.2021 | Incorporate Test Standard column in Daily Booking Detail Daily Book detail - Adding of New Colum 'Defined Tested Standard' | 5 | 2021-07-24 | 2021-07-24 | 2021-07-24 | Praveen-Singh | 2 | Done
8 | 05.03.2021 | Auto mailing on expected due date change popup window on Job Sheet Print.Enabling the right for CRM Role for accessing the Job Sheet Window on Scheduling Menu Change in Expected Due Date Popup Reason of Change Checkbox for auto mail Expected Due Date will never change after date is passed from the currrent date/Meand It should be less than and deaual to Current Date, then user will able to change it | 6 | 2021-07-24 | 2021-07-27 | 2021-07-27 | Praveen-Singh | 12 | Done
[7 empty] | Total | 62