## Nov-2020
ITC ERP TASK DETAIL(Nov-2020)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Time Spent | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2020-11-05 | Query Hour : Sales Report Detail- To be considered on priority | 1 | 2020-11-05 | 2020-11-05 | 2020-11-05 | Praveen SIngh | 2 | 2 | Done
2 | 2020-11-09 | Regarding round off of requirement column | 2 | 2020-11-11 | 2020-11-11 | 2020-11-11 | Praveen Singh | 3 | 3 | Done
3 | 2020-11-09 | Outsource sample ** remark point in Test Report | 3 | 2020-11-13 | 2020-11-23 | 2020-11-23 | Praveen Singh | 8 | 8 | Done
4 | 2020-11-09 | Sales Executive Names Updation in Customer Master | 4 | 2020-11-20 | 2020-11-20 | 2020-11-20 | Praveen Singh | 2 | 2 | Done
5 | 2020-11-09 | Employee Sales Target Report | 5 | 2020-11-23 |  |  | Praveen Singh | 24 | 45 | In-progress | 24 Hrs spent and remaining hours moved in next month
6 | 2020-11-01 | Chand Sir | 6 | 2020-11-30 | 2020-11-30 | 2020-11-30 | Chand Sir | 4 |  | Done
[7 empty] | Total | 43