## Sept-2020
ITC ERP TASK DETAIL(Sept-2020)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2020-08-14 | Regarding updation of sales executive names in LIMS | 1 | 2020-09-01 | 2020-09-07 | 2020-09-07 | Praveen Singh | 21 | Done
2 | 2020-09-07 | Sales Executive Names Updation in Customer Master | 2 | 2020-09-07 | 2020-09-07 | 2020-09-07 | Praveen Singh | 1 | Done
3 | 2020-09-07 | Budget File Updation in Master Form | 3 | 2020-09-07 | 2020-09-07 | 2020-09-07 | Praveen Singh | 8 | Done
4 | 2020-09-07 | Adding of Product Category and Sub category in Daily Sales Detail | 4 | 2020-09-11 | 2020-09-11 | 2020-09-11 | Praveen Singh | 2 | Done
5 | 2020-09-07 | EIC Report Format Implementation | 5 | 2020-09-14 | 2020-09-29 | 2020-09-29 | Praveen Singh | 45 | Done
6 | 2020-08-31 | Chand Sir | 6 | 2020-09-01 | 2020-09-30 | 2020-09-30 | Chand Sir | 3 | Done
[7 empty] | Total | 80