## Aprl-2020
ITC ERP TASK DETAIL(April-2020)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2020-01-03 | Sales Report Detail- To be considered on priority | 1 | 2020-04-07 | 2020-04-07 | 2020-04-07 | 12 | Done
2 | 2020-04-09 | Regarding new task of Employee Sales Target | 2 | 2020-04-09 | 2020-04-10 | 2020-04-10 | 10 | Done
3 | 2020-04-13 | Regarding new task -Deactivation provision of duplicacy in Master-Tests Tab | 3 | 2020-04-13 | 2020-04-16 | 2020-04-16 | 18 | Done
4 | 2020-04-16 | Invoices : Correction & Shifting og Invoice Dates : | 4 | 2020-04-18 | 2020-04-20 | 2020-04-20 | 3 | Done
5 | 2019-12-01 | Chand Sir | 5 | 2020-02-01 |  |  | 3 | Done
[6 empty] | Total | 46
INDEX
Hrs | Hours
A | Approval
QH | Query Hrs