## Dec-2020
ITC ERP TASK DETAIL(Dec-2020)
S.No. | Date | Detail | Priority | Start Date | Exp.Due Date | Rect. Date | Developer | Expected/Approved Hours | Dev Status | Tester Status | Remarks
1 | 2020-11-09 | Employee Sales Target Report | 1 | 2020-12-31 | 2020-12-31 | 2020-12-31 | Praveen Singh | 21 | Done
2 | 2020-11-09 | APEDA Format-Debugging | 2 | 2020-12-18 | 2020-12-18 | 2020-12-18 | Praveen Singh | 2 | Done
3 | 2020-11-09 | Regarding result of Pesticide Residue category to be replicated on selection of Copy Button | 3 | 2020-12-22 | 2020-12-22 | 2020-12-22 | Praveen Singh | 3 | Done
4 | 2020-11-09 | Uploading Regulation data from back end | 4 | 2020-12-19 | 2020-12-19 | 2020-12-19 | Praveen Singh | 10 | Done
5 | 2020-11-09 | APEDA Format - Dynamic Fields alignment change in PDF template | 5 | 2020-12-25 | 2020-12-25 | 2020-12-25 | Praveen Singh | 2 | Done
6 | 2020-12-01 | Chand Sir | 6 | 2020-12-01 | 2020-12-31 | 2020-12-31 | Chand Sir | 4 | Done
[7 empty] | Total | 42