## Todos
ITC ERP Panchkula (ERP)
Created By : Praveen Singh
Name | Description | Assigned To | Due Date | Date Completed | Status
Praveen-Singh : Regarding Implementation of NABL-133 : | (b) Regarding Implementation of NABL-133 with respect to separate Test Reports for accredited &amp; non-accredited parameters,for this i will share the process flow and estimation in separate mail as per our discussion.STEPS: Changes on Reviewing Stage of Order Process: Displaying of two report no's infront of main report No. Format : Main Report No.(1)(2) if Test parameter lies in both nabl scope and non-nabl Scope. Main Report No. if Test parameter has only lies in nabl scope. Changes on Report Generation Popup Window: Displaying of Checkbox for accredited Report if all Test parameter has NABL scope Displaying of Checkboxes for accredited &amp; non-accredited Report if Test parameter lies in both nabl scope and non-nabl Scope. Creation of Logic for Generation of listed Reports: Accredited Report if all Test parameter has NABL scope Accredited &amp; Non-accredited Report if Test parameter lies in both nabl scope and non-nabl Scope. Generation of PDF Templates for listed Criteria: Accredited if all Test parameter has NABL scope Format : Main Report No. Generation of nabl no. Accredited &amp; Non-accredited if Test parameter lies in both nabl scope and non-nabl Scope. Format 1: Main Report No.(1) and having Test parameter in nabl scope and Generation of nabl no. Format 2: Main Report No.(2) and having Test parameter in non-nabl scope and without nabl no. Uploading and Testing of above points on ITC Staging Server | Praveen Kumar Singh | 2020-07-01 | 2020-07-01 | Completed
Ruby : Testing of NABL-133 : | (b) Regarding Implementation of NABL-133 with respect to separate Test Reports for accredited &amp; non-accredited parameters,for this i will share the process flow and estimation in separate mail as per our discussion.STEPS: Changes on Reviewing Stage of Order Process: Displaying of two report no's infront of main report No. Format : Main Report No.(1)(2) if Test parameter lies in both nabl scope and non-nabl Scope. Main Report No. if Test parameter has only lies in nabl scope. Changes on Report Generation Popup Window: Displaying of Checkbox for accredited Report if all Test parameter has NABL scope Displaying of Checkboxes for accredited &amp; non-accredited Report if Test parameter lies in both nabl scope and non-nabl Scope. Creation of Logic for Generation of listed Reports: Accredited Report if all Test parameter has NABL scope Accredited &amp; Non-accredited Report if Test parameter lies in both nabl scope and non-nabl Scope. Generation of PDF Templates for listed Criteria: Accredited if all Test parameter has NABL scope Format : Main Report No. Generation of nabl no. Accredited &amp; Non-accredited if Test parameter lies in both nabl scope and non-nabl Scope. Format 1: Main Report No.(1) and having Test parameter in nabl scope and Generation of nabl no. Format 2: Main Report No.(2) and having Test parameter in non-nabl scope and without nabl no. Uploading and Testing of above points on ITC Staging Server | Ruby | 2020-07-02 | 2020-07-02 | Completed
Praveen-Singh : Back date provision of Building : Sample,Order and Report Number generation in Back Date Booking : | Description [4 Hrs] Sample,Order and Report Number generation in Back Date Booking: STEPS: Sample Number Generation: Generation of Sample Number on daily basis for Pharma and Building department. Order Number Generation: Generation of Order Number on daily basis for Pharma and Building department. Report Number Generation: Generation of Report Number on daily basis for Pharma and Building department. Uploading and Testing of above points on ITC Staging Server | Praveen Kumar Singh | 2020-07-04 | 2020-07-04 | Completed
Praveen-Singh : In continuation of NABL 133 task : Order confirmation mail template : | Description : [6 Hrs] STEPS: Adding of below text in Order Confirmation Mail Template Body in listed department: ["Separate Test Report will be issued for non accredited test parameters, which are marked with (*). This is in accordance of revised NABL Guideline NABL-133 (5.1) effective from 01-July-2020"] Food Pharma Water Helmet Ayurveda Building Textile Environment Cosmetics Testing of above points on listed server: Staging Server Live Server | Praveen Kumar Singh | 2020-07-07 | 2020-07-07 | Completed
Ruby : In continuation of NABL 133 task : Order confirmation mail template : | Description : [8 Hrs] STEPS: Highlighting of Accredited/Non-accredited NABL Scope on Order Confirmation Mail Templates PDF in listed department: Food Pharma Water Helmet Ayurveda Building Textile Environment Cosmetics Testing of above points on listed server: Staging Server Live Server | Ruby | 2020-07-08 | 2020-07-08 | Completed
Praveen-Singh : ITC CUSTOMER PORTAL && Software Updation : | Description:[1.00 Hrs] Software Updation: a)Updated Code on Drish Live Server from SVN b)Updated DB on Drish Live Server c)Updated Code on Drish Dev Staging Server from SVN d)Updated DB on Drish Dev Staging Server e)Updated Code on ITC Dev Staging Server from SVN f)Updated DB on ITC Dev Staging Server g)Created the Software Package for Live Server Updation. | Praveen Kumar Singh | 2020-07-14 | 2020-07-14 | Completed
Praveen Singh: Regarding General Information in Environment Report : | Description : [16 Hrs] STEPS: Creation of Logic for Generation of listed Reports: Accredited Report if all Test parameter has NABL scope Accredited &amp; Non-accredited Report if Test parameter lies in both nabl scope and non-nabl Scope. Generation of PDF Templates for listed Criteria: Accredited if all Test parameter has NABL scope Accredited &amp; Non-accredited if Test parameter lies in both nabl scope and non-nabl Scope. Format 1: Main Report No.(1) and having Test parameter in nabl scope and Generation of nabl no. Format 2: Main Report No.(2) and having Test parameter in non-nabl scope and without nabl no. Uploading and Testing of above points on ITC Staging Server Uploading and Testing of above points on ITC Live Server | Praveen Kumar Singh | 2020-08-13 | 2020-08-13 | Completed
Praveen-Singh : Back date provision of Building : Sample,Order and Report Number generation in Back Date Booking : Changes : | Description [1 Hrs] Sample,Order and Report Number generation in Back Date Booking: STEPS: Sample Number Generation: Generation of Sample Number on daily basis for Pharma and Building department. Order Number Generation: Generation of Order Number on daily basis for Pharma and Building department. Report Number Generation: Generation of Report Number on daily basis for Pharma and Building department. Uploading and Testing of above points on ITC Staging Server | Praveen Kumar Singh | 2020-08-13 | 2020-08-13 | Completed
Ruby : Query Hours : Point(d) : | Description : [2 Hrs] STEPS: (d) In Order confirmation mail template system is not highlighting non-accredited parameters with "*". Please check.(point given in NABL 133) Testing of above points on listed server: Staging Server Live Server | Ruby | 2020-08-12 | 2020-08-12 | Completed
Praveen-Singh : Query Hours : Point (a) & (c) : | Description : [4 Hrs] The details are as follows:- (a) Please help to change product batch no. in stability protocol no. P01-2008060002 of product D95-3-2a with 3.0 % Night Owl DOIS 2018C (Fragrance GCAS: 91731015).Please change batch no. from B0205A45502 to B0205A45503 (b) In all formats of test report we are writing one remark line"'*' represents categories/test parameters not covered under NABL ¦ '**' represents outsource sample ¦ '#' represents Customer Defined Fields" but as per the implementation of NABL 133 in second report(2) we have to remove" '*' represents categories/test parameters not covered under NABL " because as per the NABL 133 in place of highlighting non-accredited parameters with "*" we are generating separate report.This change is applicable only for (2) report and is not applicable for all earlier reports. (c) The terminology " Submitted by" mentioned in PART A of test report can be replaced with "Test Request Submitted By" in test report format.This change is applicable for Building,Textile,Cosmetics,Food,Technical Pesticides,Helmet) | Praveen Kumar Singh | 2020-08-13 | 2020-08-13 | Completed
Praveen-Singh : Approval-Query Hours : Point (b ) : | Description : [20 Hrs] Steps: Generation of NABL Test Report based on following condition: If Order Date is less than 15-July-2020, then : Single Test Report having asterisk sign infront of non-nabl scope test parameters. No asterisk sign infront of nabl scope test parameters If fully NABL scope order, then F will visible at the time of approving of report "'*' represents categories/test parameters not covered under NABL" will be visible in test report If fully NABL scope order,then NABL will be generated with F other wise P If Order Date is greater than or equal to 15-July-2020, then: Two Test report will be generated One Test report will have all NABL Scope parameter with NABL URL No. Other Test Report will have all non-nabl Scope parameter without NABL URL No. "'*' represents categories/test parameters not covered under NABL" will not be visible in both the test report Testing and Uploading of above task on Staging Server. Testing and Uploading of above task on Live Server. | Praveen Kumar Singh | 2020-08-24 | 2020-08-24 | Completed
Praveen-Singh : Regarding updation of sales executive names in LIMS : | Description : [21.00 Hrs] (a) GST Slab will be IGST for SEZ customer within the state: Changes in the Invoice generation logic for listed Bulling Types branch and department wise: If Customer Category is SEZ , then GST will be IGST(18%) irrespective of invoicing done within/Outside State for below Billing Types: Daily Regular Weekly Monthly PO-Wise Otherwise for all Customer Category, GST will be based on within/Outside State for below Billing Types: Daily Regular Weekly Monthly PO-Wise Testing of above logic in listed billing Types in invoice Generation branch and department wise: Daily Regular Weekly Monthly PO-Wise (b) Account Hold Provision available in customer master will be given to CRM also along with Administrator: Steps: Providing Only VIEW permission of customer to CRM Role. Implementing Hold Provision for CRM on VIEW Permission Only. | Praveen Kumar Singh | 2020-09-05 | 2020-09-07 | Completed
Praveen-Singh : Sales Executive Names Updation in Customer Master : | Description : [1 Hrs] Sales Executive Names Updation in Customer Master: Formatting of listed columns: customer code final executive names employee code sales territory Uploading using excel file provided by client | Praveen Kumar Singh | 2020-09-09 | 2020-09-09 | Completed
Praveen-Singh : Budget File Updation in Master Form : | Description : [8 Hrs] Budget File Updation in Master Form: Formatting listed columns: ust_division_id ust_product_category_id ust_customer_id ust_user_id ust_date Removing of duplicate record Creation of Uploading Script Uploading of Budget file shared by the client: Master Testing:ADD ¦ EDIT ¦ LIST ¦ DELETE | Praveen Kumar Singh | 2020-09-09 | 2020-09-11 | Completed
Praveen-Singh : Changes in MIS-Report : Daily Sales Report : Adding of Product Category and Sub category in Daily Sales Detail : | Description : [2 Hrs] I) Changes in MIS-Report : Daily Sales Report : Adding of listed column: Product Category Product Sub Category II)Testing above report on staging and local Server. | Praveen Kumar Singh | 2020-09-11 | 2020-09-11 | Completed
Praveen-Singh : Test Report : EIC Report Format Implementation : | Description : [45.00 Hrs] Process flow of Approved EIC Report Format(Pt.-1) task below: Steps: Modification in Final Test Master: On Adding: Measurement of uncertainty Limit of determination LOQ/ CCa/ CC§,as aqplicab4e (e.g.LOQ In case Of pesticides,CCg for Screening test CCa for drugs 6 oontaminated, alt.(LOD/Decision Limit LOD as applicable-master MRPL On Editing: Measurement of uncertainty Limit of determination LOQ/ CCa/ CC§,as aqplicab4e (e.g.LOQ In case Of pesticides,CCg for Screening test CCa for drugs 6 oontaminated, alt.(LOD/Decision Limit LOD as applicable MRPL Modification in Cloning of Final Test Master: Changes in the logic by adding listed fields: Measurement of uncertainty Limit of determination LOQ/ CCa/ CC§,as aqplicab4e (e.g.LOQ In case Of pesticides,CCg for Screening test CCa for drugs 6 oontaminated, alt.(LOD/Decision Limit LOD as applicable MRPL Mofication on Order Booking: On Adding: Measurement of uncertainty Limit of determination LOQ/ CCa/ CC§,as aqplicab4e (e.g.LOQ In case Of pesticides,CCg for Screening test CCa for drugs 6 oontaminated, alt.(LOD/Decision Limit LOD as applicable-master MRPL On Editing: Measurement of uncertainty Limit of determination LOQ/ CCa/ CC§,as aqplicab4e (e.g.LOQ In case Of pesticides,CCg for Screening test CCa for drugs 6 oontaminated, alt.(LOD/Decision Limit LOD as applicable MRPL HTML Designing of EIC PDF with listed heads: Header Data Footer Data Container Data: Part A-All Custom Fields.It will be one one page-1 Part C-It will contain Test Result with listed heads: Parameters tested-Test Parameters Unit of Measurement-Units Results with corrected recovery along with level of recovery-result Measurement of uncertainty Level of recovery-Will display the data added after this symbol '¦' by Analyst in Test Report Input while adding the Test Report in Analyst Window as per our discussion. Limit of determination LOQ/ CCa/ CC§,as aqplicab4e (e.g.LOQ In case Of pesticides,CCg for Screening test CCa for drugs 6 oontaminated, alt.(LOD/Decision Limit LOD as applicable MRPL Analytical Method-Equipment Used Specification standard/test method against which product tested-Method Name Used Protocol-Test report as per IS selected by Reviewer Part D: It contain notes select by users Logic creation for EIC Report Format Data PDF Generation of EIC Report Format : Option of one more checkbox on Report Popup Window of label 'EIC Report': On selecting the checkbox and clicking on Generate button, will generate the EIC Report Format PDF. Generation of PDF Report by Approval User using above HTML with listed parts: Part-A-Sample and Custom Added fields Information Part C : Test Result with all detail Part D: With Selected Notes. Testing of all above points on listed Servers: Local Server Staging Server | Praveen Kumar Singh | 2020-09-30 | 2020-09-30 | Completed
Praveen-Singh : Test Report : EIC Report Format Implementation : | Description : [45.00 Hrs] Process flow of Approved EIC Report Format(Pt.-1) task below: Steps: Modification in Final Test Master: On Adding: Measurement of uncertainty Limit of determination LOQ/ CCa/ CC§,as aqplicab4e (e.g.LOQ In case Of pesticides,CCg for Screening test CCa for drugs 6 oontaminated, alt.(LOD/Decision Limit LOD as applicable-master MRPL On Editing: Measurement of uncertainty Limit of determination LOQ/ CCa/ CC§,as aqplicab4e (e.g.LOQ In case Of pesticides,CCg for Screening test CCa for drugs 6 oontaminated, alt.(LOD/Decision Limit LOD as applicable MRPL Modification in Cloning of Final Test Master: Changes in the logic by adding listed fields: Measurement of uncertainty Limit of determination LOQ/ CCa/ CC§,as aqplicab4e (e.g.LOQ In case Of pesticides,CCg for Screening test CCa for drugs 6 oontaminated, alt.(LOD/Decision Limit LOD as applicable MRPL Mofication on Order Booking: On Adding: Measurement of uncertainty Limit of determination LOQ/ CCa/ CC§,as aqplicab4e (e.g.LOQ In case Of pesticides,CCg for Screening test CCa for drugs 6 oontaminated, alt.(LOD/Decision Limit LOD as applicable-master MRPL On Editing: Measurement of uncertainty Limit of determination LOQ/ CCa/ CC§,as aqplicab4e (e.g.LOQ In case Of pesticides,CCg for Screening test CCa for drugs 6 oontaminated, alt.(LOD/Decision Limit LOD as applicable MRPL HTML Designing of EIC PDF with listed heads: Header Data Footer Data Container Data: Part A-All Custom Fields.It will be one one page-1 Part C-It will contain Test Result with listed heads: Parameters tested-Test Parameters Unit of Measurement-Units Results with corrected recovery along with level of recovery-result Measurement of uncertainty Level of recovery-Will display the data added after this symbol '¦' by Analyst in Test Report Input while adding the Test Report in Analyst Window as per our discussion. Limit of determination LOQ/ CCa/ CC§,as aqplicab4e (e.g.LOQ In case Of pesticides,CCg for Screening test CCa for drugs 6 oontaminated, alt.(LOD/Decision Limit LOD as applicable MRPL Analytical Method-Equipment Used Specification standard/test method against which product tested-Method Name Used Protocol-Test report as per IS selected by Reviewer Part D: It contain notes select by users Logic creation for EIC Report Format Data PDF Generation of EIC Report Format : Option of one more checkbox on Report Popup Window of label 'EIC Report': On selecting the checkbox and clicking on Generate button, will generate the EIC Report Format PDF. Generation of PDF Report by Approval User using above HTML with listed parts: Part-A-Sample and Custom Added fields Information Part C : Test Result with all detail Part D: With Selected Notes. Testing of all above points on listed Servers: Local Server Staging Server | Praveen Kumar Singh | 2020-10-08 | 2020-10-08 | Completed
Praveen-Singh : Query Hours- 12.10.2020 : | Description : [2 Hrs] Removal of Tax Slab: F02-2009290625 F02-2009290624 F02-2009290623 F02-2009290622 F02-2009290621 F02-2009290620 F02-2009290619 F02-2009290618 F02-2009290617 F02-2009280609 F02-2009280608 F02-2009280607 F02-2009280606 F02-2009280605 F02-2009280604 F02-2009280603 F02-2009280602 F02-2009280601 F02-2009280600 | Praveen Kumar Singh | 2020-10-13 | 2020-10-13 | Completed
Praveen-Singh : Implementation of Financial Year in Invoice Generation: | Description : [18 Hrs] Implementation of Financial Year: Creation of Financial Year Master: Migration Creation Adding of New col in Invoice Master table and applying of logic for updation of Financial Year at the time of Invoive Generation Updation of Finacial Year data in all generated invoices | Praveen Kumar Singh | 2020-10-27 | 2020-10-27 | Completed
Praveen-Singh : Test Report : EIC Report Format :- New Changes | EIC Format :- New Changes: Migration Change: product_test_dtl - New Field 'validation_protocol' order_parameters_detail - New Field 'validation_protocol' Add one more column of "Validation Protocol" on Product Test Form whose value will be defined parameter wise at the time of master creation and display that variable under Validation Protocol in EIC report: Modification in Final Test Master: On Adding: Validation Protocol On Editing: Validation Protocol Modification in Cloning of Final Test Master: Changes in the logic by adding listed fields: Validation Protocol Modification on Order Booking: On Adding: Validation Protocol On Editing: Validation Protocol PDF Generation of Test Report: Renaming of two variables. Nature of sample - Type &amp; Nature of Product- (First page) LOQ/CCA/acc as applicable - Limit of Determination CC(symbol of alpha )/LOQ as applicable Footer Data: Disclaimer value in EIC format wil be fixed as per the user requirement and will not come from Standard master table. - will provide soon Testing of all above points on listed Servers: Local Server Staging Server | Praveen Kumar Singh | 2020-10-15 | 2020-10-15 | Completed
Praveen-Singh : Test Report : Changes on Chennai Report Format:- | Description :[12 Hrs] Changes on Chennai Report Format:- i)Completed on:- will be the date when analyst has updated result of last parameter of particular sample. ii)Date of Report :- will be the date when report is finalized by Technical Manager iii)Incorporate one more signature of Microbiologist in Chennai report(same of Panchkula report format) as presently we have only two signatures. | Praveen Kumar Singh | 2020-10-19 | 2020-10-19 | Completed
Praveen-Singh : Software Updation : | Description:[2.00 Hrs] Software Updation: a)Updated Code on Drish Live Server from SVN b)Updated DB on Drish Live Server c)Updated Code on Drish Dev Staging Server from SVN d)Updated DB on Drish Dev Staging Server e)Updated Code on ITC Dev Staging Server from SVN f)Updated DB on ITC Dev Staging Server g)Created the Software Package for Live Server Updation. | Praveen Kumar Singh | 2020-10-21 | 2020-10-21 | Completed
Praveen-Singh : MIS-Report : Incorporation of Column in Sales Report Detail : | Description : [2.00 Hrs] Incorporation of Column in Sales Report Detail Invoicing Customer Code Invoicing Customer State | Praveen Kumar Singh | 2020-10-27 | 2020-10-27 | Completed
Praveen-Singh : MIS-Report : Incorporation of Column in Account Sales Detail : | Description : [3.00 Hrs] Incorporation of Column in Account Sales Detail: Billing Month Financial Year Testing on Local and Staging Server | Praveen Kumar Singh | 2020-10-28 | 2020-10-28 | Completed
Praveen-Singh : Sales Report Detail- To be considered on priority : Testing and Finalization : | Description :[5 Hrs] Provision of Test Standard Selection Window(Master Creation): Creation of New Migration- 'Order_defined_test_std_dtl': odtsd_id odtsd_branch_id odtsd_product_category_id odtsd_test_standard_id odtsd_created_by created_at modified_at Creation of New Master Form with listed fields: Branch Selectbox - required Department Selectbox - required Test Standard with checkbox department wise- required Provision of Adding and Editing for Test Standard Record Provision of Test Standard Selection Criteria in Order Booking form: Integration of Test Standard detail in order from from defined Order_defined_test_std_dtl Master based on Branch and Department. Displaying of Test Standard Selectbox after Product Master Selectbox. Saving and Editing of Test Standard in Order Master table in new field 'defined_test_standard'. Integration/Displaying of Selected Test Standard in Sales Report Detail: Implementation of Test Standard Name from Defined Test Standard Name in place of Product Test Master. Unit Testing of all the above Steps on ITC Staging Server. | Praveen Kumar Singh | 2020-11-05 | 2020-11-05 | Completed
Praveen-Singh : Nov-2020-Task-List : Regarding round off of requirement column : | Description : [3.00 Hrs] Changes in the PDF format of Test Report: Displaying of requirement column value upto 3 decimal places if value id numeric in all branches and in all departments. Testing on Local Server and Staging Server. [Client word: Regarding round off of requirement colum] | Praveen Kumar Singh | 2020-11-11 | 2020-11-11 | Completed
Praveen-Singh : Nov-2020-Task-List : Outsource sample ** remark point in Test Report : | Description : [8.00 Hrs] I) Implementation of logic for displaying listed separately: Sample having NABL Scope Sample having tested outside the lab.(Outsource sample) Sample Field having defined under custom defined master. II)Changes in the PDF format of Test Report in listed departments : Food Pharma Ayurveda Building Helmet Water Environment Cosmatic Default III) Testing of above points on listed Servers: Local Server Staging Server. [Client word: Outsource sample ** remark point in Test Report] | Praveen Kumar Singh | 2020-11-23 | 2020-11-23 | Completed
Praveen-Singh : Sales Executive Names Updation in Customer Master : | Description : [1 Hrs] Sales Executive Names Updation in Customer Master: Formatting of listed columns: customer code final executive names employee code sales territory Uploading using excel file provided by client | Praveen Kumar Singh | 2020-11-20 | 2020-11-20 | Completed
Praveen-Singh : Nov-2020-Task-List : Employee Sales Target Report : | Description : [45.00 Hrs] Employee Sales Target Report: User Sales Target Types Master: Code Name Status User Sales Target Detail Master : New Fields : User Sales Type Id Month Year Financial Year Values should be displayed date wise in place of MTD Wise. Change in Existing Master on: Adding¦ Editing ¦ Listing ¦ Deleting Master form uploading from excel: Creation of Uploading popup Attaching Sample Format under browse button Branch,Department,Customer,Type,Month,sales-executive uniqueness validation Display error if Branch,Department,Customer,sales executive doesn't exist in software Generation of MIS-Report with columns: Budget Wise: Financial Year Branch Department Customer Code Customer Name Place State Customer Type(Existing) Type Month Name Sales Executive Amount Amount(in Lakh) Forecast Wise: Financial Year Branch Department Customer Code Customer Name Place State Customer Type(Existing) Type Month Name Sales Executive Amount Amount(in Lakh) Actual Wise: Financial Year Branch Department Customer Code Customer Name Place State Customer Type(Existing) Type Month Name Sales Executive Amount Amount(in Lakh) Testing of above points on listed Servers: Local Server Staging Server Live Server | Praveen Kumar Singh | 2020-11-26 | 2020-11-26 | Completed
Praveen-Singh : Nov-2020-Task-List : Employee Sales Target Report : | Description : [45.00 Hrs] Employee Sales Target Report: User Sales Target Types Master: Code Name Status User Sales Target Detail Master : New Fields : User Sales Type Id Month Year Financial Year Values should be displayed date wise in place of MTD Wise. Change in Existing Master on: Adding¦ Editing ¦ Listing ¦ Deleting Master form uploading from excel: Creation of Uploading popup Attaching Sample Format under browse button Branch,Department,Customer,Type,Month,sales-executive uniqueness validation Display error if Branch,Department,Customer,sales executive doesn't exist in software Generation of MIS-Report with columns: Budget Wise: Financial Year Branch Department Customer Code Customer Name Place State Customer Type(Existing) Type Month Name Sales Executive Amount Amount(in Lakh) Forecast Wise: Financial Year Branch Department Customer Code Customer Name Place State Customer Type(Existing) Type Month Name Sales Executive Amount Amount(in Lakh) Actual Wise: Financial Year Branch Department Customer Code Customer Name Place State Customer Type(Existing) Type Month Name Sales Executive Amount Amount(in Lakh) Testing of above points on listed Servers: Local Server Staging Server Live Server | Praveen Kumar Singh | 2020-12-31 | 2020-12-31 | Completed
Praveen-Singh : Test Report : APEDA Format-Debugging : | APEDA Format-Debugging | Praveen Kumar Singh | 2020-12-18 | 2020-12-18 | Completed
Praveen-Singh : Regarding result of Pesticide Residue category to be replicated on selection of Copy Button : | Description : [3.00 Hrs] Provision to replicate result of Pesticide Residue category on selection of Copy Button: Requirement: In Pesticide Residue category we are booking hundreds of parameters and maximum time result is same for all the parameters. Please provide check box in front of first parameter so that result entered in first parameter will be replicated to all the below parameters on selecting checkbox by the user. Implement this provision for Food department for both the branches on Analyst Dashboard. Along with Pesticide Residue we have to implement this provision in some other categories also having same list of parameters. If required i will provide the all category names. | Praveen Kumar Singh | 2020-12-22 | 2020-12-22 | Completed
Praveen-Singh : APEDA Format - Dynamic Fields alignment change in PDF template : | APEDA Format - Dynamic Fields alignment change in PDF template | Praveen Kumar Singh | 2020-12-18 | 2020-12-18 | Completed