## Feb-2022
ITC ERP TASK DETAIL(Feb-2022)
S.No. | Detail | Priority | Estimated Hours | Status
1 | Cosmetics Report Format - Replicate Form 39 as it is and change label 'Form 39' to 'Cos24' | 9 | 12 | Working
Points:
Coping of Form39 Format of Pharma
Implementation of logic on Report Generation Criteria Popup of Cosmetics Department : Provision on seperate checkbox on Report Generation Criteria Popup
2 | Provision to upload PO no. in order bookings using csv | 10 | 14 | Done
Points:
Uploading of CSV File using Popup window
Saving of PO No and Po Date in the order where detail is not available
3 | Write Label Test Report in Form 39 & Form 50 template Pharma | 2 | 5 | Done
4 | Order Confirmation mail is circulated to email id defined as 'Primary'. Please circulate to All. | 11 | 4
5 | Provision to edit GST tax slab and amount in generated invoice. | 12 | 40
Points:
Opening of Invoice in Edit Mode
Provision for editing the tax slab
When user enter the tax slab, system will display the calculated amount in the window.
User will not able to change the Tax slab type - IGST to CGST and SCGT and vice-versa
Invoice will be only edited by admin.
5 | Provision of Shipping To in Customer master. | 15 | 120
Points:
Changes in Customer Master:
New Master attached with Customer Master : Provision of adding multiple reporting address
New Master attached with Customer Master : Provision of adding multiple invoicing address
Changes in Order Booking:
Upon selecting the Invocing to and Reporting to, system will open all the attached address,then user will chose the required address.
Saving/Editing of selected address in order booking
Changes in Order Process Stages:
Implementing selected reporting to address in PDF Test Report and Software view in all phases of order booking for all branch and department.
Logic for setting default address for all previous booking:
Setting default address for all the previous order booking.If the user has not selected, then it will display the adresses as per the selected customer addresss both for invoiving to and reporting to.
Changes on Invoice Generation:
Saving of invoicing to addresss at the time of invoice generation
Implementing selected invoicing to address in PDF Invoice format and Software view in both invoice format all branch and department.
6 | Provision of QR Code in Test Report |  |  | Hold
7 | Provision to search Customer name by name or LIMS customer code in Payments--Credit Notes--Customer name drop down list | 13 | 1
8 | Provision to edit order booking amount to Administrator saved during Order Booking. | 14
9 | Display only current month data in all tabs of below modules. | 1 | 25 | Done
(a)Product master creation --- Master-->Tests Parameters Product Tests (b)Master -->Invoicing Product master alias State wise products Customer wise product Customer wise parameter (c)Payments Debite Notes Credit Notes
10 | Sales-Samples - Add LIMS Customer & Address along with Customer Name & Cty Sequence will be LIMS Customer Code /Customer Name/City | 3 | 5 | Done
11 | Sales-Order-Add LIMS Customer code & Address in Customer Detail along with Customer Name & City.Sequence will be LIMS Customer Code /Customer Name/City | 4 | 3 | Done
12 | Sales-Order - Dashboard-- Filter for searching Place & Prototype No. & Expected Due Date,customer code. | 5 | 4 | Done
13 | Sales -Order - Export to Excel- Under Sample Description - Product master name is coming in place of Sample Name enetered in Order Booking. | 6
14 | Master-Customer - Dashboard - Add Customer city column and search filter. | 7 | 3 | Done
15 | Sales-Reports- Dashboard- Add Customer code & City for search filter on Admin,CRM & Dispatcher Role | 8 | 5 | Done
16 | Mailgun Process Document Study and its Implementation | 9 | 3 | Working