## July-2021
S.No. | Date | Detail | Priority | Estimated Hours | Status
1 | 14.07.2021 | NABL Symbol coming in Form 50 under Cosmetics department is not proper. | 1 | 1 | Done
2 | 14.07.2021 | Disclaimer to be revised : Refer below details- Designing issue in final pdf template 1. The report is only for the sample tested. 2. Total liability of ITC Labs is limited to invoiced amount. 3. The test report shall not be reproduced except in full without the written approval of the laboratory. 4. If samples not consumed during analysis, it will be stored and retain as per company policy. 5. Samples not withdrawn by us unless otherwise stated. 6. Test report in full or parts shall not be used for promotional or publicity purposes. 7. Legal disputes are subjected to Panchkula Jurisdiction only | 2 | 4 | Done
3 | 14.07.2021 | Company Address: To be represented as given below Interstellar Testing Centre Pvt. Ltd. 86, Industrial Area, Phase-I, Panchkula-134109 (Haryana) Phone: (O) 0172-2561543, 2565825 E-mail: customersupport@itclabs.com Visit us: www.itclabs.com | 3 | 2 | Done
4 | 14.07.2021 | As discussed earlier while amending any test report the LIMS is generating a new Report number instead of suffixing "A" to previous report number. |  | Confirm By Client | To be test on staging server
5 | 14.07.2021 | As discussed the sample condition is one of the requirement of ISO 17025-Make it mandatory in order booking and display in Reviewing & Final pdf templates of Food,Environment,Building,Cosmetics,Helmet,Technical Pesticides,Water under Sample Name in Sample Information Part A | 7 | 24 | Done
6 | 14.07.2021 | Data to be enter in Test Standard in Order Booking(Routine Analysis,Method Validation & Verification,Shelf Life Study) In case of stability booking software will automatically displaye value in drop down list. In case of method validation & verification software will ask for the rate of sample to be entered by order booker. Points: Make this field required Display the Sals Report Detail - default value 'Routine Analysis'(1 yrs). In case of Stablility Order- Display the Stability Study related Option in dropdown In case of method validation & verification software will ask for the sample amount (Input Type*) to be entered by order booker. Rename the dropdown lebel as 'Analysis Type'.It will replace the sample amount with order booker entered amount.It will be placed after TAT Days. Updating records for 1 year in order booking table with default value 'Routine Analysis' if defined standard is NULL | 8 | 15 | Done
7 | 14.07.2021 | Value of Test Standard entered in order booking will be displayed in Invoicer Dashboard as a new column. Point : Displaying of Analysis Type on Invoice eGeneration Window Under Reports for Invoicing. | 4 | 2 | Done
8 | 14.07.2021 | Incorporate Test Standard column in Daily Booking Detail Daily Book detail - Adding of New Colum 'Defined Tested Standard' | 5 | 2 | Done
9 | 05.03.2021 | Auto mailing on expected due date change popup window on Job Sheet Print.Enabling the right for CRM Role for accessing the Job Sheet Window on Scheduling Menu Change in Expected Due Date Popup Reason of Change Checkbox for auto mail Expected Due Date will never change after date is passed from the currrent date/Meand It should be less than and deaual to Current Date, then user will able to change it | 6 | 12 | Done
10 | 05.03.2021 | New Format of Cosmetics | 9 | Discussion Required
11 | 20.07.2021 | Provision of back date in Others department Chennai only.
12 | 20.07.2021 | Some changes in Invoices depending upon the GST category