## March-2022
ITC ERP TASK DETAIL(Mar-2022)
S.No. | Detail | Priority | Estimated Hours | Status
1 | Order Confirmation mail is circulated to email id defined as 'Primary'. Please circulate to All. | 3 | 4
2 | Provision to edit GST tax slab and amount in generated invoice. | 2 | 40 | Working On
Points:
Opening of Invoice in Edit Mode
Provision for editing the tax slab
When user enter the tax slab, system will display the calculated amount in the window.
User will not able to change the Tax slab type - IGST to CGST and SCGT and vice-versa
Invoice will be only edited by admin.
3 | Provision of Shipping To in Customer master. | 4 | 120
Points:
Changes in Customer Master:
New Master attached with Customer Master : Provision of adding multiple reporting address
New Master attached with Customer Master : Provision of adding multiple invoicing address
Changes in Order Booking:
Upon selecting the Invocing to and Reporting to, system will open all the attached address,then user will chose the required address.
Saving/Editing of selected address in order booking
Changes in Order Process Stages:
Implementing selected reporting to address in PDF Test Report and Software view in all phases of order booking for all branch and department.
Logic for setting default address for all previous booking:
Setting default address for all the previous order booking.If the user has not selected, then it will display the adresses as per the selected customer addresss both for invoiving to and reporting to.
Changes on Invoice Generation:
Saving of invoicing to addresss at the time of invoice generation
Implementing selected invoicing to address in PDF Invoice format and Software view in both invoice format all branch and department.
4 | Provision of QR Code in Test Report
5 | Provision to search Customer name by name or LIMS customer code in Payments--Credit Notes--Customer name drop down list | 5
6 | Provision to edit order booking amount to Administrator saved during Order Booking. | 6
7 | Removal of dummy mail id from customer email addresses | 1 | 2 | Done