## May-2022
ITC ERP TASK DETAIL(May-2022)
S.No. | Detail | Priority | Estimated Hours | Status
1 | Provision to display NABL scope against parameter in section incharge |  | 8 | Done
2 | Provision to capture 'Date of start of analysis' & 'Date of completion of Analysis' | 2 | 40 | Done
| Date of start of analysis - In testing stage for an order booking analyst will enter 'Date of Start of Analysis' while updating the result against every allocated test parameter. |  |  | New
In an order booking smallest date entered against test parameter will be considered as 'Date of Start of Anlaysis' on Test Report.
In an order booking biggest date entered against test parameter will be considered as 'Date of Completion of Anlaysis' on Test Report.
Note :- (a) Value of 'Date of Start of Analysis' entered will always by equal or greater than 'Dateof Booking'.
3 | Product master file update Food & Pharma |  |  | New
4 | Travel Plan on Customer Portal (a) New form on customer portal for Sales Executive login - Customer Name Place Date of Visit Contact Prson Purpose of Visit Department Note :- (i) Visit Alerts will come two days before as per the defined plan (ii) Customer name displayed in list will be linked with concerning sales executive (b) Travel Report - Status update in visit plan as per defined Selection Criteria - Customer Wise Date wise Sales Exevutive name wise Reamrks Next visit plan Status (Completed, Not Completed,Cancelled ,Rescheduled) ( c ) MIS Report Selection Criteria - Customer Name & Place Sales Executive name Department Name From Date & To Date Date , Customer Name, Place, Department, Contact Person, Purpose of Visit, Remarks, Next Visit Plan, Visit Status (d) Provision to add travel expenses (e) Approval Hierarchy for Travel plan & travel expenses (f) Alert | 3
5 | Test Parameter Master - Provision to enable or disbale text editor.By default it should be disabled. |  | 7 | Done
6 | Pharma Back Date Booking Issue |  | 2 | Done
7 | Test Report Ammendment - Test report no.is changing on ammendment of test report |  | 6 | Live Issue
8 | Recalculation of Expected Due Date & Department Due Date on addition of parameter from 'Scheduling- Job sheet Print' |  | 4 | Done
9 | Confirmation in cut off time for +1 Day addition in Expected Due Date & Department Due - Either 02:00 Pm or 04:00 pm.(+1 is not added in department due date calculation if sample is booking after cut off time) |  | 5 | Done
10 | Provision of excel upload to update the selling price in product master as per parameter name & equipment name. |  | 2 | New