## PMP
ITC ERP Panchkula (ERP)
Created By : Praveen Singh
S.No. | Name | Date Created | Developer | Due Date | Completed On | Status
1 | Design Database | 2016-11-30 12:16 | Praveen Kumar Singh | 2016-12-05 | 2016-12-05 | Completed
2 | Basic Set up and installation | 2016-11-30 12:18 | Praveen Kumar Singh | 2016-12-05 | 2016-12-05 | Completed
3 | User Authentication and Roles | 2016-11-30 12:24 | Praveen Kumar Singh | 2016-12-21 | 2017-01-02 | Completed
4 | Employee-end / Sales / Orders Management | 2017-01-31 12:30 | Praveen Kumar Singh | 2017-01-20 | 2017-01-20 | Completed
5 | Employee-end /Sales / Report Management | 2017-01-31 12:36 | Praveen Kumar Singh | 2017-01-27 | 2017-01-27 | Completed
6 | Employe-end / Sales / Invoice Management | 2017-01-31 12:43 | Praveen Kumar Singh | 2017-02-03 | 2017-02-03 | Completed
7 | Employee-end / Inventory / Vendor Management | 2017-02-23 11:02 | Praveen Kumar Singh | 2017-02-17 | 2017-02-17 | Completed
8 | Inventory / Item Master Management | 2017-02-23 11:05 | Praveen Kumar Singh | 2017-02-22 | 2017-02-22 | Completed
9 | Admin-end/ Inventory / Branch Wise Items(BWI) | 2017-02-27 11:57 | Praveen Kumar Singh | 2017-03-10 | 2017-03-10 | Completed
10 | Admin-end / Employee-end / Inventory / Branch Wise Item (BWI) / New Item Updation | 2017-03-01 12:00 | Praveen Kumar Singh | 2017-03-01 | 2017-03-01 | Completed
11 | Admin-end / Inventory / Branch Wise Store(BWS) | 2017-03-01 12:52 | Praveen Kumar Singh | 2017-03-02 | 2017-03-02 | Completed
12 | Admin-end / Inventory / Branch Wise Item Stock (BWIS) | 2017-03-01 12:53 | Praveen Kumar Singh | 2017-03-06 | 2017-03-06 | Completed
13 | Admin-end / Sales / Orders Management | 2017-03-06 17:03 | Praveen Kumar Singh | 2017-03-06 | 2017-03-06 | Completed
14 | Admin-end /Sales / Report Management | 2017-03-06 17:05 | Praveen Kumar Singh | 2017-03-06 | 2017-03-06 | Completed
15 | Admin-end / Sales / Invoice Management | 2017-03-06 17:08 | Praveen Kumar Singh | 2017-03-06 | 2017-03-06 | Completed
16 | Admin-end / Inventory / Vendor Management | 2017-03-06 17:12 | Praveen Kumar Singh | 2017-03-08 | 2017-03-08 | Completed
17 | Employee-end /Inventory / Branch Wise Items(BWI) | 2017-03-06 17:16 | Praveen Kumar Singh | 2017-02-28 | 2017-02-28 | Completed
18 | Employee-end / Inventory / Branch Wise Store(BWS) | 2017-03-06 17:24 | Praveen Kumar Singh | 2017-03-02 | 2017-03-02 | Completed
19 | Employee-end / Inventory / Branch Wise Item Stock (BWIS) | 2017-03-06 17:26 | Praveen Kumar Singh | 2017-03-06 | 2017-03-06 | Completed
20 | Master / Employee / Changes | 2017-03-09 10:32 | Praveen Kumar Singh | 2017-03-09 | 2017-03-09 | Completed
21 | Admin-end / Inventory / PO Management | 2017-03-15 18:24 | Praveen Kumar Singh | 2017-03-24 | 2017-03-24 | Completed
22 | Employee-end / Inventory / PO Management | 2017-03-15 18:25 | Praveen Kumar Singh | 2017-03-24 | 2017-03-24 | Completed
23 | Admin-end / Inventory / DPO Management | 2017-03-22 20:12 | Praveen Kumar Singh | 2017-03-23 | 2017-03-23 | Completed
24 | Employee-end / Inventory / DPO Management | 2017-03-22 20:13 | Praveen Kumar Singh | 2017-03-24 | 2017-03-24 | Completed
25 | Admin-end / Inventory / IGN Management | 2017-04-01 19:55 | Praveen Kumar Singh | 2017-04-06 | 2017-04-06 | Completed
26 | Employee-end / Inventory / IGN Management | 2017-04-01 19:56 | Praveen Kumar Singh | 2017-04-07 | 2017-04-10 | Completed
27 | Adminend / Roles / Module Management | 2017-05-04 17:29 | Praveen Kumar Singh | 2017-05-12 | 2017-05-12 | Completed
28 | Adminend / Roles / Navigation Management | 2017-05-06 13:30 | Praveen Kumar Singh | 2017-05-15 | 2017-05-16 | Completed
29 | Admin-end / Payment / Payment Received | 2017-05-16 15:05 | Praveen Kumar Singh | 2017-05-17 | 2017-05-17 | Completed
30 | Employee-end / Payment / Payment Received | 2017-05-16 15:05 | Praveen Kumar Singh | 2017-05-17 | 2017-05-17 | Completed
31 | Admin-end / Payment / Payment Made | 2017-05-16 15:06 | Praveen Kumar Singh | 2017-05-19 | 2017-05-18 | Completed
32 | Employee-end / Payment / Payment Made | 2017-05-16 15:06 | Praveen Kumar Singh | 2017-05-19 | 2017-05-19 | Completed
33 | Admin-end / Payment / Debit Note: | 2017-05-23 14:01 | Praveen Kumar Singh | 2017-05-25 | 2017-05-29 | Completed
34 | Employee-end / Payment / Debit Note: | 2017-05-23 14:02 | Praveen Kumar Singh | 2017-05-25 | 2017-05-29 | Completed
35 | Admin-end / Payment / Credit Note: | 2017-05-23 14:03 | Praveen Kumar Singh | 2017-05-26 | 2017-05-29 | Completed
36 | Employee-end / Payment / Credit Note: | 2017-05-23 14:04 | Praveen Kumar Singh | 2017-05-26 | 2017-05-29 | Completed
37 | Admin-end / Master / Department Change to Equipment Type and Parent Category Name | 2017-06-12 20:18 | Praveen Kumar Singh | 2017-06-16 | 2017-06-16 | Completed
38 | Admin-end / Sales / Order / Order Form Changes | 2017-06-17 11:41 | Praveen Kumar Singh | 2017-06-20 | 2017-06-20 | Completed
39 | Admin-end / Sales / Report / Changes | 2017-06-20 11:48 | Praveen Kumar Singh | 2017-06-21 | 2017-06-22 | Completed
40 | Admin-end / Scheduling / Assign Job | 2017-06-22 11:41 | Praveen Kumar Singh | 2017-06-22 | 2017-06-22 | Completed
41 | Employee-end / Scheduling / Assign Job | 2017-06-22 20:40 | Praveen Kumar Singh | 2017-06-22 | 2017-06-22 | Completed
42 | Admin-end / Scheduling / Jobs | 2017-06-22 20:40 | Praveen Kumar Singh | 2017-06-23 | 2017-06-23 | Completed
43 | Employee-end / Scheduling / Jobs | 2017-06-22 20:41 | Praveen Kumar Singh | 2017-06-23 | 2017-06-23 | Completed
44 | Admin-end / Sales / Sample Receiving Management | 2017-06-29 19:03 | Praveen Kumar Singh | 2017-07-03 | 2017-07-03 | Completed
45 | Employee-end / Sales / Sample Receiving Management | 2017-06-29 19:07 | Praveen Kumar Singh | 2017-07-05 | 2017-07-05 | Completed
46 | Admin-end / Sales / Report / Template Implementation | 2017-07-05 19:48 | Praveen Kumar Singh | 2017-07-05 | 2017-07-05 | Completed
47 | Admin-end / Sales / Order / Order Form Changes(05-July-2017) | 2017-07-05 19:51 | Praveen Kumar Singh | 2017-07-05 | 2017-07-05 | Completed
48 | Admin-end / Sales / Process Management | 2017-07-12 12:18 | Praveen Kumar Singh | 2017-07-12 | 2017-07-12 | Completed
49 | Master / Invoicing Type / State Wise Product: | 2017-07-29 19:46 | Praveen Kumar Singh | 2017-07-31 | 2017-07-31 | Completed
50 | Master / Invoicing Type / Customer Wise Product: | 2017-07-29 19:46 | Praveen Kumar Singh | 2017-08-01 | 2017-08-01 | Completed
51 | Invoicer / Sales / Invoices(Invoice Structure) | 2017-08-02 14:37 | Praveen Kumar Singh | 2017-08-03 | 2017-08-03 | Completed
52 | Sales / Orders / Job Order Template Implementation: | 2017-08-22 20:03 | Praveen Kumar Singh | 2017-08-24 | 2017-08-31 | Completed
53 | Sales / Report / Pharma / PDF Report Generation(With Header & Footer and Without Header & Footer): | 2017-08-31 13:00 | Praveen Kumar Singh | 2017-09-02 | 2017-09-02 | Completed
54 | Admin-end / Scheduling / Analyst Sheet: | 2017-09-07 19:43 | Praveen Kumar Singh | 2017-09-08 | 2017-09-08 | Completed
55 | Schedular-end / Scheduling / Analyst Sheet: | 2017-09-08 10:51 | Praveen Kumar Singh | 2017-09-09 | 2017-09-16 | Completed
56 | Admin-end / MIS Report Implemetation(Details are available in MIS Report Doc) | 2017-10-17 19:29 | Praveen Kumar Singh | 2017-12-30 | 2017-12-30 | Completed
57 | Admin-end / MIS / Reports / Excel Generation: | 2017-10-25 19:36 | Praveen Kumar Singh | 2017-12-30 | 2017-12-30 | Completed
58 | Admin-end / Sales / Scheduling Management(Changes Dicussed on Client Side on 28-June-17) | 2017-06-29 19:32 | Ruby | 2017-06-30 | 2017-07-30 | Completed
59 | Admin-end / Sales / Order / Barcode Generation | 2017-07-05 14:07 | Ruby | 2017-07-04 | 2017-07-21 | Completed
60 | Admin-end / Mail and Mail Template Integration | 2017-07-05 18:28 | Ruby | 2017-10-27 | 2017-12-28 | Completed
61 | Order-Booker / Sales / Orders Management(Changes discussed on 25-July-2017) | 2017-08-02 14:26 | Ruby | 2017-07-30 | 2017-08-03 | Completed
62 | Reporter / Sales / / Report Management(Changes discussed on 25-July-2017) | 2017-08-02 14:30 | Ruby | 2017-08-03 | 2017-08-03 | Completed
63 | Admin-end / Setting Management. | 2017-08-03 20:18 | Ruby | 2017-08-05 | 2017-08-05 | Completed
64 | Master / Invoicing Type / Product Master Alias(UI & Multiple Add More Functionality): | 2017-08-08 20:04 | Ruby | 2017-08-08 | 2017-08-14 | Completed
65 | Sales / Orders / Analytical sheet-I / All Deparment | 2017-08-31 13:12 | Ruby | 2017-09-02 | 2017-09-28 | Completed
66 | Sales / Scheduling / Analytical sheet-II / All Deparment | 2017-08-31 13:13 | Ruby | 2017-09-02 | 2017-09-28 | Completed
67 | Admin-end / Master / Holiday Master: | 2017-10-27 15:24 | Ruby | 2017-10-27 | 2017-10-27 | Completed
68 | Admin-end / Invoicer / Invoice Related Orders | 2017-12-22 14:52 | Ruby | 2017-12-22 | 2017-12-26 | Completed
69 | User Permission | 2016-12-05 11:30 | Nisha | 2016-12-06 | 2016-12-07 | Completed
70 | Create tables of database | 2017-01-02 16:47 | Nisha | 2017-01-02 | 2017-02-27 | Completed
71 | Master / Company master | 2017-02-08 19:14 | Nisha | 2017-01-03 | 2017-02-23 | Completed
72 | Master / Divisions Module | 2017-02-08 19:15 | Nisha | 2017-01-05 | 2017-02-23 | Completed
73 | Master / Employee Module | 2017-02-08 19:18 | Nisha | 2017-01-25 | 2017-02-23 | Completed
74 | Master / Customer Module | 2017-02-08 19:19 | Nisha | 2017-01-24 | 2017-02-23 | Completed
75 | Master / Test Standards Module | 2017-02-23 11:13 | Nisha | 2017-01-07 | 2017-01-07 | Completed
76 | Master / Product master Module | 2017-02-23 11:14 | Nisha | 2017-01-09 | 2017-01-09 | Completed
77 | Master / Test parameter categories Module | 2017-02-23 11:16 | Nisha | 2017-01-07 | 2017-01-07 | Completed
78 | Master / Test parameters Module | 2017-02-23 11:19 | Nisha | 2017-01-10 | 2017-01-10 | Completed
79 | Master / Product categories Module | 2017-02-23 11:21 | Nisha | 2017-01-16 | 2017-01-16 | Completed
80 | Master / Department Module | 2017-02-23 11:23 | Nisha | 2017-01-18 | 2017-01-18 | Completed
81 | Master / Equipment master Module | 2017-02-23 12:34 | Nisha | 2017-01-19 | 2017-01-19 | Completed
82 | Master / Method Master Module | 2017-02-23 12:46 | Nisha | 2017-01-19 | 2017-01-19 | Completed
83 | Master / Standard-Wise-Product-Test Module | 2017-02-23 12:51 | Nisha | 2017-03-09 | 2017-03-09 | Completed
84 | Master / Unit Module | 2017-02-23 12:54 | Nisha | 2017-01-16 | 2017-01-16 | Completed
85 | Inventory / Requisition Slip (RS)(header table and detail table) | 2017-02-27 12:04 | Nisha | 2017-02-28 | 2017-03-06 | Completed
87 | Inquiry Management | 2017-03-08 11:44 | Nisha | 2017-03-08 | 2017-03-08 | Completed
88 | Inquiry Report Management: | 2017-03-08 11:44 | Nisha | 2017-03-10 | 2017-03-10 | Completed
89 | Admin-end / Inventory / Indent Management | 2017-03-15 18:22 | Nisha | 2017-03-17 | 2017-03-17 | Completed
90 | Employee-end / Inventory / Indent Management | 2017-03-15 18:23 | Nisha | 2017-03-18 | 2017-03-18 | Completed
91 | Remember Me Functionality / Login Module | 2017-03-20 16:19 | Nisha | 2017-03-20 | 2017-03-20 | Completed
92 | Master / Customer Module / Bulk Upload | 2017-04-05 19:42 | Nisha | 2017-04-05 | 2017-04-10 | Completed
93 | Master / Employee Module / Bulk Upload | 2017-04-05 19:44 | Nisha | 2017-04-06 | 2017-04-10 | Completed
94 | Master / Department Module / Bulk Upload | 2017-04-06 12:01 | Nisha | 2017-04-06 | 2017-04-10 | Completed
95 | Adminend / Roles / Module Permission Management | 2017-05-06 13:43 | Nisha | 2017-05-09 | 2017-05-16 | Completed
96 | Adminend / Roles / Navigation Ordering Management | 2017-05-10 11:34 | Praveen Kumar Singh | 2017-05-10 | 2017-05-18 | Completed
97 | Admin-end / Payment / Payment Sources | 2017-05-16 15:03 | Nisha | 2017-05-17 | 2017-05-18 | Completed
98 | Admin-end / Multi-search Implementation | 2017-05-29 12:45 | Nisha | 2017-05-31 | 2017-05-31 | Completed
99 | Admin-end / Auto Generation of Code / Master Modules | 2017-06-01 20:05 | Nisha | 2017-06-03 | 2017-06-03 | Completed
100 | Admin-end / Auto Generation of Code / Inventory Modules | 2017-06-03 11:54 | Nisha | 2017-06-05 | 2017-06-05 | Completed
101 | Admin-end / Master / Department Change to Equipment Type and Parent Category Name | 2017-06-12 20:18 | Nisha | 2017-06-16 | 2017-06-16 | Completed
102 | Admin-end / Sales / Order / Order Form Changes(Changes Dicussed on Client Side on 28-June-17) | 2017-06-29 19:53 | Nisha | 2017-06-30 | 2017-06-30 | Completed
103 | Admin-end / Sales / Report / Template Implementation | 2017-07-05 14:04 | Nisha | 2017-07-06 | 2017-07-21 | Completed
104 | Admin-end / Sales / Process Management / Food / Process & Template Implementation: | 2017-07-12 12:17 | Nisha | 2017-07-12 | 2017-07-21 | Completed
105 | Master / Invoicing Type / Product Master Alias: | 2017-07-31 12:50 | Nisha | 2017-08-03 | 2017-08-03 | Completed
106 | Master / Invoicing Type / Customer Wise Product: | 2017-07-31 12:53 | Nisha | 2017-08-03 | 2017-08-03 | Completed
107 | Master / Invoicing Type / State Wise Product(UI and Functionality Changes): | 2017-08-01 12:05 | Nisha | 2017-08-01 | 2017-08-01 | Completed
108 | Master / Invoicing Type / Customer Wise Parameters: | 2017-08-03 20:14 | Nisha | 2017-08-05 | 2017-12-28 | Completed
109 | Admin-end / Sales / Process Management / Pharma/ Process & Template Implementation: | 2017-08-08 20:00 | Nisha | 2017-08-09 | 2017-08-09 | Completed
110 | Admin-end / Sales / Process Management / WATER/ Process & Template Implementation | 2017-08-19 17:36 | Nisha | 2017-08-16 | 2017-08-16 | Completed
111 | Admin-end / Sales / Process Management / ENVIRONMENT/ Process & Template Implementation | 2017-08-19 17:37 | Nisha | 2017-08-16 | 2017-08-16 | Completed
112 | Admin-end / Sales / Process Management / HALMET/ Process & Template Implementation | 2017-08-19 17:38 | Nisha | 2017-08-16 | 2017-08-16 | Completed
113 | Admin-end / Sales / Process Management / BUILDING/ Process & Template Implementation | 2017-08-19 17:38 | Nisha | 2017-08-17 | 2017-08-17 | Completed
114 | Admin-end / Sales / Process Management / TEXTILE/ Process & Template Implementation | 2017-08-19 17:39 | Nisha | 2017-08-17 | 2017-08-17 | Completed
115 | Admin-end / Sales / Process Management / AYURVEDIC/ Process & Template Implementation | 2017-08-19 17:39 | Nisha | 2017-08-17 | 2017-08-17 | Completed
116 | Sales / Report / All Deparment / View Report | 2017-08-31 13:08 | Nisha | 2017-09-02 | 2017-09-02 | Completed
117 | Master / Tests / Product Tests / Sorting | 2017-09-18 12:27 | Nisha | 2017-09-19 | 2017-09-19 | Completed
118 | Master / Tests / Product Tests / PDF Print | 2017-10-04 15:32 | Nisha | 2017-09-26 | 2017-09-26 | Completed
119 | Mater / Tests / Bulk Uploading using CSV | 2017-10-04 15:35 | Nisha | 2017-10-07 | 2017-10-07 | Completed
120 | Ruby:Admin-end / Scheduler-end / CRM-end / Scheduling / Jobs | 2017-12-30 12:15 | Ruby | 2017-12-30 | 2018-01-01 | Completed
121 | Praveen-Singh :Admin-end / Approval-end / Amendment of Report after Aprroval(QA) | 2017-12-30 12:29 | Praveen Kumar Singh | 2017-12-30 | 2018-01-03 | Completed
122 | Praveen-Singh:Admin-end /Schedular / Jobs: | 2017-12-30 12:33 | Praveen Kumar Singh | 2017-12-27 | 2017-12-30 | Completed
123 | Praveen-Singh:Admin-end /Schedular / Jobs: | 2017-12-30 12:39 | Praveen Kumar Singh | 2017-12-28 | 2017-12-30 | Completed
124 | Praveen-Singh : Admin-end / MIS / Reports / Daily Booking Detail: | 2017-12-30 12:41 | Praveen Kumar Singh | 2017-12-28 | 2017-12-28 | Completed
125 | Praveen-Singh : Admin-end/Master/Test Parameter: | 2017-12-30 12:47 | Praveen Kumar Singh | 2017-12-27 | 2017-12-30 | Completed
126 | Praveen-Singh: Admin-end / Invoicer-end/ Invoice: | 2017-12-30 15:22 | Praveen Kumar Singh | 2017-12-21 | 2018-01-02 | Completed
127 | Ruby: Admin-end / Master /Test Parameter(Cost and Selling Price Changes): | 2018-01-01 14:42 | Ruby | 2018-01-01 | 2018-01-04 | Completed
128 | Praveen-Singh:Admin-end / MIS / Reports / TAT Report: | 2018-01-01 19:30 | Praveen Kumar Singh | 2018-01-01 | 2018-01-01 | Completed
129 | Praveen-Singh:Software Updation: | 2018-01-01 19:32 | Praveen Kumar Singh | 2018-01-01 | 2018-01-01 | Completed
130 | Ruby : Admin-end / Schedular-end / Assign Job / Schedulling: | 2018-01-02 17:26 | Ruby | 2018-01-04 | 2018-01-04 | Completed
131 | Praveen-Singh : Admin-end / Schedular-end / Assign Job / Schedulling: | 2018-01-04 10:44 | Praveen Kumar Singh | 2018-01-04 | 2018-01-04 | Completed
132 | Praveen-Singh:Software Updation: | 2018-01-04 19:54 | Praveen Kumar Singh | 2018-01-04 | 2018-01-04 | Completed
133 | Ruby : All-end / Reports/ Invoice / Schedulling: | 2018-01-05 11:20 | Ruby | 2018-01-11 | 2018-01-11 | Completed
134 | Praveen-Singh:Admin-end / Reviewer-end / Reports(Pendency Count): | 2018-01-05 15:19 | Praveen Kumar Singh | 2018-01-09 | 2018-01-09 | Completed
135 | Ruby:Admin-end / Scheduler-end / Scheduling / Assign Jobs(Pendency and capacity Column) | 2018-01-06 14:47 | Ruby | 2018-01-11 | 2018-01-11 | Completed
136 | Praveen-Singh:Software Updation: | 2018-01-06 20:08 | Praveen Kumar Singh | 2018-01-06 | 2018-01-06 | Completed
137 | Ruby : Admin-end / Master / Customers(Multiple Mail ID Option-CC): | 2018-01-08 13:06 | Ruby | 2018-01-10 | 2018-01-10 | Completed
138 | Praveen-Singh:Admin-end / MIS Reports / All Reports(Department and Division Wise): | 2018-01-08 14:26 | Praveen Kumar Singh | 2018-01-24 | 2018-01-24 | Completed
139 | Praveen-Singh:Software Updation: | 2018-01-08 19:01 | Praveen Kumar Singh | 2018-01-09 | 2018-01-09 | Completed
140 | Praveen-Singh:All-end / Reports / Generate Reports(Approval by QA) / TAT Reports(Final & Draft): | 2018-01-09 17:28 | Praveen Kumar Singh | 2018-01-12 | 2018-01-12 | Completed
141 | Praveen-Singh:Software Updation: | 2018-01-10 18:53 | Praveen Kumar Singh | 2018-01-10 | 2018-01-10 | Completed
142 | Praveen-Singh:Admin-end / Order-Booker / Job Order PDF Generation(Modification): | 2018-01-11 13:18 | Praveen Kumar Singh | 2018-01-15 | 2018-01-15 | Completed
143 | Ruby:Admin-end / Order-Booker / Order / HOLD Order Booking: | 2018-01-12 16:29 | Ruby | 2018-01-15 | 2018-01-15 | Completed
144 | Praveen-Singh : Admin-end / Tester-end / Invoicer-end / Dispatcher-end / PDF Generation: | 2018-01-15 18:04 | Praveen Kumar Singh | 2018-01-16 | 2018-01-17 | Completed
145 | Praveen-Singh:Software Updation: | 2018-01-15 18:46 | Praveen Kumar Singh | 2018-01-15 | 2018-01-15 | Completed
146 | Ruby : Admin-end / Master / Customer / GST Validation: | 2018-01-16 20:21 | Ruby | 2018-01-17 | 2018-01-19 | Completed
147 | Praveen-Singh:Admin-end / MIS Reports / Sales Reports: | 2018-01-17 13:15 | Praveen Kumar Singh | 2018-01-20 | 2018-01-20 | Completed
148 | Praveen-Singh:Admin-end / MIS Reports / TAT Report: | 2018-01-17 13:21 | Praveen Kumar Singh | 2018-01-17 | 2018-01-17 | Completed
149 | Ruby:Admin-end / Order-Booker / Orders( Inter-laboratory/Compensatory): | 2018-01-19 11:20 | Ruby | 2018-01-20 | 2018-01-20 | Completed
150 | Ruby : All-end / Invoicer-end / Invoices / PO-Wise-Invoicing: | 2018-01-20 18:28 | Ruby | 2018-01-25 | 2018-01-25 | Completed
151 | Ruby : Admin-end / Master / Export to Excel: | 2018-01-25 16:50 | Ruby | 2018-01-30 | 2018-05-23 | Completed
152 | Pratyush:Creation Of Pharma Master for Staging Server: | 2018-01-31 17:08 | Pratyush Singh | 2018-02-01 | 2018-02-01 | Completed
153 | Praveen-Singh:Software Updation: | 2018-02-15 18:46 | Praveen Kumar Singh | 2018-01-18 | 2018-01-18 | Completed
154 | Praveen-Singh:Software Updation: | 2018-02-15 18:47 | Praveen Kumar Singh | 2018-01-22 | 2018-01-22 | Completed
155 | Praveen-Singh:Software Updation: | 2018-02-15 18:48 | Praveen Kumar Singh | 2018-01-24 | 2018-01-24 | Completed
156 | Praveen-Singh:Software Updation: | 2018-02-15 18:50 | Praveen Kumar Singh | 2018-01-29 | 2018-01-29 | Completed
157 | Praveen-Singh:Software Updation: | 2018-02-15 18:50 | Praveen Kumar Singh | 2018-01-31 | 2018-01-31 | Completed
158 | Ruby : Go-Live Process of Helmet Department(Overall Process Testing) | 2018-01-31 15:26 | Ruby | 2018-02-01 | 2018-02-01 | Completed
159 | Praveen-Singh:Uploading of Pharma Master on Staging Server(CSV to Sql Data Uploading): | 2018-01-31 17:06 | Praveen Kumar Singh | 2018-02-02 | 2018-02-02 | Completed
160 | Ruby : Go-Live Process of Building Department(Overall Process Testing) | 2018-02-01 12:32 | Ruby | 2018-02-02 | 2018-02-02 | Completed
161 | Ruby : Go-Live Process of Textile Department(Overall Process Testing) | 2018-02-01 12:34 | Ruby | 2018-02-03 | 2018-02-03 | Completed
162 | Pratyush:Creation Of Helmet Master from Staging Server: | 2018-02-01 12:57 | Pratyush Singh | 2018-02-01 | 2018-02-01 | Completed
163 | Praveen-Singh:Removing of Old Pharma Master: | 2018-02-01 13:00 | Praveen Kumar Singh | 2018-02-02 | 2018-02-02 | Completed
164 | Praveen-Singh:Pharma / Job Order / Stability Notes : | 2018-02-02 18:04 | Praveen Kumar Singh | 2018-02-02 | 2018-02-03 | Completed
165 | Pratyush:Testing Helmet Department ITC Staging Server: | 2018-02-02 18:55 | Pratyush Singh | 2018-02-02 | 2018-02-03 | Completed
166 | Praveen-Singh:In Pharma,Manufacturing license no. is product specific for a particular customer. Booking user will define it at the time of booking according to product category | 2018-02-03 12:38 | Praveen Kumar Singh | 2018-02-03 | 2018-02-03 | Completed
167 | Pratyush:Creation of Ayurvedic Department Master On ITC Ayurvedic Staging Server: | 2018-02-03 15:07 | Pratyush Singh | 2018-02-08 | 2018-02-08 | Completed
168 | Ruby : Go-Live Process of Environment Department(Overall Process Testing) | 2018-02-03 16:31 | Ruby | 2018-02-05 | 2018-02-05 | Completed
169 | Ruby : Go-Live Process of Pharma Department(Overall Process Testing): | 2018-02-05 11:52 | Ruby | 2018-02-06 | 2018-02-06 | Completed
170 | Praveen-Singh:Admin-end / Invoicer-end / Tax Generation according Selected Invoicing-To / Department Due date: | 2018-02-05 12:03 | Praveen Kumar Singh | 2018-02-06 | 2018-02-06 | Completed
171 | Praveen-Singh:Back Date Booking in Pharma Department: | 2018-02-05 12:07 | Praveen Kumar Singh | 2018-02-12 | 2018-02-12 | Completed
172 | Ruby : Go-Live Process of Ayurvedic Department(Overall Process Testing) | 2018-02-07 11:20 | Ruby | 2018-02-13 | 2018-02-13 | Completed
173 | Ruby:Admin-end / Master / Product Test / Adding of Test Parameters / NA Option In Standard Value Type: | 2018-02-07 11:28 | Ruby | 2018-02-08 | 2018-02-08 | Completed
174 | Praveen-Singh:Uploading Of Helmet Master from Live Server: | 2018-02-08 20:07 | Praveen Kumar Singh | 2018-02-08 | 2018-02-12 | Completed
175 | Praveen-Singh:Software Updation: | 2018-02-12 15:21 | Praveen Kumar Singh | 2018-02-12 | 2018-02-12 | Completed
176 | Pratyush:Testing Ayurvedic Department ITC Dev Ayurvedic Staging Server: | 2018-02-12 18:25 | Pratyush Singh | 2018-02-12 | 2018-02-12 | Completed
177 | Praveen-Singh:Mail Body Intergration of All Department Except FOOD: | 2018-02-12 18:32 | Praveen Kumar Singh | 2018-02-13 | 2018-02-13 | Completed
178 | Ruby:Admin-end / Scheduiling-end / Scheduling / Job-Print: | 2018-02-12 18:36 | Ruby | 2018-02-13 | 2018-02-13 | Completed
179 | Praveen-Singh:Uploading of Pharma Master on Live Server: | 2018-02-12 18:45 | Praveen Kumar Singh | 2018-02-17 | 2018-02-17 | Completed
180 | Pratyush:Admin-end/Approval-end / Pharma Report Generation / With-Without Equipment Detail: | 2018-02-12 18:58 | Pratyush Singh | 2018-02-19 | 2018-02-19 | Completed
181 | Ruby : All-end / Invoicer-end / Invoices / Invoice-generation / Checkbox Option: | 2018-02-13 12:01 | Ruby | 2018-02-13 | 2018-02-13 | Completed
182 | Ruby : Display the list of parameters and their amount in the pop up at the time of Generate Invoices on any location to make it easier for user to cross check the rates. | 2018-02-13 12:02 | Ruby | 2018-02-16 | 2018-02-16 | Completed
183 | Praveen-Singh:Software Updation: | 2018-02-15 18:54 | Praveen Kumar Singh | 2018-02-01 | 2018-02-01 | Completed
184 | Praveen-Singh:Software Updation: | 2018-02-15 18:54 | Praveen Kumar Singh | 2018-02-02 | 2018-02-02 | Completed
185 | Praveen-Singh:Software Updation: | 2018-02-15 18:55 | Praveen Kumar Singh | 2018-02-06 | 2018-02-06 | Completed
186 | Praveen-Singh:Software Updation: | 2018-02-15 18:57 | Praveen Kumar Singh | 2018-02-12 | 2018-02-12 | Completed
187 | Ruby:Report format of Ayurvedic will be same as Pharma and Only Header format will be different: | 2018-02-16 11:32 | Ruby | 2018-02-19 | 2018-02-19 | Completed
188 | Pratyush:The signature on the report will be of the last reviewer who confirms irrespective of save(action) count. | 2018-02-16 16:14 | Pratyush Singh | 2018-02-19 | 2018-02-19 | Completed
189 | Praveen-Singh:Invoicing will be done on the basis of parameter name and instrument irresctive of method | 2018-02-19 14:49 | Praveen Kumar Singh | 2018-02-20 | 2018-02-20 | Completed
190 | Ruby:Test Master and Assay Master Category Changes all over the Pharma Section | 2018-02-19 16:57 | Ruby | 2018-02-21 | 2018-02-21 | Completed
191 | Pratyush:Pin Code in Customer Master & Country wise state and city. | 2018-02-19 20:07 | Pratyush Singh | 2018-02-22 | 2018-02-22 | Completed
192 | Praveen-Singh:Signature of User on Order Process Stage-Pharma | 2018-02-20 19:00 | Praveen Kumar Singh | 2018-02-21 | 2018-02-21 | Completed
193 | Praveen-Singh:Software Updation: | 2018-02-20 19:03 | Praveen Kumar Singh | 2018-02-20 | 2018-02-20 | Completed
194 | Praveen-Singh:Pharma User Feedback: | 2018-02-21 19:04 | Praveen Kumar Singh | 2018-02-22 | 2018-02-22 | Completed
195 | Praveen-Singh:Displaying of Department Due Date in Scheduling and Changing of Expected Due date will change the Report DUe date and Department DUe Date | 2018-02-22 15:42 | Praveen Kumar Singh | 2018-02-23 | 2018-02-23 | Completed
196 | Pratyush:Creation of New Role for Master Creation for the Users. | 2018-02-22 17:20 | Pratyush Singh | 2018-02-22 | 2018-02-22 | Completed
197 | Ruby:In Pharma back date booking,at the time of finalization there should be an option to select date of finalization .By default the date of reviewing will be displayed to the the finalizer and date of finalization will be displayed to the Approval to QA. | 2018-02-22 17:33 | Ruby | 2018-02-23 | 2018-02-23 | Completed
198 | Pratyush:Uploading of Ayurvedic Master on Live Server: | 2018-02-23 20:12 | Pratyush Singh | 2018-02-23 | 2018-02-23 | Completed
199 | Praveen-Singh:Reporting and Invoicing Feedbacks: | 2018-02-24 14:30 | Praveen Kumar Singh | 2018-02-24 | 2018-02-24 | Completed
200 | Pratyush:Uploading of Textile Master on Staging Server | 2018-02-24 14:31 | Pratyush Singh | 2018-02-24 | 2018-02-24 | Completed
201 | Pratyush:Search Buttons on all Invoicing Structure | 2018-02-26 13:13 | Pratyush Singh | 2018-02-27 | 2018-02-27 | Completed
202 | Praveen-Singh:Invoice generation will be department wise | 2018-02-26 16:57 | Praveen Kumar Singh | 2018-02-26 | 2018-02-26 | Completed
203 | Ruby:Invoicing Structure for adding rates will be department wise | 2018-02-26 18:27 | Ruby | 2018-02-27 | 2018-03-01 | Completed
204 | Pratyush:Department Filter on Order Number Selectbox in Job Sheet Print in Scheduling | 2018-02-27 15:13 | Pratyush Singh | 2018-02-28 | 2018-02-28 | Completed
205 | Praveen-Singh:Name and Signature Implementation on Helment Order Process Stages.Removing of Equipment Column: | 2018-02-27 15:18 | Praveen Kumar Singh | 2018-02-27 | 2018-02-27 | Completed
206 | Pratyush:In the report format of food, Part -A Sample information the fields with N/A will not be displayed in report. | 2018-02-28 12:52 | Pratyush Singh | 2018-02-28 | 2018-02-28 | Completed
207 | Praveen-Singh:User Assigned Department Wise in Scheduling | 2018-02-28 12:45 | Praveen Kumar Singh | 2018-03-01 | 2018-03-01 | Completed
208 | Pratyush:Ayurvedic Order Process Changes on listed Stages On Web and PDF View: | 2018-03-01 11:24 | Pratyush Singh | 2018-03-05 | 2018-03-05 | Completed
209 | Praveen-Singh:Switching of User Role: | 2018-03-01 18:48 | Praveen Kumar Singh | 2018-03-05 | 2018-03-05 | Completed
210 | Pratyush:Building Order Process Changes on listed Stages On Web and PDF View: | 2018-03-05 16:37 | Pratyush Singh | 2018-03-05 | 2018-03-05 | Completed
211 | Praveen-Singh:Creation and Uploading of Pharma Master on Live Server: | 2018-03-05 16:38 | Praveen Kumar Singh | 2018-03-08 | 2018-03-08 | Completed
212 | Ruby:In all departments, reviewing date will be the current date and report finalization date and report approval to QA date will also be the current date irrespective of report review date. | 2018-03-06 14:46 | Ruby | 2018-03-07 | 2018-03-07 | Completed
213 | Pratyush:Testing of Switching of User Role according to their assigned role/roles | 2018-03-06 18:08 | Pratyush Singh | 2018-03-06 | 2018-03-06 | Completed
214 | Pratyush:Dispatcher Permission to Print an report. | 2018-03-07 19:31 | Praveen Kumar Singh | 2018-03-07 | 2018-03-07 | Completed
215 | Ruby:Report Ammendment- Option to type report ammenment no on the reviewer window and suffix 'A' should be added on the end of report and Date of reviewing and DAte of Completion will be the current date. | 2018-03-07 19:32 | Ruby | 2018-03-12 | 2018-03-12 | Completed
216 | Praveen-Singh:Software Updation: | 2018-03-07 19:43 | Praveen Kumar Singh | 2018-03-07 | 2018-03-07 | Completed
217 | Pratyush:Party Ref Date/Letter Date on Ayurvedic Reports | 2018-03-08 11:39 | Pratyush Singh | 2018-03-08 | 2018-03-08 | Completed
218 | Praveen-Singh:Users Feedback Points: | 2018-03-09 15:40 | Praveen Kumar Singh | 2018-03-09 | 2018-03-09 | Completed
219 | Praveen-Singh:Calculation of Calim Value for Alpha-numeric Value. | 2018-03-12 15:51 | Praveen Kumar Singh | 2018-03-12 | 2018-03-12 | Completed
220 | Pratyush:User Manual Creation-Order and Master Creation | 2018-03-12 18:39 | Pratyush Singh | 2018-03-12 | 2018-03-12 | Completed
221 | Pratyush:Displaying of dispatched detail in Invocier and Dispatcher | 2018-03-12 20:13 | Pratyush Singh | 2018-03-13 | 2018-03-13 | Completed
222 | Ruby:Displaying of Product Master Name in a Product Master Alias in State-Wise-Product and Customer-Wise-Product Invocing | 2018-03-12 20:18 | Ruby | 2018-03-14 | 2018-03-14 | Completed
223 | Praveen:ENV Report PDF:Requirement Label Changes in case of IS:10500 Test Standard in Environment Test Report. | 2018-03-12 20:20 | Praveen Kumar Singh | 2018-03-13 | 2018-03-13 | Completed
224 | Ruby:Displaying of Party Ref. No on Order Process Stage of Ayurvedic Department | 2018-03-14 15:51 | Ruby | 2018-03-14 | 2018-03-14 | Completed
225 | Pratyush:Customer-wise-Parameter Rates Updation: | 2018-03-14 18:13 | Pratyush Singh | 2018-03-14 | 2018-03-14 | Completed
226 | Praveen-Singh:Uploading of Invoicing Rate of State-wise Invoicing Structure in Pharma Deparment | 2018-03-14 20:55 | Praveen Kumar Singh | 2018-03-14 | 2018-03-14 | Completed
227 | Pratyush:Microbiological Signature on Ayurvedic Report | 2018-03-15 14:02 | Pratyush Singh | 2018-03-15 | 2018-03-15 | Completed
228 | Ruby:New Report Format Implementation on Environment Report Template regarding General Parameter seperation | 2018-03-15 14:04 | Ruby | 2018-03-19 | 2018-03-19 | Completed
229 | Praveen-Singh:Uploading of Invoicing Rate-Customer-Wise-Product Invoicing Structure in Pharma Deparment and Addressing of User Feedbacks. | 2018-03-15 14:05 | Praveen Kumar Singh | 2018-03-15 | 2018-03-16 | Completed
230 | Praveen-Singh:Dispalying of Customer-name with Cityname in Submitted By Field in Pharma Test Report | 2018-03-15 19:24 | Praveen Kumar Singh | 2018-03-15 | 2018-03-15 | Completed
231 | Pratyush:In Pharma backdate Booking,Review date will be the default date for further Order Process Stage .i.e in datepicker of Finalizer and Approval | 2018-03-15 19:34 | Pratyush Singh | 2018-03-16 | 2018-03-16 | Completed
232 | Pratyush:Rounding of Standard value from and Standard value to according to Standard Value Type ie Numeric,Alphanumeric,NA in all Departments | 2018-03-17 12:45 | Pratyush Singh | 2018-03-17 | 2018-03-17 | Completed
233 | Praveen-Singh:Uploading of Invoicing Rate-Customer-Wise-Parameter Invoicing Structure in Pharma Deparment and Addressing of User Feedbacks. | 2018-03-17 12:46 | Praveen Kumar Singh | 2018-03-17 | 2018-03-17 | Completed
234 | Praveen-Singh:Cloning of Order Booking as New Order using Save as Option: | 2018-03-19 20:15 | Praveen Kumar Singh | 2018-03-20 | 2018-03-20 | Completed
235 | Pratyush:MIS Report: Daily Invoicing Report as Excel Format | 2018-03-19 20:20 | Pratyush Singh | 2018-03-19 | 2018-03-19 | Completed
236 | Ruby:Integration of Invoice Number in Credit and Debit Note of Payment Module. | 2018-03-20 14:59 | Ruby | 2018-03-21 | 2018-03-21 | Completed
237 | Praveen-Singh:Displaying of Batch No with search in Order Listing and option to refresh the Invoicing Structure at the time of Booking | 2018-03-20 17:40 | Praveen Kumar Singh | 2018-03-21 | 2018-03-21 | Completed
238 | Ruby:Creation of Detector Master according to Equipment. | 2018-03-21 14:23 | Ruby | 2018-03-21 | 2018-03-21 | Completed
239 | Ruby:Test Master Creation(Step-2)-Option to Select Detector in selectbox | 2018-03-21 15:23 | Ruby | 2018-03-23 | 2018-03-23 | Completed
240 | Praveen-Singh:New Invoicing Structure : Customer Wise Assay Parameter-Option for adding of rates using new Customer Wise Assay Parameter form | 2018-03-21 16:11 | Praveen Kumar Singh | 2018-03-24 | 2018-03-24 | Completed
241 | Pratyush:Creation of Test Master for Partial Report and Part-Wise Report | 2018-03-21 20:04 | Pratyush Singh | 2018-03-23 | 2018-03-23 | Completed
242 | Praveen-Singh:Software Updation: | 2018-03-22 17:33 | Praveen Kumar Singh | 2018-03-22 | 2018-03-22 | Completed
243 | Praveen-Singh:Users Feedback Points(Approval and Invoicing): | 2018-03-22 19:30 | Praveen Kumar Singh | 2018-03-22 | 2018-03-22 | Completed
244 | Praveen-Singh:Allowing Order Booking with checking the Invoicing in case of Pharma Department in Customer-wise-Parameter Invoicing and Addressing of User Feedback Points | 2018-03-23 11:52 | Praveen Kumar Singh | 2018-03-23 | 2018-03-23 | Completed
245 | Pratyush:Report Changes in Ayurvedic Department listed in a Hard Copy | 2018-03-23 13:54 | Pratyush Singh | 2018-03-23 | 2018-03-28 | Completed
246 | Pratyush:Department wise Mail Body Intergration changes | 2018-03-23 14:01 | Pratyush Singh | 2018-03-26 | 2018-03-26 | Completed
247 | Pratyush:Invoicer should able to take a print out of report | 2018-03-24 14:45 | Pratyush Singh | 2018-03-27 | 2018-03-30 | Completed
248 | Ruby:All department Except Food : There sholud be a provision to send the report with equipment & Without equipment at the the time of finalization by Finalizer and Dispatcher for printing | 2018-03-24 14:50 | Ruby | 2018-03-28 | 2018-03-28 | Completed
249 | Praveen-Singh:Pharma User Feedback Points: | 2018-03-28 21:08 | Praveen Kumar Singh | 2018-03-29 | 2018-03-29 | Completed
250 | Ruby:Report PDF Format : Error to be Checked - In Order Booking Form if supplied by & manufactured by is blank then on final report Part A system automatically keep submitteb by col. blank. | 2018-03-29 16:03 | Praveen Kumar Singh | 2018-03-29 | 2018-03-30 | Completed
251 | Ruby:Error to be checked :- The sorting of parameter(top & down) is not functioning properly. | 2018-03-30 12:31 | Ruby | 2018-03-30 | 2018-03-30 | Completed
252 | Pratyush:Testing of Order Booking in case of Customer Wise Product/Fixed Rate Invoicing Structure. | 2018-03-30 12:38 | Pratyush Singh | 2018-03-30 | 2018-03-30 | Completed
253 | Ruby:Error to be Checked:- In Scheduling,Job sheet print if user want to leave one col. of of standard value from & to blank then system is not allowing to do that.And Provision to Update Standard Value Type also | 2018-03-30 18:01 | Ruby | 2018-03-31 | 2018-03-31 | Completed
254 | Praveen-Singh:Pharma User Feedback Points: | 2018-03-30 18:10 | Praveen Kumar Singh | 2018-03-30 | 2018-03-30 | Completed
255 | Praveen-Singh:Software Updation: | 2018-03-31 12:26 | Praveen Kumar Singh | 2018-03-31 | 2018-03-31 | Completed
256 | Pratyush:Ayurvedic Report Format Implementation(New Changes): | 2018-03-31 12:46 | Pratyush Singh | 2018-03-31 | 2018-03-31 | Completed
257 | Praveen-Singh:Clearance of Invoicing Issues of all Department | 2018-03-31 19:09 | Praveen Kumar Singh | 2018-03-31 | 2018-03-31 | Completed
258 | Praveen-Singh:Admin-end / MIS Reports / Sample Log Status(Changes): | 2018-01-02 12:47 | Praveen Kumar Singh | 2018-04-25 | 2018-04-25 | Completed
259 | Praveen-Singh:Equipment Sorting and Instrument Wise Performance Detail | 2018-01-29 13:37 | Praveen Kumar Singh | 2018-04-28 | 2018-04-28 | Completed
260 | Ruby:Duplicacy Check- Order Booking Form :- if a sample of particular batch for a corresponding client already exists then then system will display a warning message to the user having the previous order booking date and order no and asked for permission of user to proceed for booking ,. If user press "Yes" then booking will be continued and if user select "No" then booking will not be proceed. | 2018-03-30 12:27 | Ruby | 2018-04-02 | 2018-04-02 | Completed
261 | Pratyush:Ayurvedic-Department:Changing of layout of Viewing of Ayurvedic Order Process Stage and editing with same Format at Reviewer-end | 2018-04-02 14:16 | Pratyush Singh | 2018-04-02 | 2018-04-02 | Completed
262 | Praveen-Singh:Administrator End:- Administrator should have provision to close the receiving of sample if its left unlcosed by the user by mistake. | 2018-04-02 14:22 | Praveen Kumar Singh | 2018-04-02 | 2018-04-02 | Completed
263 | Pratyush:Report Format Implementation(New Changes in all Department): | 2018-04-02 20:09 | Pratyush Singh | 2018-04-04 | 2018-04-04 | Completed
264 | Praveen-Singh:Creation of Food Staging Server for Chennai Team | 2018-04-02 21:09 | Praveen Kumar Singh | 2018-04-02 | 2018-04-02 | Completed
265 | Ruby:Customer Master:- We should incorporate department & branch in customer master to define (billing type,invoicing type,discount type) | 2018-04-02 21:26 | Ruby | 2018-04-06 | 2018-04-06 | Completed
266 | Praveen-Singh:Sample Receiving Code:- Incorporate Location code in sample receiving code same as booking code(i.e 01 for panchkula & 02 for chennai). | 2018-04-04 12:12 | Praveen Kumar Singh | 2018-04-04 | 2018-04-04 | Completed
267 | Praveen-Singh:Signature of invoicer will be displayed on invoices. | 2018-04-04 12:39 | Praveen Kumar Singh | 2018-04-04 | 2018-04-04 | Completed
268 | Praveen-Singh:In invoicing only customer name of corresponding departments will be displayed to the invoicer. | 2018-04-04 13:16 | Praveen Kumar Singh | 2018-04-04 | 2018-04-04 | Completed
269 | Praveen-Singh:Pharma User Feedback Points: | 2018-04-04 19:32 | Praveen Kumar Singh | 2018-04-04 | 2018-04-04 | Completed
270 | Praveen-Singh:The changes done in Customer wise Product is also applicable on State Wise Product. | 2018-04-04 19:41 | Praveen Kumar Singh | 2018-04-05 | 2018-04-05 | Completed
271 | Praveen-Singh:MIS Report :- Add column of current date in MIS report of Pharma. | 2018-04-05 16:08 | Praveen Kumar Singh | 2018-04-05 | 2018-04-05 | Completed
272 | Praveen-Singh:Changes on Invoicing Structure : Customer Wise Assay Parameter-Option for adding of rates using new Customer Wise Assay Parameter form: | 2018-04-06 14:56 | Praveen Kumar Singh | 2018-04-07 | 2018-04-07 | Completed
273 | Praveen-Singh:Pharma User Feedback Points: | 2018-04-04 19:32 | Praveen Kumar Singh | 2018-04-06 | 2018-04-06 | Completed
274 | Ruby:Pharma-: In automailing of Govt. reports we need stamp of Standard Quality & Not of Standard Quality and Roud stamp of ITC with signature of Finalizer. The Stamp type will be depend on the remark selected by the reviewer. Standard Quality :- (a) The sample referred above is of standard quality with respect to above tests only. (b)In the opinion of the undersigned,the sample referred above is of standard quality as defined in the Drugs and Cosmetics Act 1940 and the rules made there under for the reasons given below. Not of Standard quality :- (a) The sample referred above is not of standard quality with respect to above test only. (b)In the opinion of the undersigned,the sample referred above is not of standard quality as defined in the Drugs and Cosmetics Act 1940 and the rules made there under for the reasons given below. | 2018-04-07 12:13 | Ruby | 2018-04-07 | 2018-04-10 | Completed
275 | Pratyush:To be provided:- Remark form to the administrator to add ,remove or edit a new remark department wise. | 2018-04-07 12:24 | Pratyush Singh | 2018-04-06 | 2018-04-07 | Completed
276 | Pratyush:Create master form for the label of these charges,user will select the charges type and add the amount. | 2018-04-07 12:31 | Pratyush Singh | 2018-04-09 | 2018-04-09 | Completed
277 | Praveen-Singh:Pharma User Feedback Points: | 2018-04-04 19:32 | Praveen Kumar Singh | 2018-04-07 | 2018-04-07 | Completed
278 | Praveen-Singh:Customer Wise Assay Parameter integration with Order Booking Form-Option to enter running time as combo box and no of Injection as Input.Also allow user to book an order only if rate is available. | 2018-04-09 11:55 | Praveen Kumar Singh | 2018-04-18 | 2018-04-18 | Completed
279 | Pratyush:Round Off of results:- If claim value will be of decimal point then limit will not be roundoff and decimal place value of limit will be one as of claim value. | 2018-04-10 13:37 | Pratyush Singh | 2018-04-10 | 2018-04-12 | Completed
280 | Ruby:Order module testing regarding Customer Defined Structure | 2018-04-10 13:40 | Ruby | 2018-04-10 | 2018-04-10 | Completed
281 | Ruby:Invoicing Master:- Incorporate branch in all invoicing types to add rates. | 2018-04-10 13:44 | Ruby | 2018-04-13 | 2018-04-13 | Completed
282 | Praveen-Singh:Pharma User Feedback Points: | 2018-04-04 19:32 | Praveen Kumar Singh | 2018-04-12 | 2018-04-12 | Completed
283 | Pratyush:"1.After booking the order if user want to add extra parameter than on claim value section previous added standard value from and to will not showing the calculated value , user need to again click on the tab for calculation claim . 2.In Invoices list section Batch no,discounttype,discount value option needed in the list." | 2018-04-13 15:23 | Pratyush Singh | 2018-04-13 | 2018-04-13 | Completed
284 | Praveen-Singh:Pharma User Feedback Points: | 2018-04-04 19:32 | Praveen Kumar Singh | 2018-04-13 | 2018-04-13 | Completed
285 | Praveen-Singh:Pharma User Feedback Points: | 2018-04-04 19:32 | Praveen Kumar Singh | 2018-04-14 | 2018-04-14 | Completed
286 | Ruby:Connect weekly off with the calculation of expected due date.TAT :- In TAT Report Expected due report will be calculated according to the current date irrespective of current date. | 2018-04-16 15:50 | Ruby | 2018-04-17 | 2018-04-17 | Completed
287 | Praveen-Singh:Pharma User Feedback Points: | 2018-04-04 19:32 | Praveen Kumar Singh | 2018-04-16 | 2018-04-16 | Completed
288 | Pratyush:Pharma:- Limit of Disintegration time will be displayed automatically on the selection of header note. | 2018-04-17 19:53 | Pratyush Singh | 2018-04-17 | 2018-04-17 | Completed
289 | Praveen-Singh:Pharma User Feedback Points: | 2018-04-04 19:32 | Praveen Kumar Singh | 2018-04-17 | 2018-04-17 | Completed
290 | Praveen-Singh:Customer Wise Assay Parameter integration with generation of Invoice | 2018-04-18 21:01 | Praveen Kumar Singh | 2018-04-19 | 2018-04-19 | Completed
291 | Ruby:Testing of Order Modules | 2018-04-18 21:13 | Ruby | 2018-04-30 | 2018-04-30 | Completed
292 | Praveen-Singh:Pharma User Feedback Points: | 2018-04-04 19:32 | Praveen Kumar Singh | 2018-04-19 | 2018-04-19 | Completed
293 | Praveen-Singh:Pharma User Feedback Points: | 2018-04-04 19:32 | Praveen Kumar Singh | 2018-04-20 | 2018-04-20 | Completed
294 | Praveen-Singh:Pharma User Feedback Points: | 2018-04-04 19:32 | Praveen Kumar Singh | 2018-04-21 | 2018-04-21 | Completed
295 | Praveen-Singh:Pharma User Feedback Points and Meeting with Client regarding MIS-Report Discussion | 2018-04-23 19:29 | Praveen Kumar Singh | 2018-04-23 | 2018-04-23 | Completed
296 | Praveen-Singh:Option for Editing of Sample Date in case of Pharma Department | 2018-04-23 19:41 | Praveen Kumar Singh | 2018-04-23 | 2018-04-23 | Completed
297 | Praveen-Singh:Pharma User Feedback Points: | 2018-04-04 19:32 | Praveen Kumar Singh | 2018-04-24 | 2018-04-24 | Completed
298 | Praveen-Singh:TAT Report: Filter by Expected Due Date and Order Process Stage | 2018-04-25 15:53 | Praveen Kumar Singh | 2018-04-25 | 2018-04-25 | Completed
299 | Praveen-Singh:Pharma User Feedback Points: | 2018-04-04 19:32 | Praveen Kumar Singh | 2018-04-26 | 2018-04-26 | Completed
300 | Praveen-Singh:MIS-Report :User Wise Performance Detail and Analyst Summary Report: | 2018-04-26 20:22 | Praveen Kumar Singh | 2018-04-30 | 2018-04-30 | Completed
301 | Praveen-Singh:Software Updation: | 2018-03-22 17:33 | Praveen Kumar Singh | 2018-04-29 | 2018-04-29 | Completed
302 | Praveen-Singh:Pharma User Feedback Points: | 2018-04-04 19:32 | Praveen Kumar Singh | 2018-04-30 | 2018-04-30 | Completed
303 | Praveen-Singh:Integration of DT Limit in Order Module: | 2018-05-02 12:37 | Praveen Kumar Singh | 2018-05-01 | 2018-05-01 | Completed
304 | Praveen-Singh:Instrument Wise Performance Detail(Changes Discuss by Client) | 2018-01-29 13:37 | Praveen Kumar Singh | 2018-05-02 | 2018-05-02 | Completed
305 | Praveen-Singh:Implementation of Branch and Department in Invoice Generation Module: | 2018-05-02 13:06 | Praveen Kumar Singh | 2018-05-02 | 2018-05-02 | Completed
306 | Ruby:Testing of DT Limit Upon Selecting the Header Note: | 2018-05-02 13:14 | Ruby | 2018-05-03 | 2018-05-03 | Completed
307 | Praveen-Singh:Master Creation Process Slow and Mail Sending(Send Mail Issue) | 2018-05-03 20:56 | Praveen Kumar Singh | 2018-05-03 | 2018-05-03 | Completed
308 | Praveen-Singh:User Feedback Points: | 2018-04-04 19:32 | Praveen Kumar Singh | 2018-05-04 | 2018-05-04 | Completed
309 | Praveen-Singh:Software Updation: | 2018-03-22 17:33 | Praveen Kumar Singh | 2018-05-04 | 2018-05-04 | Completed
310 | Ruby:Testing of Order Modules | 2018-04-18 21:13 | Ruby | 2018-05-11 | 2018-05-11 | Completed
311 | Praveen-Singh:User Feedback Points: | 2018-05-05 20:02 | Praveen Kumar Singh | 2018-05-05 | 2018-05-05 | Completed
312 | Praveen-Singh:User Feedback Points: | 2018-05-05 20:02 | Praveen Kumar Singh | 2018-05-07 | 2018-05-07 | Completed
313 | Praveen-Singh:User Feedback Points: | 2018-05-05 20:02 | Praveen Kumar Singh | 2018-05-08 | 2018-05-08 | Completed
314 | Praveen-Singh:Client Feedback Points(Changes Discussed): | 2018-05-05 20:02 | Praveen Kumar Singh | 2018-05-09 | 2018-05-09 | Completed
315 | Praveen-Singh:Client Feedback Points(Changes Discussed): | 2018-05-05 20:02 | Praveen Kumar Singh | 2018-05-10 | 2018-05-10 | Completed
316 | Praveen-Singh : Dynamic Header Implementation:All Department Test Report | 2018-05-11 20:53 | Praveen Kumar Singh | 2018-05-15 | 2018-05-15 | Completed
317 | Praveen-Singh:Client Feedback Points(Changes Discussed): | 2018-05-05 20:02 | Praveen Kumar Singh | 2018-05-11 | 2018-05-11 | Completed
318 | Ruby: Dynamic Header Implementation-Master Creation:Report Section | 2018-05-14 19:03 | Ruby | 2018-05-15 | 2018-05-15 | Completed
319 | Ruby : Testing of Dynamic Header Implementation:All Department(View/PDF) | 2018-05-11 20:53 | Ruby | 2018-05-16 | 2018-05-16 | Completed
320 | Praveen-Singh:Displaying of Right Logo Dynamically on all Test Report Blade: | 2018-05-15 21:14 | Praveen Kumar Singh | 2018-05-16 | 2018-05-16 | Completed
321 | Ruby:Testing of Microbiological Name and Sign on Order Process:All Department except : Pharma | 2018-05-17 11:56 | Ruby | 2018-05-17 | 2018-05-17 | Completed
322 | Praveen-Singh:Client Feedback Points:All Department | 2018-05-17 20:37 | Praveen Kumar Singh | 2018-05-17 | 2018-05-17 | Completed
323 | Praveen-Singh:User Feedback Points & Software Updates on Staging Server | 2018-05-05 20:02 | Praveen Kumar Singh | 2018-05-18 | 2018-05-18 | Completed
324 | Ruby:Implemetation of EXCEL and PDF Download Option on Sale Modules. | 2018-05-18 20:51 | Ruby | 2018-05-21 | 2018-05-21 | Completed
325 | Praveen-Singh:User Feedback Points: | 2018-05-21 19:10 | Praveen Kumar Singh | 2018-05-21 | 2018-05-21 | Completed
326 | Praveen-Singh : Dynamic Header Implementation: Invoicing(All Division) | 2018-05-11 20:53 | Praveen Kumar Singh | 2018-05-24 | 2018-05-24 | Completed
327 | Ruby: Dynamic Header Implementation-Master Creation:Invoicing Section | 2018-05-14 19:03 | Ruby | 2018-05-22 | 2018-05-22 | Completed
328 | Praveen-Singh:User Feedback Points: | 2018-05-21 19:10 | Praveen Kumar Singh | 2018-05-23 | 2018-05-23 | Completed
329 | Ruby : Admin-end / Master / Export to Excel: | 2018-01-25 16:50 | Ruby | 2018-05-24 | 2018-05-24 | Completed
330 | Praveen-Singh:Client Feedback Points: | 2018-05-23 13:47 | Praveen Kumar Singh | 2018-05-23 | 2018-05-23 | Completed
331 | Praveen-Singh:Client Feedback Points: | 2018-05-25 19:25 | Praveen Kumar Singh | 2018-05-25 | 2018-05-25 | Completed
332 | Ruby:Testing of Invoicing Structure Module | 2018-05-25 19:29 | Ruby | 2018-05-25 | 2018-05-25 | Completed
333 | Praveen-Singh:Client Feedback Points: | 2018-05-28 19:55 | Praveen Kumar Singh | 2018-05-28 | 2018-05-28 | Completed
334 | Praveen-Singh:Scope-2 meeting and discussion with Client regarding listed Modules: | 2018-05-29 20:19 | Praveen Kumar Singh | 2018-05-29 | 2018-05-29 | Completed
335 | Praveen-Singh:Client Feedback Points: | 2018-05-30 19:39 | Praveen Kumar Singh | 2018-05-30 | 2018-05-30 | Completed
336 | Praveen-Singh:Document Creation and Client Feedback Points: | 2018-05-31 19:51 | Praveen Kumar Singh | 2018-05-31 | 2018-05-31 | Completed
337 | Praveen-Singh:Small Amendments: | 2018-06-01 19:55 | Praveen Kumar Singh | 2018-06-01 | 2018-06-01 | Completed
338 | Praveen-Singh:Client Feedback Points: | 2018-06-08 19:39 | Praveen Kumar Singh | 2018-06-08 | 2018-06-08 | Completed
339 | Praveen-Singh:Changes discussed in dynamic header Implementation and provided in Mail | 2018-06-11 20:08 | Praveen Kumar Singh | 2018-06-12 | 2018-06-12 | Completed
340 | Ruby:Testing of Changes discussed in dynamic header Implementation and provided in Mail | 2018-06-11 20:08 | Ruby | 2018-06-12 | 2018-06-12 | Completed
341 | Praveen-Singh:Client Feedback Points(Urgent Requirement of 2 MIS Reports) | 2018-06-12 20:27 | Praveen Kumar Singh | 2018-06-16 | 2018-06-16 | Completed
342 | Praveen-Singh:Software Updation: | 2018-03-22 17:33 | Praveen Kumar Singh | 2018-06-14 | 2018-06-14 | Completed
343 | Praveen-Singh:Client Feedback Points: | 2018-06-18 14:48 | Praveen Kumar Singh | 2018-06-18 | 2018-06-18 | Completed
344 | Praveen-Singh:POINT-15:Signature of Reviewer & Finalizer on every page: | 2018-06-18 16:04 | Praveen Kumar Singh | 2018-06-21 | 2018-06-21 | Completed
345 | Praveen-Singh:Client Feedback Points: | 2018-06-19 20:26 | Praveen Kumar Singh | 2018-06-19 | 2018-06-19 | Completed
346 | Ruby : Testing of Date Format in Excel Download on sales Modules | 2018-06-20 12:12 | Ruby | 2018-06-20 | 2018-06-20 | Completed
347 | Ruby(S2):POINT-12-Small Amendments | 2018-06-21 12:31 | Ruby | 2018-06-26 | 2018-06-26 | Completed
348 | Praveen-Singh(S2):POINT-1:Order Booking Cancellation | 2018-06-21 12:40 | Praveen Kumar Singh | 2018-06-25 | 2018-06-25 | Completed
349 | Praveen-Singh:Client Feedback Points: | 2018-06-22 19:02 | Praveen Kumar Singh | 2018-06-22 | 2018-06-22 | Completed
350 | Ruby:POINT-13-Report Format of Chennai | 2018-06-25 15:46 | Ruby | 2018-06-28 | 2018-06-28 | Completed
351 | Praveen-Singh:POINT-10-Digital Signature: | 2018-06-25 15:54 | Praveen Kumar Singh | 2018-06-29 | 2018-06-29 | Completed
352 | Praveen-Singh:Software Updation: | 2018-03-22 17:33 | Praveen Kumar Singh | 2018-06-25 | 2018-06-25 | Completed
353 | Praveen-Singh:Client Feedback Points: | 2018-06-26 21:18 | Praveen Kumar Singh | 2018-06-26 | 2018-06-26 | Completed
354 | Praveen-Singh:Client Feedback Points: | 2018-06-27 20:29 | Praveen Kumar Singh | 2018-06-27 | 2018-06-27 | Completed
355 | Praveen-Singh:Client Feedback Points: | 2018-06-26 21:18 | Praveen Kumar Singh | 2018-06-30 | 2018-06-30 | Completed
356 | Ruby:POINT-7-VOC (Voice of Customer): | 2018-06-28 13:03 | Ruby | 2018-07-03 | 2018-07-03 | Completed
357 | Praveen-Singh:POINT-5-S2-New bill format of Andhra/Telangana | 2018-06-30 11:46 | Praveen Kumar Singh | 2018-07-03 | 2018-07-03 | Completed
358 | Praveen-Singh:POINT-2-Order Confirmation Mail | 2018-07-03 12:58 | Praveen Kumar Singh | 2018-07-06 | 2018-07-06 | Completed
359 | Praveen-Singh:Client Feedback Points: | 2018-06-26 21:18 | Praveen Kumar Singh | 2018-07-06 | 2018-07-06 | Completed
360 | Praveen-Singh:Client Feedback Points: | 2018-06-26 21:18 | Praveen Kumar Singh | 2018-06-30 | 2018-06-30 | Completed
361 | Praveen-Singh:Client Feedback Points(MIS Reports Validation) | 2018-07-09 20:37 | Praveen Kumar Singh | 2018-07-09 | 2018-07-09 | Completed
362 | Praveen-Singh:Client Feedback Points: | 2018-06-26 21:18 | Praveen Kumar Singh | 2018-07-10 | 2018-07-10 | Completed
363 | Praveen-Singh:POINT-8-MIS Reports-(b) Amended Reports: | 2018-07-16 12:28 | Praveen Kumar Singh | 2018-07-16 | 2018-07-16 | Completed
364 | Ruby:POINT-8-MIS-Reports-(e)-Export to Excel Button on master forms: | 2018-07-16 12:43 | Ruby | 2018-07-25 | 2018-07-25 | Completed
365 | Praveen-Singh:Scope-2-POINT-8-MIS Reports-(f)-Daily Sales Report: | 2018-07-16 21:00 | Praveen Kumar Singh | 2018-07-21 | 2018-07-21 | Completed
366 | Praveen-Singh:Client Feedback Points(Customer Wise Product / Customer Wise Parameters): | 2018-07-18 19:25 | Praveen Kumar Singh | 2018-07-19 | 2018-07-19 | Completed
367 | Ruby:POINT-11-S2-Printing of Reports:- | 2018-07-19 12:11 | Ruby | 2018-07-21 | 2018-07-21 | Completed
369 | Praveen-Singh:Scope-2-POINT-14-Cancellation & Regeneration of Invoices:- | 2018-07-20 19:42 | Praveen Kumar Singh | 2018-07-27 | 2018-07-27 | Completed
370 | Ruby:MIS-Reports:Sample Log Status:Display of Counter Detail | 2018-07-21 19:18 | Ruby | 2018-07-23 | 2018-07-23 | Completed
371 | Praveen-Singh:Scope-2-POINT-8-MIS Reports-(d) Report to calculate value of delay reports, released report, delay % &:- | 2018-07-23 13:54 | Praveen Kumar Singh | 2018-07-24 | 2018-07-24 | Completed
372 | Praveen-Singh:Client Feedback Points: | 2018-07-30 13:13 | Praveen Kumar Singh | 2018-07-30 | 2018-07-30 | Completed
373 | Praveen-Singh:S2-POINT-(6) Customer Wise TAT: | 2018-07-30 13:56 | Praveen Kumar Singh | 2018-07-31 | 2018-07-31 | Completed
374 | Praveen-Singh:Client Feedback Points/Software Update(Deleviery On Staging Server): | 2018-07-31 20:22 | Praveen Kumar Singh | 2018-07-31 | 2018-07-31 | Completed
375 | Ruby:POINT-3-Provision of Section Incharge for reviewing of report: | 2018-07-03 12:56 | Praveen Kumar Singh | 2018-08-03 | 2018-08-03 | Completed
376 | Praveen-Singh:POINT-9-Reminders or Pop-Ups Role wise: | 2018-07-06 13:39 | Praveen Kumar Singh | 2018-08-02 | 2018-08-02 | Completed
377 | Praveen-Singh:Scope-2-POINT-8-(c)Sales Report by accounts for reconciliation of invoices: | 2018-07-25 20:27 | Praveen Kumar Singh | 2018-08-03 | 2018-08-03 | Completed
378 | Ruby:Scope-2-POINT-(4)New Report Template of Textile: | 2018-07-26 12:23 | Ruby | 2018-08-01 | 2018-08-01 | Completed
379 | Ruby : Scope-2-POINT-14-a) Credit & Debit Note Generation Invoice wise: | 2018-08-04 15:17 | Praveen Kumar Singh | 2018-08-06 | 2018-08-06 | Completed
380 | Praveen-Singh:Client Feedback Points: | 2018-08-04 20:40 | Praveen Kumar Singh | 2018-08-04 | 2018-08-04 | Completed
381 | Praveen-Singh:Client Feedback Points: | 2018-08-06 13:33 | Praveen Kumar Singh | 2018-08-06 | 2018-08-06 | Completed
382 | Ruby:Testing of Scope-2 task: | 2018-08-07 17:55 | Ruby | 2018-08-28 | 2018-08-28 | Completed
383 | Praveen-Singh:Client Feedback Points: | 2018-08-07 17:56 | Praveen Kumar Singh | 2018-08-08 | 2018-08-08 | Completed
384 | Praveen-Singh:Software Updation: | 2018-03-22 17:33 | Praveen Kumar Singh | 2018-08-09 | 2018-08-09 | Completed
385 | Praveen-Singh:Client Feedback Points: | 2018-08-10 20:08 | Praveen Kumar Singh | 2018-08-10 | 2018-08-10 | Completed
386 | Praveen-Singh:Client Feedback Points:(Points Available in Document) | 2018-08-10 20:08 | Praveen Kumar Singh | 2018-08-13 | 2018-08-13 | Completed
387 | Praveen-Singh:Client Feedback Points: | 2018-08-10 20:08 | Praveen Kumar Singh | 2018-08-16 | 2018-08-16 | Completed
388 | Praveen-Singh:POINT-3-Provision of Section Incharge for reviewing of report: | 2018-07-03 12:56 | Praveen Kumar Singh | 2018-08-21 | 2018-08-21 | Completed
389 | Praveen-Singh:Implementation of Template Design and Testing of Order Process Stage for New Department Water: | 2018-08-21 18:14 | Praveen Kumar Singh | 2018-08-22 | 2018-08-22 | Completed
390 | Ruby:Editing of Sample Name in Pharma and Ayurvedic Department by Reviewer: | 2018-08-22 13:57 | Ruby | 2018-08-22 | 2018-08-22 | Completed
391 | Praveen-Singh:Software Update on ITC Live / Client Feedback Points:: | 2018-08-23 19:35 | Praveen Kumar Singh | 2018-08-23 | 2018-08-23 | Completed
392 | Praveen-Singh:Client Feedback Points:: | 2018-08-24 20:25 | Praveen Kumar Singh | 2018-08-24 | 2018-08-24 | Completed
393 | Rubyy:Description/reference to protocol parameter Editing By Reviewer: | 2018-08-27 13:25 | Ruby | 2018-08-27 | 2018-08-27 | Completed
394 | Praveen-Singh:Client Feedback Points:: | 2018-08-27 19:50 | Praveen Kumar Singh | 2018-08-27 | 2018-08-27 | Completed
395 | Ruby:S2-(NABL Code)-Accreditation Certificate Master Creation and Multilocation Laboratories Master Creation with linking: | 2018-08-28 19:31 | Ruby | 2018-08-29 | 2018-08-31 | Completed
396 | Praveen-Singh:S2-(NABL Code)-Implementation of NABL Scope in Test Parameter Master: | 2018-08-28 19:38 | Praveen Kumar Singh | 2018-08-29 | 2018-08-29 | Completed
397 | Praveen-Singh:Client Feedback Points:: | 2018-08-28 20:21 | Praveen Kumar Singh | 2018-08-28 | 2018-08-28 | Completed
398 | Ruby:Implemetation of NABL Code in all department Test Report Templates in both PDF View and Software View. | 2018-08-30 12:27 | Praveen Kumar Singh | 2018-09-01 | 2018-09-01 | Completed
399 | Praveen-Singh:(S2)-NABL Code Generation at the time of Approving to QA Order Statge: | 2018-08-30 12:28 | Praveen Kumar Singh | 2018-09-01 | 2018-09-01 | Completed
400 | Ruby:Validation of Sales Person creation in Employee Module: | 2018-09-04 15:39 | Praveen Kumar Singh | 2018-09-04 | 2018-09-04 | Completed
401 | Praveen-Singh:Client Feedback Points: | 2018-09-04 15:40 | Praveen Kumar Singh | 2018-09-04 | 2018-09-04 | Completed
402 | Ruby: Testing of Scope-2 Task: | 2018-09-05 13:04 | Ruby | 2018-09-05 | 2018-09-05 | Completed
403 | Praveen-Singh:(S2)-NABL Code Generation at the time of Approving to QA Order Statge(NEW MODIFICATION) | 2018-08-30 12:28 | Praveen Kumar Singh | 2018-09-07 | 2018-09-07 | Completed
404 | Praveen-Singh : Implementation of Decimal Place for Test Result for all Department: | 2018-09-10 16:03 | Praveen Kumar Singh | 2018-09-13 | 2018-09-13 | Completed
405 | Praveen-Singh:Implementation of InvoicingTo provision in Invoice Cancellation & Re-Generation: | 2018-09-13 14:45 | Praveen Kumar Singh | 2018-09-18 | 2018-09-18 | Completed
406 | Praveen-Singh : Implementation Logic of Department Due Date : | 2018-09-13 18:03 | Praveen Kumar Singh | 2018-09-14 | 2018-09-14 | Completed
407 | Praveen-Singh:MIS-Report -User Wise Performance Report: | 2018-09-19 20:22 | Praveen Kumar Singh | 2018-09-20 | 2018-09-20 | Completed
408 | Praveen-Singh:Software Updation: | 2018-03-22 17:33 | Praveen Kumar Singh |  | 2018-09-19 | Completed
409 | Praveen-Singh : Implementation Standard Template in Order Confirmation Mail: | 2018-09-20 14:27 | Praveen Kumar Singh | 2018-09-25 | 2018-09-25 | Completed
410 | Praveen-Singh:Client Feedback Points: | 2018-09-21 21:00 | Praveen Kumar Singh | 2018-09-21 | 2018-09-21 | Completed
411 | Praveen-Singh : Implementation of Chennai Report Format Changes: | 2018-09-25 20:16 | Praveen Kumar Singh | 2018-09-27 | 2018-09-27 | Completed
412 | Praveen-Singh:(S2)-NABL Code Generation Automatically(NEW MODIFICATION) | 2018-09-26 20:00 | Praveen Kumar Singh | 2018-09-28 | 2018-09-28 | Completed
413 | Praveen-Singh:Uploading of NABL Scope Parameters Status in Product Test Detail On ITC Live Server: | 2018-09-29 18:39 | Praveen Kumar Singh | 2018-09-29 | 2018-09-29 | Completed
414 | Praveen-Singh : Blocking of back date booking for Parameters in scope of NABL: | 2018-10-03 12:15 | Praveen Kumar Singh | 2018-10-03 | 2018-10-03 | Completed
415 | Praveen-Singh : MIS-Report Multiple Reports Data Validation | 2018-10-08 17:53 | Praveen Kumar Singh | 2018-10-09 | 2018-10-09 | Completed
416 | Praveen-Singh:Client Feedback Points:: | 2018-10-12 17:07 | Praveen Kumar Singh | 2018-10-12 | 2018-10-12 | Completed
417 | Praveen-Singh:Client Feedback Points:: | 2018-10-12 17:07 | Praveen Kumar Singh | 2018-10-23 | 2018-10-23 | Completed
418 | Praveen-Singh : Regarding provision of section incharge and NABL logo in ERP | 2018-11-02 13:33 | Praveen Kumar Singh | 2018-12-13 | 2018-11-13 | Completed
419 | Praveen-Singh : Regarding test master of food to be used since today | 2018-11-02 13:57 | Praveen Kumar Singh | 2018-11-02 | 2018-11-02 | Completed
420 | Praveen-Singh:Client Feedback Points:: | 2018-11-12 10:49 | Praveen Kumar Singh | 2018-11-12 | 2018-11-12 | Completed
421 | Praveen-Singh:Client Feedback Points:: | 2018-11-12 10:49 | Praveen Kumar Singh | 2018-11-13 | 2018-11-13 | Completed
422 | Praveen-Singh : Regarding updation of New NABL logo in ERP | 2018-11-27 15:01 | Praveen Kumar Singh | 2018-11-27 | 2018-11-27 | Completed
423 | Praveen-Singh:New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(a) In case of "F" also we have to keep NABL logo optional presently it is mandatory: | 2018-11-28 10:38 | Praveen Kumar Singh | 2018-11-28 | 2018-11-28 | Completed
424 | Praveen-Singh : Implementation of Multi Session Script-Stopping User to Open New Tab of Software. | 2018-11-28 15:11 | Praveen Kumar Singh | 2018-11-28 | 2018-11-28 | Completed
425 | Praveen-Singh : New Requirement of NABL ULR no. :: TASK-(c) In case of "F" and "P", we have to define non-NABL scope parameters on the test report using '*' in front of parameter name and one remark will be printed in remark box ('*' represents test parameters not covered under NABL Scope.): | 2018-11-28 19:23 | Praveen Kumar Singh | 2018-11-30 | 2018-11-30 | Completed
426 | Praveen-Singh : New Requirement of NABL ULR no. :: TASK-(d) The reports in which no NABL ULR no. is not defined, we have to use '*' front of all parameter category to represent non NABL scope parameters and one remark will be printed in remark box( '*' represents parameter categories not covered under NABL scope.): | 2018-12-01 19:35 | Praveen Kumar Singh | 2018-12-03 | 2018-12-03 | Completed
427 | Praveen-Singh:New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(e) In case of Outsource sample we have to use '**' to represent parameters tested outside the lab. How to add provision will need discussion.(subcontract user): | 2018-12-03 15:55 | Praveen Kumar Singh | 2018-12-03 | 2018-12-03 | Completed
428 | Praveen-Singh:New Requirement of NABL ULR no.- to be implemented on urgent basis :TASK-(g)For every department we have to keep provision to keep limit column optional by providing check box at the time of "Approval to QA": | 2018-12-03 15:59 | Praveen Kumar Singh | 2018-12-04 | 2018-12-04 | Completed
429 | Praveen-Singh : User-Role-Wise : Implementation of Multi Session Script-Stopping User to Open New Tab of Software. | 2018-11-28 15:11 | Praveen Kumar Singh | 2018-12-06 | 2018-12-06 | Completed
430 | Praveen-Singh:Client Feedback Points:: | 2018-12-07 15:32 | Praveen Kumar Singh | 2018-12-07 | 2018-12-07 | Completed
431 | Praveen-Singh : Regarding Credit Note / Debit Note / Account Sales Report Task | 2018-12-10 20:06 | Praveen Kumar Singh | 2018-12-12 | 2018-12-12 | Completed
432 | Praveen-Singh : STABILITY-MODULE : A)Setting of Stability Order: | 2018-12-18 19:36 | Praveen Kumar Singh | 2018-12-18 | 2018-12-18 | Completed
433 | Praveen-Singh:Software Updation: | 2018-03-22 17:33 | Praveen Kumar Singh |  | 2018-12-19 | Completed
434 | Praveen-Singh : Deactivation of one feature of NABL Notification: | 2018-12-21 19:52 | Praveen Kumar Singh | 2018-12-21 | 2018-12-21 | Completed
435 | Praveen-Singh : STABILITY-MODULE : B) Adding the Stability Order: | 2018-12-24 19:50 | Praveen Kumar Singh | 2019-01-10 | 2019-01-02 | Completed
436 | Ruby : Scope-3 : DOCUMENT-1 : Master-Creation : | 2018-12-27 16:39 | Ruby | 2018-12-28 | 2018-12-28 | Completed
437 | Ruby:Pharma-back Date Booking-Error in saving approving date | 2018-12-29 13:29 | Ruby | 2018-12-29 | 2018-12-29 | Completed
438 | Praveen-Singh : STABILITY-MODULE : B) Adding the Stability Order: | 2018-12-24 19:50 | Praveen Kumar Singh | 2019-01-15 | 2019-01-15 | Completed
439 | Ruby : STABILITY-MODULE : D) Listing the Stability Order: | 2019-01-02 16:41 | Ruby | 2019-01-22 | 2019-01-22 | Completed
440 | Praveen-Singh : STABILITY-MODULE : C) Editing the Stability Order: | 2019-01-10 19:29 | Praveen Kumar Singh | 2019-01-22 | 2019-01-22 | Completed
441 | Praveen-Singh : Deactivation of one feature of NABL Notification | 2019-01-11 18:01 | Praveen Kumar Singh | 2019-01-22 | 2019-01-22 | Completed
442 | Praveen-Singh : STABILITY-MODULE : E) Notification about taking off the Sample from Chamber | 2019-01-16 20:13 | Praveen Kumar Singh | 2019-01-21 | 2019-01-21 | Completed
443 | Ruby:STABILITY-MODULE : B) Adding the Stability Order: Mailing | 2019-01-18 10:44 | Ruby | 2019-01-21 | 2019-01-21 | Completed
444 | Ruby : STABILITY-MODULE : G) Testing: Complete Testing of Stability Modules: | 2019-01-22 11:16 | Ruby | 2019-01-31 | 2019-01-31 | Completed
445 | Praveen-Singh : STABILITY-MODULE : F) PDF Report Format of Stability Modules: | 2019-01-22 11:19 | Praveen Kumar Singh | 2019-01-22 | 2019-01-22 | Completed
446 | Praveen-Singh : Revised Task List 16-Jan-2019 : TASK-(A): Incorporate Branch code in Invoice-No. : | 2019-01-22 12:16 | Praveen Kumar Singh | 2019-01-28 | 2019-01-28 | Completed
447 | Praveen-Singh : Revised Task List 16-Jan-2019 : TASK-(B): Branch code in holiday master: | 2019-01-22 12:18 | Praveen Kumar Singh | 2019-01-25 | 2019-01-25 | Completed
448 | Praveen-Singh : Revised Task List 16-Jan-2019 : TASK-(C): No confirmation mail will be sent to customer on changing of analyst name after Scheduling: | 2019-01-22 12:19 | Praveen Kumar Singh | 2019-01-23 | 2019-01-23 | Completed
449 | Ruby : Revised Task List 16-Jan-2019 : TASK-(D): Incorporation of country in invoicing structure or wherever it is required: | 2019-01-22 12:20 | Ruby | 2019-01-29 | 2019-01-29 | Completed
450 | Praveen-Singh : STABILITY-MODULE : NEW CHANGES : A) Adding the Stability Order: , C)Editing the Stability Order & E)Notification about taking off the Sample from Chamber: | 2019-01-29 11:11 | Praveen Kumar Singh | 2019-01-30 | 2019-01-30 | Completed
451 | Praveen-Singh : STABILITY-MODULE : Client Feedback Points: | 2019-01-30 17:53 | Praveen Kumar Singh | 2019-01-31 | 2019-01-31 | Completed
452 | Ruby : Customer Module : To incorporate emaild(from + option) in customer master export button: | 2019-01-31 15:23 | Ruby | 2019-01-31 | 2019-01-31 | Completed
453 | Praveen-Singh : STABILITY-MODULE : F) PDF Report Format of Stability Modules: | 2019-01-22 11:19 | Praveen Kumar Singh | 2019-02-04 | 2019-02-04 | Completed
454 | Praveen-Singh:Software Updation: | 2018-03-22 17:33 | Praveen Kumar Singh |  | 2019-02-22 | Completed
455 | Praveen-Singh : STABILITY-MODULE : Client Feedback Points: | 2019-02-22 16:18 | Praveen Kumar Singh | 2019-02-27 | 2019-02-27 | Completed
456 | Ruby : STABILITY-MODULE : Client Feedback Points: | 2019-02-22 16:18 | Ruby | 2019-02-25 | 2019-02-25 | Completed
457 | Praveen-Singh : Regarding Customer Wise TAT : | 2019-03-08 12:07 | Praveen Kumar Singh | 2019-03-11 | 2019-03-11 | Completed
458 | Praveen-Singh:Software Updation: | 2018-03-22 17:33 | Praveen Kumar Singh | 2019-03-13 | 2019-03-13 | Completed
459 | Praven-Singh:MIS-Report:TAT:Incorporation of instrument name in TAT Report | 2019-03-19 16:41 | Praveen Kumar Singh | 2019-03-19 | 2019-03-19 | Completed
460 | Praveen-Singh : MIS-Report : TAT : As per our discussion please incorporate these instruments in TAT report. | 2019-03-28 12:00 | Praveen Kumar Singh | 2019-03-28 | 2019-03-28 | Completed
461 | Praveen-Singh : Default Order Process Flow : Regarding Creation of new department in ERP | 2019-03-28 12:07 | Praveen Kumar Singh | 2019-03-28 | 2019-03-28 | Completed
462 | Praveen-Singh : Remove columns Storage name and merge its value with storage condition. In product name please write sample name in place of test master name. | 2019-04-03 11:48 | Praveen Kumar Singh | 2019-04-03 | 2019-04-03 | Completed
463 | Praveen-Singh : MIS-Report : TAT : Regarding problem in approved date | 2019-04-09 12:04 | Praveen Kumar Singh | 2019-04-09 | 2019-04-09 | Completed
464 | Praveen-Singh : STABILITY-MODULE : Back date booking in stability samples | 2019-04-09 12:16 | Praveen Kumar Singh | 2019-04-09 | 2019-04-09 | Completed
465 | Ruby : Invoice-Section : Printing of Reports : All Reports in One PDF : | 2019-04-09 12:35 | Ruby | 2019-04-09 | 2019-04-09 | Completed
466 | Praveen-Singh : Automation of Orders,Order Status,Reports,Invoices of Web Module: | 2019-04-09 15:48 | Praveen Kumar Singh | 2019-04-22 | 2019-04-22 | Completed
467 | Praveen-Singh : Documentation : Quotation/PI Module Process Flow: | 2019-04-12 19:41 | Pratyush Singh | 2019-04-16 | 2019-04-16 | Completed
468 | Praveen-Singh : TAT-Report : Incorporation of instrument name in TAT Report | 2019-04-16 13:19 | Praveen Kumar Singh | 2019-04-16 | 2019-04-16 | Completed
469 | Praveen-Singh : Expected Due Date Calculation : Please update cut off time as 4:30 in place of .01:30 in the calculation of expected due date. | 2019-04-16 13:24 | Praveen Kumar Singh | 2019-04-16 | 2019-04-16 | Completed
470 | Praveen-Singh:Software Updation: | 2019-04-17 18:10 | Praveen Kumar Singh | 2019-04-17 | 2019-04-17 | Completed
471 | Praveen-Singh : Dispatch : Multiple time option to enter dispatching detail for reports & invoices | 2019-04-18 15:29 | Praveen Kumar Singh | 2019-04-19 | 2019-04-19 | Completed
472 | Praveen-Singh : Documentation : Inventory Module Documentation: | 2019-04-22 20:17 | Praveen Kumar Singh | 2019-04-30 | 2019-04-30 | Completed
473 | Praveen-Singh : ITC Web Module : Regarding Automation of Orders,Order Status,Reports,Invoices : Revised List : Changes : | 2019-04-24 20:40 | Praveen Kumar Singh | 2019-04-30 | 2019-04-30 | Completed
474 | Praveen-Singh : Documentation : Inventory Module Documentation: | 2019-04-22 20:17 | Praveen Kumar Singh | 2019-05-31 | 2019-05-31 | Completed
475 | Praveen-Singh : Regarding Accounts Related Task GST: | 2019-04-30 20:14 | Praveen Kumar Singh | 2019-05-06 | 2019-05-06 | Completed
476 | Praveen-Singh : Web-Module : ERP & Customer Module : TRF Creation : | 2019-05-06 20:30 | Praveen Kumar Singh | 2019-05-28 | 2019-05-28 | Completed
477 | Praveen-Singh : Urgent-Task-Regarding Incorporation of Form 50(Test Report Format) in Cosmetics department : | 2019-05-08 19:23 | Praveen Kumar Singh | 2019-05-09 | 2019-05-09 | Completed
478 | Praveen-Singh : Regarding new tasks : | 2019-05-28 21:03 | Praveen Kumar Singh | 2019-05-31 | 2019-05-31 | Completed
479 | Praveen-Singh : Regarding new tasks : | 2019-05-28 21:03 | Praveen Kumar Singh | 2019-06-14 | 2019-06-14 | Completed
480 | Praveen-Singh : Documentation : Inventory Module Documentation: | 2019-04-22 20:17 | Praveen Kumar Singh | 2019-06-30 | 2019-06-30 | Completed
481 | Praven-Singh : Client Feedback Points : | 2019-06-04 20:15 | Praveen Kumar Singh | 2019-06-04 | 2019-06-04 | Completed
482 | Praven-Singh : Regarding changes in test report formats for NABL: | 2019-06-14 16:16 | Praveen Kumar Singh | 2019-06-19 | 2019-06-19 | Completed
483 | Praveen-Singh : Scheduled MIS-TAT | 2019-06-19 20:55 | Praveen Kumar Singh | 2019-06-27 | 2019-06-27 | Completed
484 | Praveen-Singh:Software Updation: | 2019-04-17 18:10 | Praveen Kumar Singh | 2019-06-24 | 2019-06-24 | Completed
485 | Praveen-Singh : NABL Scope Updation from Excel in FOOD & ENV Department: | 2019-06-27 20:31 | Praveen Kumar Singh | 2019-06-27 | 2019-06-27 | Completed
486 | Praveen-Singh : Regarding 9th digit of NABL ULR no. -- Very Very Urgent : | 2019-06-28 13:09 | Praveen Kumar Singh | 2019-06-29 | 2019-06-29 | Completed
487 | Praveen-Singh : Scheduled MIS-TAT | 2019-06-19 20:55 | Praveen Kumar Singh | 2019-07-01 | 2019-07-01 | Completed
488 | Praveen-Singh : Regarding 9th digit of NABL ULR no. -- Very Very Urgent : | 2019-06-28 13:09 | Praveen Kumar Singh | 2019-07-01 | 2019-07-01 | Completed
489 | Praveen-Singh : Regarding multiple access to client in web portal: | 2019-07-01 19:48 | Praveen Kumar Singh | 2019-07-04 | 2019-07-04 | Completed
490 | Praveen-Singh : Regarding report no. in invoice : | 2019-07-05 19:05 | Praveen Kumar Singh | 2019-07-05 | 2019-07-05 | Completed
491 | Praveen-Singh:Software Updation : WEB-PORTAL : | 2019-04-17 18:10 | Praveen Kumar Singh | 2019-07-06 | 2019-07-06 | Completed
492 | Praveen-Singh : ITC Web Module : Client Feedback Points : Changes : | 2019-07-06 21:06 | Praveen Kumar Singh | 2019-07-06 | 2019-07-06 | Completed
493 | Praveen-Singh : MIS-Report : Sales Report Detail and Daily Sales Detail : | 2019-07-08 19:09 | Praveen Kumar Singh | 2019-07-09 | 2019-07-09 | Completed
494 | Praveen-Singh : Regarding new task of Department due date : | 2019-07-10 21:06 | Praveen Kumar Singh | 2019-07-17 | 2019-07-17 | Completed
495 | Praveen-Singh : List of small Tasks : | 2019-07-17 12:39 | Praveen Kumar Singh | 2019-07-20 | 2019-07-20 | Completed
496 | Praveen-Singh : Query hour - 17.07.2019 : | 2019-07-17 13:44 | Praveen Kumar Singh | 2019-07-17 | 2019-07-17 | Completed
497 | Praveen-Singh : Client Feedback Points : TAT Mail Scheduling : | 2019-07-23 17:55 | Praveen Kumar Singh | 2019-07-23 | 2019-07-23 | Completed
498 | Praveen-Singh : Scheduled MIS-TAT : Changes : | 2019-08-01 18:15 | Praveen Kumar Singh | 2019-08-07 | 2019-08-07 | Completed
499 | Praveen-Singh : Regarding Customer master with executive names: | 2019-08-02 20:58 | Praveen Kumar Singh | 2019-08-02 | 2019-08-02 | Completed
500 | Praveen-Singh : Regarding Food Report Format for Others in Panchkula : | 2019-08-07 19:37 | Praveen Kumar Singh | 2019-08-08 | 2019-08-08 | Completed
501 | Praveen-Singh : Regarding Stability Module Formats for DSM (HTML Design): | 2019-08-07 19:40 | Praveen Kumar Singh | 2019-08-09 | 2019-08-09 | Completed
502 | Praveen-Singh : Stability Module Formats for DSM : Changes : | 2019-08-13 19:05 | Praveen Kumar Singh | 2019-08-22 | 2019-08-22 | Completed
503 | Praven-Singh : Regarding Query Hour- 20.08.2019 : | 2019-08-20 16:15 | Praveen Kumar Singh | 2019-08-20 | 2019-08-20 | Completed
504 | Praveen-Singh : Regarding correction of Sales Executive Name Linking in MIS: | 2019-08-22 17:55 | Praveen Kumar Singh | 2019-08-31 | 2019-08-31 | Completed
505 | Praven-Singh : Regarding Query Hour- 30-Aug-2019 : Saving of Booking Sample Amount at the time of Booking an Order: | 2019-08-30 21:03 | Praveen Kumar Singh | 2019-08-30 | 2019-08-30 | Completed
506 | Praven-Singh : Query Hour-30.08.2019 : | 2019-09-02 15:01 | Praveen Kumar Singh | 2019-09-02 | 2019-09-02 | Completed
507 | Praveen-Singh : Software Updation : | 2019-09-03 18:46 | Praveen Kumar Singh | 2019-09-03 | 2019-09-03 | Completed
508 | Praveen-Singh : Regarding Himalaya Monthly Tracker : | 2019-09-04 17:55 | Praveen Kumar Singh | 2019-09-10 | 2019-09-10 | Completed
509 | Praveen-Singh : Client Feedback Points : New errors in existing system after software update : | 2019-09-10 21:06 | Praveen Kumar Singh | 2019-09-12 | 2019-09-12 | Completed
510 | Praveen-Singh : Regarding date change in Microbiologist Signature | 2019-09-13 12:45 | Praveen Kumar Singh | 2019-09-16 | 2019-09-16 | Completed
511 | Praveen-Singh : Changes & Corrections required in Customer Master : | 2019-09-16 16:40 | Praveen Kumar Singh | 2019-09-25 | 2019-09-25 | Completed
512 | Praven-Singh : Integration of User Log Activity Functionality: | 2019-09-21 17:27 | Praveen Kumar Singh | 2019-09-23 | 2019-09-23 | Completed
513 | Praveen-Singh : Correction in Daily Sales Detail : | 2019-09-25 20:56 | Praveen Kumar Singh | 2019-09-25 | 2019-09-25 | Completed
514 | Praven-Singh : Regarding Shifting of ITC Project to New Server | 2019-09-26 21:38 | Praveen Kumar Singh | 2019-09-26 | 2019-09-26 | Completed
515 | Praveen-Singh : Regarding Protocol Review Remarks in all departments other than Pharma : | 2019-09-27 14:04 | Praveen Kumar Singh | 2019-09-27 | 2019-09-27 | Completed
516 | Praveen-Singh : Sales Related MIS-Report Validation Regarding Credit Note Amount : | 2019-12-05 17:37 | Praveen Kumar Singh | 2019-09-10 | 2019-09-10 | Completed
517 | Praveen-Singh : Regarding Very-Very Urgent task of Chennai Branch : | 2019-10-01 19:01 | Praveen Kumar Singh | 2019-10-04 | 2019-10-04 | Completed
518 | Praveen-Singh : Regarding issue in calculation of department due date : | 2019-10-04 20:44 | Praveen Kumar Singh | 2019-10-19 | 2019-10-19 | Completed
519 | Praveen-Singh : ITC New Server : Debugging & Optimization of the SQL Query | 2019-10-16 20:53 | Praveen Kumar Singh | 2019-10-19 | 2019-10-19 | Completed
520 | Praveen-SIngh : Optimization of Report Landing Page according to Role Users : | 2019-10-31 12:27 | Praveen Kumar Singh | 2019-10-31 | 2019-10-31 | Completed
521 | Pravee-Singh : Query hour- 19.10.2019 : Merging of Customer Name and Invoicing Customer Name : | 2019-11-01 17:39 | Praveen Kumar Singh | 2019-11-01 | 2019-11-01 | Completed
522 | Praveen-Singh : Regarding Chennai Report Format : | 2019-11-04 18:27 | Praveen Kumar Singh | 2019-11-22 | 2019-11-22 | Completed
523 | Praveen-Singh : Software Updation : | 2019-09-03 18:46 | Praveen Kumar Singh | 2019-11-08 | 2019-11-08 | Completed
524 | Praveen-Singh : Software Updation : | 2019-09-03 18:46 | Praveen Kumar Singh | 2019-11-25 | 2019-11-25 | Completed
525 | Praveen-Singh : Points to be corrected-Chennai reporting : | 2019-12-04 20:03 | Praveen Kumar Singh | 2019-12-12 | 2019-12-12 | Completed
526 | Praveen-Singh : Client Feedback Points : | 2019-12-09 19:52 | Praveen Kumar Singh | 2019-12-09 | 2019-12-09 | Completed
527 | Praveen-Singh : Software Updation : | 2019-09-03 18:46 | Praveen Kumar Singh | 2019-12-13 | 2019-12-13 | Completed
528 | Praveen-Singh : Test Report : REGARDING STACK REPORT FOR ENVIRONMENT : | 2019-12-16 20:00 | Praveen Kumar Singh | 2019-12-19 | 2019-12-19 | Completed
529 | Praveen-Singh : Regarding Points to be clear : | 2019-12-23 12:47 | Praveen Kumar Singh | 2019-12-31 | 2019-12-31 | Completed
530 | Praveen-Singh : Regarding Points to be clear : Client Feedback Points : | 2019-12-23 12:47 | Praveen Kumar Singh | 2020-01-09 | 2020-01-09 | Completed
531 | Praveen-Singh-Sales Report Detail- To be considered on priority : | 2020-01-15 17:40 | Praveen Kumar Singh | 2020-01-28 | 2020-01-28 | Completed
532 | Praveen-Singh : Software Updation : | 2019-09-03 18:46 | Praveen Kumar Singh | 2020-01-15 | 2020-01-15 | Completed
533 | Praveen-Singh : Database Issue : | 2020-01-22 20:22 | Praveen Kumar Singh | 2020-01-22 | 2020-01-22 | Completed
534 | Praveen-Singh : Regarding Chennai report formats to be incorporated in LIMS : | 2020-01-28 19:50 | Praveen Kumar Singh | 2020-01-31 | 2020-01-31 | Completed
535 | Praveen-Singh : Regarding change approval date to 25.01.2020 from 27.01-QH | 2020-01-29 12:17 | Praveen Kumar Singh | 2020-01-29 | 2020-01-29 | Completed
536 | Praveen-Singh : Regarding Rest of the invoices-QH | 2020-01-29 12:28 | Praveen Kumar Singh | 2020-01-29 | 2020-01-29 | Completed
537 | Praveen-Singh : Regarding Chennai report formats to be incorporated in LIMS : | 2020-01-28 19:50 | Praveen Kumar Singh | 2020-02-24 | 2020-02-24 | Completed
538 | Praveen-Singh : Web Portal : Auto Synchronization of Report/Invoice/VOC using CRON JOB Scheduler : | 2020-02-14 19:44 | Praveen Kumar Singh | 2020-02-15 | 2020-02-15 | Completed
539 | Praveen-Singh : Task List : | 2020-02-18 15:13 | Praveen Kumar Singh | 2020-02-20 | 2020-02-20 | Completed
540 | Praveen-Singh : Changes : APEDA Chennai report formats to be incorporated in LIMS : | 2020-02-24 13:05 | Praveen Kumar Singh | 2020-02-29 | 2020-02-29 | Completed
541 | Praveen-Singh : MIS-Report : Sales Report Detail : Account Sales Detail : Integration of Global Customer Invoicing Name : | 2020-03-17 21:01 | Praveen Kumar Singh | 2020-03-19 | 2020-03-19 | Completed
542 | Praveen-Singh : Implementation of NABL-133 with respect to separate Test Reports for accredited & non-accredited parameters ¦ Integration of Discipline/Group Test Report Format in Panchkula Report | 2020-03-20 21:23 | Praveen Kumar Singh | 2020-03-20 | 2020-03-20 | Completed
543 | Ruby : Implementation of NABL-133 with respect to separate Test Reports for accredited & non-accredited parameters ¦ Integration of Discipline/Group Test Report Format in Panchkula Report | 2020-03-20 21:23 | Ruby | 2020-04-03 | 2020-04-03 | Completed
544 | Ruby : Sales Report Detail- To be considered on priority : | 2020-04-04 19:21 | Ruby | 2020-04-07 | 2020-11-05 | Completed
545 | Ruby : Regarding new task of Employee Sales Target : | 2020-04-09 17:08 | Ruby | 2020-04-10 | 2020-04-10 | Completed
546 | Ruby : Regarding new task -Deactivation provision of duplicacy in Master-Tests Tab : | 2020-04-13 19:38 | Ruby | 2020-04-16 | 2020-04-16 | Completed
547 | Praveen-Singh : Invoices : Correction & Shifting of Invoice Dates : | 2020-04-17 22:16 | Praveen Kumar Singh | 2020-04-20 | 2020-04-20 | Completed
548 | Ruby : Back date provision of Building : | 2020-06-29 15:02 | Ruby | 2020-06-30 | 2020-06-30 | Completed
549 | Praveen-Singh : Regarding Implementation of NABL-133 : | 2020-06-29 15:12 | Praveen Kumar Singh | 2020-07-01 | 2020-07-01 | Completed
550 | Ruby : Testing of NABL-133 : | 2020-06-29 15:12 | Ruby | 2020-07-02 | 2020-07-02 | Completed
551 | Praveen-Singh : Back date provision of Building : Sample,Order and Report Number generation in Back Date Booking : | 2020-06-29 15:02 | Praveen Kumar Singh | 2020-07-04 | 2020-07-04 | Completed
552 | Praveen-Singh : In continuation of NABL 133 task : Order confirmation mail template : | 2020-07-04 20:55 | Praveen Kumar Singh | 2020-07-07 | 2020-07-07 | Completed
553 | Ruby : In continuation of NABL 133 task : Order confirmation mail template : | 2020-07-04 20:55 | Ruby | 2020-07-08 | 2020-07-08 | Completed
554 | Praveen-Singh : ITC CUSTOMER PORTAL && Software Updation : | 2019-09-03 18:46 | Praveen Kumar Singh | 2020-07-14 | 2020-07-14 | Completed
555 | Praveen Singh: Regarding General Information in Environment Report : | 2020-07-28 22:39 | Praveen Kumar Singh | 2020-08-13 | 2020-08-13 | Completed
556 | Praveen-Singh : Back date provision of Building : Sample,Order and Report Number generation in Back Date Booking : Changes : | 2020-06-29 15:02 | Praveen Kumar Singh | 2020-08-13 | 2020-08-13 | Completed
557 | Ruby : Query Hours : Point(d) : | 2020-07-04 20:55 | Ruby | 2020-08-12 | 2020-08-12 | Completed
558 | Praveen-Singh : Query Hours : Point (a) & (c) : | 2020-08-12 20:33 | Praveen Kumar Singh | 2020-08-13 | 2020-08-13 | Completed
559 | Praveen-Singh : Approval-Query Hours : Point (b ) : | 2020-08-17 22:24 | Praveen Kumar Singh | 2020-08-24 | 2020-08-24 | Completed
560 | Praveen-Singh : Regarding updation of sales executive names in LIMS : | 2020-08-14 22:30 | Praveen Kumar Singh | 2020-09-05 | 2020-09-07 | Completed
561 | Praveen-Singh : Sales Executive Names Updation in Customer Master : | 2020-09-09 14:55 | Praveen Kumar Singh | 2020-09-09 | 2020-09-09 | Completed
562 | Praveen-Singh : Budget File Updation in Master Form : | 2020-09-09 22:43 | Praveen Kumar Singh | 2020-09-09 | 2020-09-11 | Completed
563 | Praveen-Singh : Changes in MIS-Report : Daily Sales Report : Adding of Product Category and Sub category in Daily Sales Detail : | 2020-09-09 14:55 | Praveen Kumar Singh | 2020-09-11 | 2020-09-11 | Completed
564 | Praveen-Singh : Test Report : EIC Report Format Implementation : | 2020-09-15 21:39 | Praveen Kumar Singh | 2020-09-30 | 2020-09-30 | Completed
565 | Praveen-Singh : Test Report : EIC Report Format Implementation : | 2020-09-15 21:39 | Praveen Kumar Singh | 2020-10-08 | 2020-10-08 | Completed
566 | Praveen-Singh : Query Hours- 12.10.2020 : | 2020-10-13 22:06 | Praveen Kumar Singh | 2020-10-13 | 2020-10-13 | Completed
567 | Praveen-Singh : Implementation of Financial Year in Invoice Generation: | 2020-10-14 20:51 | Praveen Kumar Singh | 2020-10-27 | 2020-10-27 | Completed
568 | Praveen-Singh : Test Report : EIC Report Format :- New Changes | 2020-10-14 21:12 | Praveen Kumar Singh | 2020-10-15 | 2020-10-15 | Completed
569 | Praveen-Singh : Test Report : Changes on Chennai Report Format:- | 2020-10-16 19:40 | Praveen Kumar Singh | 2020-10-19 | 2020-10-19 | Completed
570 | Praveen-Singh : Software Updation : | 2019-09-03 18:46 | Praveen Kumar Singh | 2020-10-21 | 2020-10-21 | Completed
571 | Praveen-Singh : MIS-Report : Incorporation of Column in Sales Report Detail : | 2020-10-27 19:27 | Praveen Kumar Singh | 2020-10-27 | 2020-10-27 | Completed
572 | Praveen-Singh : MIS-Report : Incorporation of Column in Account Sales Detail : | 2020-10-27 19:27 | Praveen Kumar Singh | 2020-10-28 | 2020-10-28 | Completed
573 | Praveen-Singh : Sales Report Detail- To be considered on priority : Testing and Finalization : | 2020-04-04 19:21 | Praveen Kumar Singh | 2020-11-05 | 2020-11-05 | Completed
574 | Praveen-Singh : Nov-2020-Task-List : Regarding round off of requirement column : | 2020-11-11 16:52 | Praveen Kumar Singh | 2020-11-11 | 2020-11-11 | Completed
575 | Praveen-Singh : Nov-2020-Task-List : Outsource sample ** remark point in Test Report : | 2020-11-11 16:52 | Praveen Kumar Singh | 2020-11-23 | 2020-11-23 | Completed
576 | Praveen-Singh : Sales Executive Names Updation in Customer Master : | 2020-09-09 14:55 | Praveen Kumar Singh | 2020-11-20 | 2020-11-20 | Completed
577 | Praveen-Singh : Nov-2020-Task-List : Employee Sales Target Report : | 2020-11-23 13:16 | Praveen Kumar Singh | 2020-11-26 | 2020-11-26 | Completed
578 | Praveen-Singh : Nov-2020-Task-List : Employee Sales Target Report : | 2020-11-23 13:16 | Praveen Kumar Singh | 2020-12-31 | 2020-12-31 | Completed
579 | Praveen-Singh : Test Report : APEDA Format-Debugging : | 2020-12-18 19:58 | Praveen Kumar Singh | 2020-12-18 | 2020-12-18 | Completed
580 | Praveen-Singh : Regarding result of Pesticide Residue category to be replicated on selection of Copy Button : | 2020-12-22 13:53 | Praveen Kumar Singh | 2020-12-22 | 2020-12-22 | Completed
581 | Praveen-Singh : APEDA Format - Dynamic Fields alignment change in PDF template : | 2020-12-31 18:52 | Praveen Kumar Singh | 2020-12-18 | 2020-12-18 | Completed
582 | Praveen-Singh : Nov-2020-Task-List : Employee Sales Target Report : | 2020-11-23 13:16 | Praveen Kumar Singh | 2021-01-01 | 2021-01-01 | Completed
583 | Praveen-Singh : QH : Regarding Errors in STF of stability protocol: | 2021-02-12 18:15 | Praveen Kumar Singh | 2021-02-12 | 2021-02-12 | Completed

## Summary
Developers
Dev-1 | Praveen Kumar Singh
Dev-2 | Ruby
Dev-3 | Nisha
Dev-4 | Pratyush Singh
Dev-5 | Anjana Garg